Annex 1 – Budget and Implementation Plan

Part – A – Implementation Plan

- Background

As the operational arm of the United Nations Framework Convention on Climate Change (UNFCCC)’s Technology Mechanism, the CTCN received from the UNFCCC the mandate to promote the accelerated transfer of environmentally sound technologies for low carbon and climate resilient development at the request of developing countries (cf. COP decisions 1/CP.16, 2/CP.17, 14/CP.18, and 25/CP.19). To achieve this, the CTCN provides technology solutions, capacity building and technical advice on policy, legal and regulatory frameworks tailored to the needs of individual countries and based on specific country requests submitted by a National Designated Entity (NDE). The CTCN is therefore a demand-driven mechanism; as its services are offered upon request by developing countries, the volume and specific nature of activities ultimately depend on countries’ requirements and needs.

The CTCN is composed of a Climate Technology Centre (CTC) and a Network (cf. COP decision 2/CP.17). The CTCN is hosted by the United Nations Environment Programme (UNEP) in collaboration with the United Nations Industrial Development Organization (UNIDO) and with the support of 12 independent organizations with expertise in climate technologies called ‘CTCN Consortium Partners’.

The CTCN Consortium, including DTU, consists of partner institutions forming a Technical Resource Pool, and is responsible for supporting the CTC Climate Technology Manager in the initial appraisal, refinement, and technical support of requests received through NDEs. When necessary, a small expert team from these institutions is established to support the Climate Technology Manager in responding to a request, prepare a response plan for more in-depth support, and deliver immediate technical assistance assuring a rapid and flexible response and implementation (flexibility and speed that have been one of the main selling points of the UNEP proposal to the UNFCCC). The Consortium Partners, including DTU, also provide support to the CTCN’s capacity building, networking, knowledge sharing and awareness-raising activities.

DTU has been selected to be part of the UNEP-led consortium selected to operate the CTCN by the 196 Parties to the United Nations Framework Convention on Climate Change. DTU’s strong international presence and technical expertise are instrumental in supporting the CTCN, and in enhancing the CTCN capacities to foster the transfer of climate technologies in developing countries.

The purpose of this agreement is to cooperate with DTU in implementing the Response Plan with reference number 2015000070 entitled ‘Catalysing low cost green technologies for sustainable water service delivery’ in the framework of the approved project: Joint UNEP-UNIDO Programme to host and manage the Climate Technology Centre and Network (CTCN).

This agreement contributes to the Climate Change Subprogramme 2016-2017 including Expected Accomplishment (b), “Energy efficiency is improved and the use of renewable energy is increased in partner countries to help reduce greenhouse gas emissions and other pollutants as part of their low emission development pathways”; and Output 6, “Climate technology partnerships and multi-stakeholder networks facilitated to stimulate and encourage the development and transfer of existing and emerging environmentally sound technologies responding to country needs”.

This agreement is consistent with the Memorandum of Understanding (MoU) effective on October, 14th 2013 between UNEP and DTU which is partially reproduced below for convenience.

“2.	The Parties have agreed to the following preliminary overarching themes for this MoU:

a.	Collaborate in the operations of the CTCN. In particular, a Pool member will, at the request of UNEP as represented by the CTC Director and within the constraints of the resources made available by UNEP under a separate legal agreement pursuant to Article 1.2; the in-kind contribution included in UNEP’s CTCN proposal submitted to the UNFCCC in March 2012; and the funding that each Pool member can raise for the relevant purpose:

i.	Appraise and refine requests from National Designated Entities (“NDEs”), deliver immediate technical assistance when requested, and design in-country response plans; or engage in a CTC Expert Team for these purposes;

ii.	Support the design and development of the Knowledge Management System and the Information Portal and their contents;

iii.	Support the development and compilation of training materials for NDEs; and

iv.	Support the development of the Network.”

DTU has an on-going PCA with UNEP (reference number DTIE15-EN011) for a total of US$ 666,000.00 through 31st May 2017 to support the generation of CTCN technical assistance requests, develop response plans and undertake implementation of quick requests up to US$  50,000.00; as well as to support the CTCN’s capacity building, networking, knowledge sharing and awareness-raising activities.

DTU has been selected to jointly implement this agreement, in consideration of its:

- Status of a non-profit organization;

- Established role and relationships in Africa in general, in Kenya in particular; and

- Long-standing, proven substantive expertise in climate technology for adaptation, including in areas of direct relevance to the activities detailed in this agreement: the design, development, implementation and evaluation of strategies and actions that effectively address climate change adaptation and sustainable development needs of developing countries; the development of sustainable financeable frameworks and private sector engagement in adaptation technologies.

- Definitions

In accordance with COP decision 25/CP.19,

(a) “Convention” means the United Nations Framework Convention on Climate Change (UNFCCC);

(b) “COP” means the Conference of the Parties to the Convention;

(c) “CTCN” means the Climate Technology Centre and Network formed by a Climate Technology Centre (CTC) and a Network managed by the CTC;

(d) “CTC” means the Climate Technology Centre that is hosted by the United Environment Programme (UNEP) in collaboration with the United Nations Industrial Development Organization (UNIDO) and supported by a technical resource pool formed by 11 institutions;

(e) “Technical resource pool” means the 11 partner institutions that with UNEP and UNIDO submitted to the UNFCCC a proposal to host the CTCN;

(f) “Network” means the collection of institutions and other entities established in accordance with the criteria approved by the Advisory Board for the designation of members of the Network and its structure;

(g) ”Advisory Board” means the Advisory Board of the CTCN;

(h) “National designated entity” (NDE) means the national entity designated under decision 4/CP.13.

- Objective of the SSFA

Kenya requested support from the CTCN to catalyze low cost green technologies for sustainable water service delivery in northern Kenya. The technical assistance implemented by DTU will aim to analyse the feasibility and sustainability of the deployment of 3 specific low-cost green technologies for improved water services for household consumption, farming and/or irrigation, in underserviced ASAL areas in Northern Kenya and in peri-urban areas. These main outputs are as follows:

- Prioritization of identified technologies and selection of three green water technologies adapted to targeted areas ;

- A pre-feasibility study to determine the technical, economic and social feasibility of the three selected water technologies for the targeted areas;

- The development of a concept note to trigger future funding (i.e. to enable piloting of technologies, supporting implementation of PPP etc.);

- A final report summarizing all activities and outputs and presenting the main conclusions and recommendations for future action.

- Activities

Activity 1 – Prioritization of technology options

The technologies selected (Solar water pumping system, wind powered pumping systems, Sand dams, Djabias, Water pans) are prioritized by the proponent, and three technologies are selected for further analysis under this response plan. In case other relevant technologies have been omitted from the pre-selection they may be added to the rapid prioritization/selection exercise.

The proponent undertakes rapid prioritization exercise and identifies three technologies with most PPP relevance for further analysis. A list of criteria and a simplified Multi-Criteria Analysis (MCA) template will be shared with proponent to facilitate the identification of technologies.

| Deliverables | Delivery date |
| --- | --- |
| Final list of selected technologies | 30th September 2016 |

Activity 2 – Development of Feasibility study of the selected technologies

Pre-feasibility studies are undertaken in order to determine the technical, economic and social feasibility of each of the three selected water technologies for the targeted areas. This entails in-depth analysis of the current experience with each of the technologies in target areas and/or similar contexts (similar technologies applied in other parts of the world), with focus on technical feasibility (types of techniques and materials, skills and knowledge, potential providers etc.), economic feasibility (cost effectiveness, price of materials, potential to create employment, operation and maintenance costs, current demand and supply etc.), social feasibility of the chosen technologies (acceptability, attitude and perception of the technology, land-use patterns, capacity to absorb, gender and governance issues etc.), risk analysis as well as sustainability and replicability potential.

Activity 2.1 – Identification and consultation of relevant stakeholders for the framing of the feasibility study

Expert(s) identify main stakeholders to be involved in consultations and interviews in close collaboration with proponent. Expert(s) consults with proponents and relevant stakeholder to finalize framing, content, research questions and methodology of feasibility study. The target area(s) (in ASAL and peri-urban areas) for the feasibility study is/are identified in collaboration with proponents, based on relevance for the identified technologies, prior knowledge and WSTF (Water Services Trust Fund – the proponent of this response plan) work undertaken in these areas, local vulnerability and other potential considerations. The concrete steps, planned activities, timing and logistics are also discussed.

| Deliverables | Delivery date |
| --- | --- |
| Report on agreed feasibility study framework | 15th October 2016 |

Activity 2.2 - Data Collection

Expert conducts desk study where available documents (scientific articles, reports, surveys etc.) covering relevant topics related to the chosen technologies (e.g. on current experience with these in Kenya and other countries, technology briefs etc.), the national water sector policy context in Kenya, the local context in selected areas (socio-economic context, water sector, land-use patterns, governance etc.) etc.

This first secondary data collection phase is followed by a primary data collection phase for qualitative study. This exercise covers: Choice of data collection methods; Selection of interviewees, development of interview guides/questionnaires and interviews/focus groups with relevant stakeholders (water service providers (WSPs), technology providers, water Service Board (WSB), Water Resources User Associations-WRUAs CBOs etc.) are held by expert. List of interviewees and interview guides is included in final report as annex.

| Deliverables | Delivery date |
| --- | --- |
| List of interviewees and interview guides | 30th November 2016 |

Activity 2.3 - Data analysis and submission of final feasibility study report

Data analysis and draft of feasibility report. The report should be 30-50 pages conveying clear, concise and accurate information. The report may include but need not be restricted to:

- Executive summary

- Introduction

- Methodology section

- Technology description (e.g. types of techniques, skills and knowledge required, current experience with the technologies in target areas and with similar technologies applied in other parts of the world, potential providers, etc.).

- Economic feasibility (e.g. economic viability of technology, cost effectiveness, potential to create employment, operation and maintenance costs etc.).

- Social feasibility of the chosen technologies (e.g. acceptability attitude and perception of the technology, consideration of gender and youth issues (i.e. involvement of women in local water management etc.) land-use patterns, capacity to absorb, gender and governance issues etc.).

- Risk analysis

- Sustainability and replicability potential

- Findings: PPP potential and Recommendations

- Annexes: list of interviewees, interview guides etc.

Submission of feasibility report to proponents, CTCN and other potential stakeholders for comments followed by submission of final report.

| Deliverables | Delivery date |
| --- | --- |
| Final Feasibility study report | 28th February 2017 |

Activity 3 – Training in and identification of potential PPP

Based on outcomes from feasibility study, multi-stakeholder consultations are conducted to identify potential private sector actors and approaches to Public Private Partnerships (PPP) and involved actors from public and private sectors are capacitated to engage in PPP for the deployment of the selected water technologies and make informed investments in the domain. This activity will be implemented together with a network member of the CTCN, yet to be determined. While the coordination of activity 3 is the responsibility of DTU, the deliverable will be submitted by the network member, after review of the NDE and DTU.

Activity 3.1 - Identification and consultation of relevant stakeholders

In collaboration with proponents relevant public and private actors (investors, SMEs etc.) for PPP are identified and multi-stakeholder consultations are conducted to identify PPP opportunities within the water sector and selected technologies.

| Deliverables | Delivery date |
| --- | --- |
| List of stakeholders identified | 28th February 2017 |
| Consultation report | 15th April 2017 |

Activity 3.2 - Design of a PPP business model

Based on outcomes from feasibility study and consultations a PPP business model for selected water technology(ies) most apt for PPPis developed and shared with WSTF, private sector actor and other relevant stakeholders.

| Deliverables | Delivery date |
| --- | --- |
| Public Private Partnership Business model for selected water technology | 30th April 2017 |

Activity 3.3 - Conduct workshop on feasibility study outcomes and training of actors in PPP for selected green water technologies

A 1-day-workshop is held to communicate feasibility report outcomes to stakeholders identified in activity 3.1 and to train actors (WSTF and other identified private and public sector actors) to engage in - and implement - PPP in general for the deployment of selected green water technologies and present business model as an example.

| Deliverables | Delivery date |
| --- | --- |
| Workshop report | 15th May 2017 |

Activity 4 – Catalyzing finance

Activity 4.1 - Development of a project concept note

A concept note for future projects to build on outputs and outcomes from current technical assistance, is developed by expert in close collaboration with proponents and relevant stakeholders (i.e. to enable piloting of technologies, supporting implementation of PPP, etc.). The concept note should thus contribute to the overall long-term objective of this assistance: to strengthen access to - and sustainable financing of - green water technologies for underserved ASAL and peri-urban areas.

| Deliverables | Delivery date |
| --- | --- |
| Project concept note | 30th June 2017 |

Activity 4.2 - Identification of future funding opportunities

Based on the outcomes and recommendations of the feasibility study and the concept note, the expert will support WSTF in approaching different kinds of funding. The expert will identify national (private and public), bilateral, regional and/or international financing resources and elaborate a list of potential future funding opportunities and/or provide referrals to potential funding opportunities. This activity will also include a short report (10-15 pages) containing recommendations for future funding for clean water technologies and specifically the technology prioritized in Activity 1.1. This report will also include examples of fundraising initiative in the clean water sector in other developing countries.

| Deliverables | Delivery date |
| --- | --- |
| List of potential funding institutions | 30th June 2017 |
| Recommendations for future funding report | 31st July 2017 |
| 50 copies of the recommendation report | 31st July 2017 |

Activity 4.3 – Draft recommendations for future actions

Draft of final CTCN assistance report by expert, summarizing all activities, outputs and expected outcomes under the current assistance, presenting the main conclusions and recommendations for future action, including links with other initiatives, examples of good practice in other countries, future initiatives needed to capitalize on current assistance (e.g. based on concept note and other options). The report is printed and disseminated with relevant actors.

| Deliverables | Delivery date |
| --- | --- |
| Final report of activities and outputs of assistance and recommendations for future action (including layout) | 31st August 2017 |
| Print and shipment of 300 copies of the report | 31st August 2017 |

Activity 5 – Evaluation and Learning

Activities progress and deliverables will be monitored closely by the DTU with the collaboration of the National Designated Entity (NDE) in Kenya and CTCN. DTU is responsible for verifying project progress against timeline and associated milestones and communicates these results to the NDE and CTCN. At the end of each activity, DTU will provide a short summary of lessons learned of the activity reflecting on the progress, successes and challenges encountered during the activity. Every month a teleconference with country and international partners is held to communicate the state of advancement of the project, challenges, possible needs for adjustments etc. DTU is responsible for planning these.

| Deliverables | Delivery date |
| --- | --- |
| Short summary about lessons learned in activity 2 | 28th February 2017 |
| Short summary about lessons learned in activity 3 | 15th May 2017 |
| Short summary about lessons learned in activity 4 | 31st August 2017 |

Summary – Implementation period

| Start date | Date of counter-signature |
| --- | --- |
| End date | 31st August 2017 |

Annex 1 – Budget and Implementation Plan – Part B – Activity Based Budget

| IP codes | Cost Category | Description | Quantity | Unit | Unit Cost (US$) | 2016 (US$) | 2017 (US$) | Total cost (US$) |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Activity 1: Prioritization of technology options |  |  |  |  |  |  |  |  |
|  | Activity 1.1: Priorization of technologies |  |  |  |  |  |  |  |
|  | Personnel cost |  |  |  |  |  |  |  |
|  | Technology MCA expert | Provide criteria and simplified MCA template | 0.5 | Person day | 800 | 400 | 0 | 400 |
| 78101010 | Sub-total Personnel |  |  |  |  | 400 | 0 | 400 |
| Activity 1 Total |  |  |  |  |  | 400 | 0 | 400 |
| Activity 2: Development of Feasibility study of the selected technologies |  |  |  |  |  |  |  |  |
|  | Activity 2.1: Identification and consultation of relevant stakeholders for the framing of the feasibility study |  |  |  |  |  |  |  |
|  | Personnel cost |  |  |  |  |  |  |  |
|  | Water Expert / Overall coordinator | Helps with development of feasibility study framework and supervision and coordination of activity | 12 | Person day | 800 | 9,600 | 0 | 9,600 |
| 78101010 | Sub-total Personnel |  |  |  |  | 9,600 | 0 | 9,600 |
|  | Consultant cost |  |  |  |  |  |  |  |
|  | National coordinator - Water expert with gender expertise: UN fee table, level B | Identification of stakeholders, target area, development of feasibility study framework, including gender dimensions | 15 | Person day | 380 | 5,700 | 0 | 5,700 |
| 78101010 | Sub-total Consultant |  |  |  |  | 5,700 | 0 | 5,700 |
|  | Travel cost |  |  |  |  |  |  |  |
|  | In country travel | Cost related to the mission to identify target area identification and preparation (time required: 5 days) | 1 | Lump sum | 1,250 | 1,250 | 0 | 1,250 |
|  | DSA Nairobi/Kenya | DSA for national consultant | 5 | DSA | 200 | 1,000 | 0 | 1,000 |
|  | Plane Ticket for international expert | Round trip ticket from Copenhagen to Kenya including terminal expenses | 1 | Ticket | 1,500 | 1,500 | 0 | 1,500 |
|  | DSA Nairobi/Kenya | DSA for international water expert | 5 | DSA | 312 | 1,560 | 0 | 1,560 |
| 78102010 | Sub-total Travel |  |  |  |  | 5,310 | 0 | 5,310 |
| Sub-total Activity 2.1 |  |  |  |  |  | 20,610 | 0 | 20,610 |
|  | Activity 2.2: Data Collection |  |  |  |  |  |  |  |
|  | Personnel cost |  |  |  |  |  |  |  |
|  | Water Expert / Overall coordinator | Helps with the choice of data collection methods, interview guides, desk study etc. | 10 | Person day | 800 | 8,000 | 0 | 8,000 |
| 78101010 | Sub-total Personnel |  |  |  |  | 8,000 | 0 | 8,000 |
|  | Consultant cost |  |  |  |  |  |  |  |
|  | National coordinator - Water expert with gender expertise: UN fee table, level B | Coordinates and conducts primary and secondary data collection | 30 | Person day | 380 | 11,400 | 0 | 11,400 |
| 78101010 | Sub-total Consultant |  |  |  |  | 11,400 | 0 | 11,400 |
|  | Travel cost |  |  |  |  |  |  |  |
|  | DSA Kenya | DSA for national consultant during visits in the northern part of Kenya and ASAL region; DSA calculated on average for Kenya | 25 | DSA | 200 | 5,000 | 0 | 5,000 |
| 78102010 | Sub-total Travel |  |  |  |  | 5,000 | 0 | 5,000 |
|  | Contractual services |  |  |  |  |  |  |  |
|  | In-country travel (car rental) | Costs to transportation (car rental) to Field visits to conduct interviews (25 days are needed for this activity) | 1 | Lumpsum | 6,250 | 6,250 | 0 | 6,250 |
| 78103010 | Sub-total Contractual services |  |  |  |  | 6,250 | 0 | 6,250 |
| Sub-total Activity 2.2 |  |  |  |  |  | 30,650 | 0 | 30,650 |
|  | Activity 2.3: Data Analysis & draft and submission of feasibility report |  |  |  |  |  |  |  |
|  | Personnel cost |  |  |  |  |  |  |  |
|  | Water Expert / Overall coordinator | Helps with data analysis draft of feasibility study, review of final doc. | 15 | Person day | 800 | 0 | 12,000 | 12,000 |
| 78101010 | Sub-total Personnel |  |  |  |  | 0 | 12,000 | 12,000 |
|  | Consultant cost |  |  |  |  |  |  |  |
|  | National coordinator - Water expert with gender expertise: UN fee table, level B | Conducts data analysis (including gender dimensions), development of feasibility report and submission of final report | 50 | Person day | 380 | 0 | 19,000 | 19,000 |
| 78101010 | Sub-total Consultant |  |  |  |  | 0 | 19,000 | 19,000 |
| Sub-total Activity 2.3 |  |  |  |  |  | 0 | 31,000 | 31,000 |
| Activity 2 Total |  |  |  |  |  | 51,260 | 31,000 | 82,260 |
| Activity 3: Training in and identification of potential PPP |  |  |  |  |  |  |  |  |
|  | Activity 3.1: Identification and consultation of relevant stakeholders |  |  |  |  |  |  |  |
|  | Personnel cost |  |  |  |  |  |  |  |
|  | Water Expert / Overall coordinator | Supports PPP experts and in charge of overall coordination and links with earlier activities | 1 | Person day | 743 | 0 | 743 | 743 |
| 78101010 | Sub-total Personnel |  |  |  |  | 0 | 743 | 743 |
|  | Consultant cost |  |  |  |  |  |  |  |
|  | National coordinator - Water expert with gender expertise: UN fee table, level B | Coordinates identification of PPP stakeholders and participates in consulations and consultation report | 10 | Person day | 380 | 0 | 3,800 | 3,800 |
| 78101010 | Sub-total Consultant |  |  |  |  | 0 | 3,800 | 3,800 |
| Sub-total Activity 3.1 |  |  |  |  |  | 0 | 4,543 | 4,543 |
|  | Activity 3.2: Design of a PPP business model |  |  |  |  |  |  |  |
|  | Personnel cost |  |  |  |  |  |  |  |
|  | Water Expert / Overall coordinator | Supports PPP experts in overall coordination and links with earlier activities | 1 | Person day | 743 | 0 | 743 | 743 |
| 78101010 | Sub-total Personnel |  |  |  |  | 0 | 743 | 743 |
|  | Consultant cost |  |  |  |  |  |  |  |
|  | National coordinator - Water expert with gender expertise: UN fee table, level B | Participates in PPP business model design and review | 5 | Person day | 380 | 0 | 1,900 | 1,900 |
| 78101010 | Sub-total Consultant |  |  |  |  | 0 | 1,900 | 1,900 |
| Sub-total Activity 3.2 |  |  |  |  |  | 0 | 2,643 | 2,643 |
|  | Activity 3.3: Conduct workshop on feasibility study outcomes and training of actors in PPP for selected green water technologies |  |  |  |  |  |  |  |
|  | Personnel cost |  |  |  |  |  |  |  |
|  | Water Expert / Overall coordinator | Participates in Workshop preparation, Presentation of outcomes from feasibility study | 5 | Person day | 800 | 0 | 4,000 | 4,000 |
| 78101010 | Sub-total Personnel |  |  |  |  | 0 | 4,000 | 4,000 |
|  | Consultant cost |  |  |  |  |  |  |  |
|  | National coordinator - Water expert with gender expertise: UN fee table, level B | Organizes Workshop, presentations | 10 | Person day | 380 | 0 | 3,800 | 3,800 |
| 78101010 | Sub-total Consultant |  |  |  |  | 0 | 3,800 | 3,800 |
|  | Travel : workshop in Nairobi for 2 days |  |  |  |  |  |  |  |
|  | Plane Ticket for international expert | Round trip ticket from Copenhagen to Nairobi, incl. terminal expenses | 1 | Ticket | 1,500 | 0 | 1,500 | 1,500 |
|  | DSA Nairobi/Kenya | DSA for international water expert: 1 expert * 5 days (including preparation of the workshop) | 5 | DSA | 312 | 0 | 1,560 | 1,560 |
|  | Travel for some participants | Round trip local travel | 15 | Ticket | 150 | 0 | 2,250 | 2,250 |
|  | DSA Nairobi/Kenya (reduced rate) | DSA for participants from outside Nairobi: 5-10 participants for 2 days (reduced DSA due to budget restriction) | 15 | DSA | 123 | 0 | 1,845 | 1,845 |
|  | Venue cost | Rental meeting room and equipment, and workshop material | 1 | lump sum | 2,000 | 0 | 2,000 | 2,000 |
|  | Catering | Lunches and coffee breaks for 65 people for 2 days | 130 | cost/part | 20 | 0 | 2,600 | 2,600 |
| 78102010 | Sub-total Travel |  |  |  |  | 0 | 11,755 | 11,755 |
| Sub-total Activity 3.3 |  |  |  |  |  | 0 | 19,555 | 19,555 |
| Activity 3 Total |  |  |  |  |  | 0 | 26,741 | 26,741 |
| Activity 4: Catalyze finance |  |  |  |  |  |  |  |  |
|  | Activity 4.1: Development of a project concept note |  |  |  |  |  |  |  |
|  | Personnel cost |  |  |  |  |  |  |  |
|  | Finance expert | Development of concept note for future projects | 10 | Person day | 800 | 0 | 8,000 | 8,000 |
|  | Water Expert / Overall coordinator | Reviews concept note and supports PPP experts in overall coordination and links with earlier activities | 2 | Person day | 743 | 0 | 1,486 | 1,486 |
| 78101010 | Sub-total Personnel |  |  |  |  | 0 | 9,486 | 9,486 |
|  | Consultant cost |  |  |  |  |  |  |  |
|  | National coordinator - Water expert with gender expertise: UN fee table, level B | Participates in concept note development, review | 10 | Person day | 380 | 0 | 3,800 | 3,800 |
| 78101010 | Sub-total Consultant |  |  |  |  | 0 | 3,800 | 3,800 |
| Sub-total Activity 4.1 |  |  |  |  |  | 0 | 13,286 | 13,286 |
|  | Activity 4.2: Identification of future funding opportunities |  |  |  |  |  |  |  |
|  | Personnel cost |  |  |  |  |  |  |  |
|  | Finance expert | Identification and approach of different sources of potential funding opportunities, recommendation report | 15 | Person day | 800 | 0 | 12,000 | 12,000 |
| 78101010 | Sub-total Personnel |  |  |  |  | 0 | 12,000 | 12,000 |
|  | Consultant cost |  |  |  |  |  |  |  |
|  | National coordinator - Water expert with gender expertise: UN fee table, level B | Review recommendation report | 5 | Person day | 380 | 0 | 1,900 | 1,900 |
| 78101010 | Sub-total Consultant |  |  |  |  | 0 | 1,900 | 1,900 |
| Sub-total Activity 4.2 |  |  |  |  |  | 0 | 13,900 | 13,900 |
|  | Activity 4.3: Draft Rrecommendations for future actions |  |  |  |  |  |  |  |
|  | Personnel cost |  |  |  |  |  |  |  |
|  | Water Expert / Overall coordinator | Elaboration of final assistance report | 15 | Person day | 800 | 0 | 12,000 | 12,000 |
|  | Finance expert | Review of final assistance report | 2 | Person day | 800 | 0 | 1,600 | 1,600 |
| 78101010 | Sub-total Personnel |  |  |  |  | 0 | 13,600 | 13,600 |
|  | Consultant cost |  |  |  |  |  |  |  |
|  | National coordinator - Water expert with gender expertise: UN fee table, level B | Participates in elaboration of final assistance report | 10 | Person day | 380 | 0 | 3,800 | 3,800 |
| 78101010 | Sub-total Consultant |  |  |  |  | 0 | 3,800 | 3,800 |
|  | Contractual services |  |  |  |  |  |  |  |
|  | Printing | Print of 200 copies of the report, including layout | 1 | Lump Sum | 3,000 | 0 | 5,000 | 5,000 |
| 78103010 | Sub-total Contractual services |  |  |  |  | 0 | 5,000 | 5,000 |
| Sub-total Activity 4.3 |  |  |  |  |  | 0 | 22,400 | 22,400 |
| Activity 4 Total |  |  |  |  |  | 0 | 49,586 | 49,586 |
| Activity 5: Evaluation & Learning |  |  |  |  |  |  |  |  |
|  | Personnel costs |  |  |  |  |  |  |  |
|  | Water Expert / Overall coordinator | undertakes monthly monitoring and reporting to CTCN and drafts activity short summary on lessons learned | 14 | Person day | 800 | 0 | 11,200 | 11,200 |
| 78101010 | Sub-total Personnel |  |  |  |  | 0 | 11,200 | 11,200 |
| Activity 5 Total |  |  |  |  |  | 0 | 11,200 | 11,200 |
| Total |  |  |  |  |  | 51,660 | 118,527 | 170,187 |

Travel arrangements not to exceed entitlement as per UN rules.

All expenditures will be reimbursed at actual cost and subject to reporting as per Article 7 of the SSFA.