Design of a Terrestrial, Aquatic and Marine Biodiversity Monitoring Network in the Context of Climate Change in Chile

PROPOSED AMENDMENT TO SCHEDULE

Activities

Activity 1. Design of Biodiversity Network in the Context of Climate Change in Chile

Activity 1.1. Analyzing information availability and gap

| Deliverables | Delivery date |
| --- | --- |
| Report of interviews drafted | Concluded |
| Study reports for three types of ecosystems drafted | Concluded |
| Gap needs report drafted | Concluded |

Activity 1.2. Identifying the architectural and conceptual design

Activity 1.2.1. CATIE will be responsible for organizing a national workshop on the identification of variables that need to be measured to meet the information needs of decision markers.

| Deliverables | Delivery date |
| --- | --- |
| Workshop program finalized | Concluded |
| Workshop report with results of different sub-activities drafted | Concluded |

Activity 1.2.2. Based on the need and gaps analysis and on the workshop outputs, CATIE, in collaboration with ICRAF, will develop data collection protocols and data quality standards.

| Deliverables | Delivery date |
| --- | --- |
| Draft protocol develop | 15st December 2015 |
| Report on Systems requirements drafted | 15st December 2015 |
| Workshop | 20st January 2015 |
| Workshop report with results of validation drafted | 30st January 2015 |

Activity 1.2.3 CATIE develop a proposal for baseline establishment including an analysis of available information for baseline establishment, the definition of short-term actions to gain  access to this information, a proposal for use of existing information and identification of needs for additional information for the baseline, and terms of Reference for a baseline study.

| Deliverables | Delivery date |
| --- | --- |
| Terms of Reference baseline study drafted | 30st January 2015 |

Activity 1.2.4 CATIE will be responsible for coordinating the integration of the technical studies and workshops into one draft report for review and finalization with relevant national actors, in collaboration with ICRAF.

| Deliverables | Delivery date |
| --- | --- |
| Report on conceptual and architectural design monitoring systems drafted | 30st January 2015 |

Activity 3. Proposing standards and protocol for collaboration and information sharing

Activity 1.3.1 CATIE will be responsible for analysis standards and protocols for collaboration and information sharing.

| Deliverables | Delivery date |
| --- | --- |
| Report on analysis of data sharing standards and protocols drafted | 30st January 2015 |

Activity 1.3.2 Based on this analysis, CATIE will be responsible for proposing standards and protocols for collaborations and information sharing, including best practices to ensure reliability and quality of data to be provided.

| Deliverables | Delivery date |
| --- | --- |
| Standard and protocols proposal drafted | 15st January 2015 |

Activity 1.4 Proposing institutional arrangement and logistic and operational requirements

Activity 1.4.1 CATIE will be responsible for identifying potential partners to involve in the monitoring network and their respective roles.

| Deliverables | Delivery date |
| --- | --- |
| List of potential partners for the network drafted | 30st December 2015 |

Activity 1.4.2 CATIE will be responsible for identifying the technological, human and financial requirements for the establishment and operation of the system, based on the second national workshop, the integration report, and the analysis of the needs and existence of resources among potential network partners.

| Deliverables | Delivery date |
| --- | --- |
| Technical proposal for implementation of monitoring system drafted | 28st February 2016 |
| Financial proposal for second phase of investments drafted | 28st February 2016 |

Activity 1.4.3 CATIE will be available for additional on-line support beyond the duration of this contract, to advise the Ministry of Environment and the network partners during the establishment of a preliminary baseline for piloting the network with existing resources.

| Deliverables | Delivery date |
| --- | --- |
| Preliminary baseline analysis drafted | 28st March 2016 |