# Instructions to lead Implementers for drafting the

# Technical Assistance Closure and Data Collection Report

Objective of the technical assistance (TA) Closure Report and Data Collection Report:

- To communicate publicly in one synthesis document a summary of progress made and lessons learned under the technical assistance (TA) towards the anticipated impact (main template).

- Compile TA-specific information required for internal use in donor and UN reporting (annex 1).

Steps for completing the TA Closure report:

- The lead TA implementer drafts the report at the end of the assignment as a final deliverable /product.  The TA Closure report will capture all activities conducted under the TA hence it is expected that duplication of information will occur from earlier documents. Please copy and summarise relevant material from previous TA outputs/deliverables and the Response Plan, as relevant.

- A CTCN Manager will review and revise the report before final approval by the CTCN Director.

Important note on public and internal use of the closure report:

Once approved by the CTCN Director, the TA Closure and Data Collection Report will be a public document available on the CTCN website.  Annex 1 is for internal use only and will not be publicly available.

Closure and Data Collection Report for CTCN Technical Assistance

- Basic information

| Title of response plan | Scaling-up sustainable wood fuel (charcoal and firewood) cooking systems in the Pwani, Lindi and Mtwara regions. |
| --- | --- |
| Technical assistance reference number | DTIE17-EN0048 |
| Country / countries | Tanzania |
| NDE focal point and organisation | Dr. Gerald Kafuku, Tanzania Commission for Science and Technology (COSTECH). |
| Proponent focal point and organisation | Engineer Mathew Matimbwi, Tanzania Renewable Energy Association (TAREA), |
| Sector(s) addressed | Forestry |
| Technologies supported | Instruction: Please indicate the type of technologies supported by this assistance, referring to the taxonomy of climate sectors and technologies available (download in pdf format and choose from column C): https://www.ctc-n.org/resources/ctcn-taxonomy If technologies supported are not found in the taxonomy, please suggest. Renewable energy, bioenergy, charcoal production for cooking and heating, improved cookstoves |
| Implementation period and total duration | 15 months (extension of 3 months) |
| Total budget for implementation | Instruction: In addition to financial value of the technical assistance, please also include if any pro bono or in-kind support has been provided by both the implementer and/or the national counterparts. US$ 220,492 |
| Designer of the response plan | International Centre for Research in Agroforestry (ICRAF) |
| Implementer of response plan | International Centre for Research in Agroforestry (ICRAF) |

2.  Summary of all activities, outputs and products that contribute to the expected impact of the technical assistance.

| Description of delivered outputs and products as well as the activities undertaken to achieve them. In doing so, review the log frame of the original response plan and refer to it as appropriate | Attached Annex 1. |
| --- | --- |
| Partners organisations | Instruction: Implementers and other partner organisations are defined as the people and institutions engaged in the implementation of the TA ICRAF TAREA COSTECH Other involved partners in co-designing and co-delivery of the co-training or trainers and grassroots training on sustainable woodfuel systems: Government bodies: Tanzania Forest Services Regional Secretariats Vocational Education and Training Authority (VETA) Lindi Grassroots community groups: Environmental Conservation and Community Enterprise ECOCE Kaza Moyo Group Upendo Halisi group Madendo Mtima Group Other local community Firewood and charcoal producers, traders and users |
| Beneficiaries | Instruction: Beneficiaries are defined as people and institutions benefitting from the TA -88 people representing government departments, NGO’s, training and research organizations, grassroots community based organizations and community charcoal producers, traders and users were involved in context analysis and planning during the Stakeholder Approach to Risk-informed and Evidence-based Decision-making (SHARED) exercises - 16 male and 5 female representing government bodies, NGO’s, grassroots community based organizations, community charcoal producers, traders and users trained as trainers on sustainable woodfuel systems acquired skills of designing and delivering trainers courses through application of a co-learning approach including additional 2 female and 4 male from the three key partner organizations (ICRAF, TAREA and COSTECH) -Graduates of the trainers course trained 76 males; 42 females on sustainable woodfuel systems at the grassroots level in the three target regions -15 people representing Ministry of Energy, Universities, research organizations community and private sector involved in development of a proposal for scaling up sustainable woodfuel systems in Tanzania |
| Methodologies applied to produce outputs and products | Instruction: Examples of methodologies: E.g. Cost-benefit analysis; surveys and structured interviews with key stakeholders; etc. -Stakeholder Approach to Risk-informed and Evidence-based Decision-making (SHARED) a methodology developed by ICRAF -Co-designing and co-knowledge synthesis for preparation of training materials and co-delivery of trainings -Training of trainer (trainers’ course) who subsequently delivered grassroots trainings -Training on Bioenergy-Biochar climate smart systems for NDE and representatives of Ministry of Agriculture in 14 countries in Africa during the works on Technologies to Enhance and Monitor Soil Carbon for African Countries organized by ICRAF 12-14 December 2018. |
| Deviations | Instruction: Please describe any deviations from the response plan against the actual implemented activities, outputs and products. None |
| Achieved or anticipated gender benefits from the TA | Instruction: Please describe expected gender benefits as described in the response plan and in the relevant deliverable. -Men and women involved in training course and equipped with skills of for co-designing and co-delivering trainers courses -Men, women including the young and old reached with skills and knowledge on sustainable woodfuel systems. Language used in training included local languages as trainers were from the villages -Data disaggregated by gender and age on roles and challenges faced in woodfuel systems - Gender responsiveness in illustrations training materials such as photos -Training materials translated into local language for ease of understanding by majority |
| Achieved or anticipated co-benefits from the TA | Instruction: Please describe expected co-benefits as described in the response plan and in the relevant deliverable. -Training materials produced both in English and local languages can be used by other organizations -Proposal developed from the TA will raise more funding for going to scale with the innovations -Increased income from efficient charcoal production technologies -Reduced health risks from indoor air pollution -Increased tree cover from improved management of tree resources -Reduced air pollution from increased trees that capture carbon dioxide and use of more efficient kilns -Increased government revenue from enhanced purchases of licences and other documents required for legal charcoal production and trade. -Enhanced community development from incomes from licences on sourcing trees from villages forests |
| Anticipated follow up activities and next steps | Instruction: Please describe how the Proponent, partner organisations and beneficiaries will use outputs and products and how these will contribute to the expected impact of the TA. -Training materials produced both in English and local language Kiswahili and the SHARED book with analysed context and prioritised intervention for making woodfuel systems sustainable are online and will be used by other organizations for reaching more people an initiative being pursued by COSTECH the NDE. They already have a lot of reads on research gate. -Proposal developed from the TA will raise more funding for going to scale with the innovations and Finish Embassy and DFID are keen to support. This will be pursued by the NDE (COSTECH) in partnership with TAREA and ICRAF. |

- Lessons learnt

|  | Lessons learnt | Recommendations |
| --- | --- | --- |
| Lessons learnt for this TA. Describe essential factors contributing to successful implementation, as well as specific challenges. Recommendations include considerations on what would need to be in place for increasing success of similar efforts (i.e. regulatory, legal, stakeholders, communication, etc.) | -Involvement of the NDE and Proponents in all the planning and implementation of the activities led to the success of this TA. -Participation of government departments, NGO, private sector and individuals including grassroot communities involved in woodfuel production, trade and use enabling the co-learning process yielding very useful insights from multiple dimensions for making the woodfuel systems sustainable and addressing societal problems associated to the sector. | -The methodologies applied in the TA were successful and should be applied in other works on making woodfuel systems sustainable |
| Lessons learnt related to climate technology transfer Describe opportunities, challenges and barriers for the use and deployment of the technology or technologies supported by the TA. The objective is to identify specific success factors for technology transfer | -A system approach to woodfuel that considers wood production, conversion of wood to charcoal, marketing and trade and use while integrating gender and policy framework has potential for making this sector sustainable. -Stakeholder engagement and co-learning are good ways of analyzing local context, prioritizing interventions, developing capacity building products and delivering trainings as they ensure that the process takes into consideration diverse perspectives -A training process that builds the skills of local resource persons as trainers promotes open interaction between trainers and trainees while contextualizing lessons. Involvement of technical experts in development of the capacity building products helps bridge the gap between science and practice. -Training materials needs to be translated into Kiswahili for ease of use by local trainers. | -Growing trees on farms and management of natural vegetation for woodfuel needs to be adopted so as to reduce negative effects from cutting down trees without replanting system -Adoption of improved kilns will reduce wood wastage hence less trees will be harvested for charcoal and there will be less air pollution form charcoal processing. -There is need for enhanced use of improved stoves to reduce fuel wastage and indoor air pollution -There is need for capacity development, incentives and reduced taxation on improved technologies for sustainable woodfuel systems |
| Lessons learnt related the CTCN process for TA | -The assigned period of 18 months is unsuitable for implementation of activities of TA that involve multi-stakeholder consultations. | -Need to extend the implementation to 24 months |

4. Illustration of the TA and photos

For communication purposes, please provide 2-4 Power Point slides with illustrations or charts showing the TA process, applied methodology, activities, outputs and achieved results. The illustrations must be copied into the TA Closure report but must also be delivered as power point files. Also, please provide at least five high-resolution pictures in jpg format, capturing technical assistance. The pictures should illustrate how the TA has impacted the lives of the beneficiaries in particular and the communities in general.

5. Information for TA Impact Description

The information in the table below will be used to produce the CTCN TA Impact Description. The TA Impact description is a 2-page summary document for communication purposes.

| Challenge: Approx. 500 characters with spaces | Globally 2.7 billion people—38% of the world’s population, relies on the traditional use of solid biomass for cooking, typically using inefficient stoves in poorly ventilated spaces. In sub-Saharan Africa (SSA), more than 90% of the population relies on firewood and charcoal derived from wood as a primary source of domestic energy. Use of woodfuel is not a bad thing, but the negative impacts on the environment and indoor health from unsustainable production and inefficient utilization practices are of concern which has resulted in policies and campaigns to discourage its use. This can be addressed by making woodfuel cooking systems (production, marketing and utilization) sustainable. |
| --- | --- |
| CTCN Assistance: 2 to 4 bullet points. Approximately 450 characters with spaces | -Synthesis of secondary data on the situation of woodfuel systems in the Country and in the three target regions including urban areas as points of demand -Conduct participatory context analysis and planning for sustainable woodfuel systems -Developing capacity and awareness for sustainable woodfuel systems -Develop a proposal on scaling up sustainable wood fuel systems in Tanzania |
| Anticipated impact: 2 to 4 bullet points to summarise anticipated impact. Approximately 250 characters with spaces. As a minimum, please include the impacts described in annex 1B as well as other relevant qualitative and quantitative impacts anticipated after completion of CTCN technical assistance. | -89 people: government departments, NGO’s, training and research organizations, grassroots community based organizations, charcoal producers, traders and users analysed context in 3 regions and planned for sustainable woodfuel systems through SHARED workshops -Literature review described woodfuel situation and identified interventions for scaling up sustainable woodfuel systems -English and Kiswahili grassroots training manuals on sustainable woodfuel systems -20 male and 7 female: government bodies, NGO’s, research and training organizations, grassroots community based organizations, charcoal producers, traders and users applied co-learning approach in co-designing of grassroots training -Graduate of the trainers course trained 76 males; 42 females on sustainable woodfuel systems at the grassroots level in the three target regions -15 people representing Ministry of Energy, Universities, research organizations community and private sector developed a proposal for scaling up sustainable woodfuel systems in Tanzania. Donor consultations with DFID and Finish Embassy showed interest. -In the long run the the knowledge and skills gained will influence adoption of improved technologies in sourcing wood, carbonizing wood into charcoal, and utilization leading to reduced negative effects on environment including climate change and human health. |
| Linkages and contribution to NDC: 2 to 4 bullet points. Approximately 350 characters with spaces | -The capacity developed through the trainings, stakeholder engagement and the proposal development for scaling up the technologies for sustainable woodfuel system will contribute to the adaptation identified under (1)Forest sector on enhancing (a) efficiency in wood fuel utilization, b) forest governance and protection of forest resources and c) sustainable forest management.. (2) Energy sector on (a) promoting use of energy efficient technologies and behaviour and (b) enhancing the use of renewable energy potential across the country (hydro, solar, wind, biomass and geothermal) |
| The narrative story: Approximately 1200 characters with spaces | Tanzania Renewable Energy Association (TAREA), requested assistance from CTCN through Tanzania Commission of Science and Technology (COSTECH) on the appreciation that households, enterprises and institutions in Pwani, Lindi and Mtwara coastal regions in Tanzania use charcoal and firewood for cooking, leading to a rate of biomass harvested from the forest to produce domestic energy higher than the natural regeneration. Charcoal production is considered an important potential source of economic activity for these communities and considering the demand and population growth in urban areas such as the city of Dar es Salaam the rate of deforestation is unlikely to decrease. The assistance generated knowledge for scaling-up climate friendly and environmentally sound wood fuel (charcoal and firewood) and resource recovery for biomass technology and policy frameworks that include sustainable production, efficient marketing and efficient utilization throughout the country. Through a consultative process (SHARED) 88 representatives of various stakeholders generated knowledge about current status and prioritized interventions to make woodfuel sustainable. Twenty male and 7 female from a diverse range of stakeholders applied co-learning approach in co-designing of grassroots trainings. Graduates of the trainers course trained 76 males; 42 females on sustainable woodfuel systems at the grassroots level in the three target regions -15 people from a diverse range of stakeholders developed a proposal for scaling up sustainable woodfuel systems in Tanzania. |
| Contribution to SDGs: Always include contribution to SDG 13, and to the extent possible, please include contribution to 2 other SDGs, describing the contribution with a few sentences for each SDG concerned. A complete list of SDGs and their targets is available here: https://sustainabledevelopment.un.org/partnership/register/ | SDG 5. Achieve gender equality and empower all women and girls. The response plan involved women and men including youth in the activities and their participation was encouraged through gender sensitive approaches and tools. Roles, benefits, needs, perception, challenges and opportunities for different categories of people was characterised to ensure gender responsive decision making and impact. SDG 7. Ensure access to affordable, reliable, sustainable, and modern energy for all. The assistance generated knowledge on current wood production and management, charcoal production, marketing, domestic and commercial use, local regulations and interventions. The prioritized technologies took into account those aspects and once implemented will contribute to improved livelihoods of the stakeholders (households, charcoal producers, cookstove producers) by strengthening the whole value chain SDG 13: Take urgent action to combat climate change and its impacts Sustainable woodfuel systems will considerably reduce deforestation and emissions which are critical steps in mitigating against climate change associated with biomass energy. SDG 16. Promote peaceful and inclusive societies for sustainable development, provide access to justice for all and build effective, accountable and inclusive institutions at all levels. The participatory context analysis and planning process (SHARED) ensured inclusivity in understating the context, setting development outcomes and designing the implementation strategy of intervention and training for sustainable woodfuel systems. |

Note: Please see examples of TA Impact Description in adaptation and mitigation at the following link:

https://www.ctc-n.org/sites/www.ctc-n.org/files/learning-reports/18106-ctcnimpactdescriptionv02.pdf

https://www.ctc-n.org/sites/www.ctc-n.org/files/learning-reports/ta_impact_description_2014000002_gcai.doc

Annex 1 - Standardised CTCN performance indicators for donor and UN reporting

Please add quantitative values and qualitative descriptions for indicators relevant to the particular TA in the tables below.  Non-relevant indicators should be left blank.

- Activities and outputs supported by CTCN technical assistance

Please only fill in the table for activities and outputs conducted or produced directly by the CTCN assistance.

| CTCN standardised performance indicators | Quantitative value | Qualitative description List the various elements corresponding to the quantitative value |
| --- | --- | --- |
| Overview |  |  |
| - Number of work days of the international expert team spent on the implementation of the technical assistance | 350 | -Literature review -SHARED workshops -Report on SHARED -Preparation of training materials -Delivering training -Proposal development |
| - Number of work days of the locally-contracted expert team spent on the implementation of the technical assistance | 250 | -Administration -Financial support -Driving -Workshop and training logistics -Community mobilization -Training -SHARED workshop notes |
| - Number of external communication and outreach activities conducted to showcase the assistance (news release, newsletters, articles on website, events presenting the results of the technical assistance, social media postings, and presentations at events outside the technical assistance etc.) | 1 7 1 2 | Please list the type of external communications here -Articles on website (in preparation) -International conferences -Round table discussions with stakeholders -Donor meetings |
| Events (other than trainings) held as part of the assistance |  |  |
| - Total number of events other than trainings (Aggregation of numbers in categories below) | Aggregation of numbers in categories below | 4 |
| - Number of international and multi-country (at regional or sub-regional level) technology and knowledge sharing events |  | List title of events |
| - Number of participants in the events above |  |  |
| - Number of national technology and knowledge sharing events (national events held including national consultations) | 4 | List title of events -Stakeholder Approach to Risk-informed and Evidence-based Decision-making (SHARED) workshops in Mtwara, Lindi and Pwani held in November 2017 -Round table meeting for proposal development in November in Bagamoyo, Tanzania |
| - Number of participants in the events above | 103 |  |
| - Number of public-private events related to technologies |  | List title of events |
| - Number of participants in the events above |  |  |
| Training and capacity building activities conducted during the assistance |  |  |
| - Number of training sessions and capacity strengthening activities | 4 | List the title of the training sessions and capacity strengthening activities - 1 training of trainers -3 grassroots training in Mtwara, Lindi and Pwani |
| - Number of people who received the training |  |  |
| - Number of men | 94 |  |
| - Number of women | 42 |  |
| - Total number of organisations trained | List total number here |  |
| - Number of research organisations, laboratories and universities | 3 | List the name of organisations trained here -Vocational Education and Training Authority (VETA) Lindi -COSTECH -ICRAF |
| - Number of private companies |  | List the name of organisations trained here |
| - Number of cities and local government |  | List the name of organisations trained here |
| - Number of communities | Communities in 3 regions, Mtwara, Lindi and Pwani 1 | List the name of organisations trained here -Charcoal producers -Stove producers -Charcoal and firewood users -Tree nursery producers -Hotel as user of woodfuel |
| - Number of ministries | 1 1 1 | List the name of organisations trained here -Tanzania Forest Services -Regional secretariat -Regional agriculture advisor - |
| - Number of specialised governmental institutions | 1 | List the name of organisations trained here -Primary school as user of woodfuel - |
| - Number of non-profit organisations | 1 | List the name of organisations trained here -Environmental Conservation and Community Enterprise ECOCE |
| - Number of participants that were significantly or moderately satisfied after the training (from CTCN training feedback form). |  |  |
| - Number of participants that significantly or moderately increased their capacities thanks to the training (from CTCN training feedback form). |  |  |
| - Number of men |  |  |
| - Number of women |  |  |
| - Level of satisfaction of participants after the training (from training feedback form). Categories include: From very satisfied, satisfied, partly not satisfied, not satisfied at all | 80% | All the participants of the trainer course (ToT) were happy with the co-learning approach which allowed them to share their expertise and experience and learn from others. -All the participants were happy with the system approach that seek to improve technologies in the whole value chain of woodfuel production to use. -Use of practical demonstrations and field visits during the training was highly appreciated |
| - Percentage of participants that increased their capacities thanks to the training (from training feedback form). Categories include: Significantly, very, moderately, to none. |  | Impact story written by one farmer on his improved charcoal yield and income after attending the training. He improved his selection of wood, kiln efficiency - Selous Game Reserve in southern Tanzania has started charcoal production using improved kilns in areas where they are clearing land and are support by one of the participants in the proposal development meeting. |
| Percentage of men |  |  |
| Percentage of women |  |  |
| Tools, technical documents and information material supported by the assistance |  |  |
| - Total number of tools, technical documents s and information material supported by the assistance (excluding mission, progress and internal reports) |  |  |
| - Number of tools strengthened, revised or developed (including tools, methodology, software, calculation systems, etc.) | 1 1 | List the name of the documents -Grassroots training manual on sustainable woodfuel systems in English ISBN 978-9966-108-12-8 -Grassroots training manual on sustainable woodfuel systems in Kiswahili the national language. ISBN 978-9966-108-13-5 |
| - Number of technical documents strengthened, revised or created | 1 1 | List the name of the documents Sustainable woodfuel systems in coastal regions in Tanzania: Stakeholder Approach to Risk-informed and Evidence-based Decision-making (SHARED) published as a book. ISBN 978-9966-108-23-4 A literature review: Woodfuel systems in Pwani, Pwani, Mtwara and Lindi Regions, Tanzania: Strategies for making them sustainable and inclusive. A review of recent literature |
| - Number of other information materials strengthened, revised or created (For example training and workshop reports, Power Points, exercise docs etc.) | 2 8 | List the name of the documents Training reports (1 on trainers’ course, 1 on grassroots trainings) TA results integrated in other PowerPoint presentations |
| Policies, laws and regulations supported by the assistance |  |  |
| - Total number of policies, strategies, plans, laws, agreements or regulations supported by the assistance |  | List the policies, strategies, plans, laws, agreements or regulations |
| - Number of policies, strategies, and plans drafted addressing climate change adaptation |  | List the policies, strategies, plans, laws, agreements or regulations |
| - Number of policies, strategies, and plans drafted addressing climate change mitigation |  | List the policies, strategies, plans, laws, agreements or regulations |
| - Number of documents developed to inform other policies, strategies, and plans on climate change adaptation (sectoral strategies, national development plans, etc.) |  | List the documents |
| - Number of documents developed to inform other policies, strategies, and plans on climate change mitigation (sectoral strategies, national development plans, etc.) |  | List the documents |
| - Number of laws, agreements, or regulations drafted addressing climate change adaptation |  | List the laws, agreements and regulations |
| - Number of laws, agreements, or regulations drafted addressing climate change mitigation |  | List the laws, agreements and regulations |
| - Number of documents developed to inform laws, agreements, or regulations on climate change adaptation |  | List the documents |
| - Number of documents developed to inform laws, agreements, or regulations on climate change mitigation |  | List the documents |
| Institutional strengthening supported by the assistance |  |  |
| - Total number of institutional arrangements supported to support climate change planning |  | List the institutional arrangements |
| - Number of organisations with increased awareness and knowledge among countries to better own and drive national adaptation planning processes |  | List the organizations |
| - Number of organisations with increased awareness and knowledge among countries to better own and drive national mitigation planning processes | 15 | List the organizations -Department of Economics-UDOM (University of Dodoma) - New Forest Company-Iringa -Ministry of Energy-Dodoma -Arti Energy NGO - Wood utilization-Sokoine university (SUA) - Science and Technology-University of Dar es Salaam (UDSM) -Local Government Lindi Zone - Tanzania Forest Services (TFS) -Regional secretariats in Mtwra, Lindi and Pwani -Regional agriculture advisor, Lindi -Environmental Conservation and Community Enterprise ECOCE, NGO -Selous Game Reserve in southern Tanzania -Vocational Education and Training Authority (VETA) Lindi |
| Partnerships and cooperation |  |  |
| Number of private companies directly engaged in the assistance (that partnered with the proponent, the beneficiaries or the CTCN to implement the assistance) (Excluding the role of the CTCN and TA implementers) |  | Please list here the names of the organisations cooperating |
| - Number of South-South collaborations enabled during or through the assistance, when stakeholders from other countries were involved in the assistance (Excluding the role of the CTCN and TA implementers) |  | Please list here the names of the organisations cooperating |
| - Number of North-South collaborations enabled during or through the assistance, when stakeholders from other countries were involved in the assistance (Excluding the role of the CTCN and TA implementers) |  | Please list here the names of the organisations cooperating |
| - Number of Triangular collaborations enabled during or through the assistance, when stakeholders from other countries were involved in the assistance (Excluding the role of the CTCN and TA implementers) |  | Please list here the names of the organisations cooperating |
| UNFCCC planning/support processes |  |  |
| - Number of National Adaptation Plans (NAPs) developed as part of the technical assistance |  | List as appropriate |
| - Number of Nationally Appropriate Mitigation Actions (NAMA) developed as part of the technical assistance |  | List as appropriate |
| - Number of Technology Needs Assessment s(TNAs) developed as part of the technical assistance |  | List as appropriate |

B. Impacts anticipated after completion of CTCN technical assistance: core indicators

Every technical assistance should contribute to at least one indicator below.

| CTCN core indicators | Quantitative value | Unit | Methodology Explain the method or process of verifying the indicator and how data was gathered | Assumptions Indicate assumptions made during quantification | Expected timeline Indicate when the indicator and value are expected to be achieved |
| --- | --- | --- | --- | --- | --- |
| - Total anticipated amount of funding/investment mobilised (in USD) as a result of the TA |  |  |  |  |  |
| - Anticipated amount of public funding mobilised (in USD) from national sources as a result of the TA |  |  |  |  |  |
| - Anticipated amount of public funding mobilized (in USD) from international and regional sources as a result of the TA | A proposal developed worth 5 Million | US | Proposal | That the donors will be willing to support the proposed work | By end of 2020 |
| - Anticipated amount of private investment mobilised (in USD) from national sources as a result of the TA |  |  |  |  |  |
| - Anticipated amount of private investment mobilised (in USD) from international and regional sources as a result of the TA |  |  |  |  |  |
| - Anticipated number of beneficiaries as a result of a mitigation TA |  |  | (please describe the calculation process, original unit etc) |  |  |
| - Anticipated number of people with increased resilience as co-benefits as a result of the TA |  |  | (please describe the calculation process, original unit etc) |  |  |
| - Anticipated average the total GHG reductions in metric tons of CO2-e, as a result of the TA | 900-1350 | metric tons of CO2-e, per year | (please describe the calculation process, original unit etc) If the proposal is funded 300 tonnes of charcoal will be produced sustainably each year. | (please also indicate the baseline year and when the indicated value is expected to be achieved) From 2020 If 50% efficiency is improved the 6-9kg of CO2-e, per kg of charcoal from inefficient technologies along the charcoal life cycle (FAO, 2017) can be halved. The current 1800-2700 t of CO2-e from 300t of charcoal can be halved per year. | Year 2024 |
| - Anticipated average annual GHG reductions in metric tons of CO2-e, as a result of the TA |  |  |  | (please also indicate the baseline year and when the indicated value is expected to be achieved) |  |
| - Anticipated and projected greenhouse gas emissions reduced or avoided through 2030, in metric tons of CO2-e, from adopted laws, policies, regulations, or technologies related to clean energy/sustainable landscapes as a result of the TA |  |  |  | (please also indicate the baseline year and when the indicated value is expected to be achieved) |  |

C. Outputs and impacts anticipated after completion of CTCN technical assistance: standardised performance indicators

| CTCN standardised performance indicators | Quantitative value Insert the request value and unit | Content List the elements included in the number provided | Expected timeline Indicate when the indicator and value are expected to be achieved | Responsible institution Indicate the institution(s) that will play leading role(s) in enabling the indicators and anticipated values to be achieved |
| --- | --- | --- | --- | --- |
| - Anticipated number of policies, strategies, plans, addressing climate change mitigation officially proposed, adopted, or implemented as a result of the TA |  |  |  |  |
| - Anticipated number of policies, strategies, plans, addressing climate change adaptation officially proposed, adopted, or implemented as a result of the TA. |  |  |  |  |
| - Anticipated number of policies, strategies, plans, addressing climate change on both adaptation and mitigation officially proposed, adopted, or implemented as a result of the TA |  |  |  |  |
| - Anticipated number of laws or regulations addressing climate change mitigation officially proposed, adopted, or implemented as a result of the TA. |  |  |  |  |
| - Anticipated number of laws or regulations addressing climate change adaptation officially proposed, adopted, or implemented as a result of the TA. |  |  |  |  |
| - Anticipated number of laws or regulations addressing climate change both adaptation and mitigation officially proposed, adopted, or implemented as a result of the TA |  |  |  |  |
| - Anticipated number of public-private partnerships and collaboration created (Excluding the role of the CTCN and TA implementers) |  |  |  |  |
| - Anticipated twinning arrangements created as a result of the TA |  |  |  |  |
| - Anticipated number of technology projects to support action on low emission and climate-resilient development |  |  |  |  |
| - Anticipated number of strengthened National Systems of Innovation and technology innovation centres in recipient country | 12 | -Department of Economics-UDOM (University of Dodoma) -Ministry of Energy-Dodoma - Wood utilization-Sokoine university (SUA) - Science and Technology-University of Dar es Salaam (UDSM) -Local Government Lindi Zone - Tanzania Forest Services (TFS) -Regional secretariats in 3 regions Mtwara, Lindi and Pwani -Regional agriculture advisor, Lindi -Selous Game Reserve in southern Tanzania -Vocational Education and Training Authority (VETA) Lindi | -Immediate use of the lessons learned | -Each of the listed institution |
| - Anticipated Clean Energy Generation Capacity in kWh supported by the TA |  |  |  |  |
| - Anticipated technology types effectively deployed in the country | -7 | -System approach to sustainable woodfuel -Sustainable wood production for woodfuel -Efficient kilns for charcoal production -Efficient biomass stoves -Effective marketing, trade -Policy framework on woodfuel -Bioenergy-bioenergy climate smart systems | -Skills transferred during the TA | --Charcoal producers -Stove producers -Charcoal and firewood users -Tree nursery producers -Hotel as user of woodfuel --Tanzania Forest Services (TFS) -Regional secretariats in Mtwra, Lindi and Pwani -Regional agriculture advisor, Lindi -Environmental Conservation and Community Enterprise ECOCE, NGO -Selous Game Reserve in southern Tanzania -Ministry of Agriculture in Botswana, Ethiopia, Kenya, Lesotho, Malawi, Mozambique, Namibia, Uganda, Rwanda, South Sudan, Swaziland, Tanzania, Zambia, and Zimbabwe who attended the training on Technologies to Enhance and Monitor Soil Carbon for African Countries organised by ICRAF in December 2018 -NDE in Ethiopia, Mozambique, Tanzania, Kenya, Namimbia, Lesotho, Botswana, Malawi and South Sudan |
| - Anticipated UNFCCC processes implemented as a result of the TA (NAMA, NAPA, NDC, etc.) |  |  |  |  |
| - Anticipated Technology Needs Assessments (TNA) and technology Action Plans (TAP) as a result of the TA |  |  |  |  |
| - Anticipated cooperative research, development and demonstration programmes within and between developed and developing country Parties facilitated as a result of the TA |  |  |  |  |
| - Anticipated improved climate change observation systems and related information management in developing country Parties. |  |  |  |  |

Appendix 1. Activities and deliverables

| Activity | Deliverables | Delivered |
| --- | --- | --- |
| - Synthesis of secondary data on the situation of woodfuel cooking systems in the three target regions including urban areas as points of demand | - Detailed workplan with specific dates and monitoring milestones (consistent with closure report indicated in activity 5) and 1 page description of the intended outcomes and impacts (template to be provided by CTCN) - List of key actors and decision-makers in woodfuel systems. - A synthesis of existing literature on woodfuel cooking systems and lessons for replication | # This output were delivered as a report titled: Woodfuel systems in Pwani, Mtwara & Lindi Regions, Tanzania: Strategies for making them sustainable and inclusive |
| - Conduct participatory context analysis and planning for sustainable woodfuel cooking systems | - Action plan developed based on the results of the stakeholder-driven participatory context analysis and planning approach for the 3 regions - Synthesis of local context including rural-urban linkages and implications in woodfuel cooking systems - Area natural resource maps by communities indicating past, present and future with or without intervention outcomes in 2030 including rural-urban flows - A report on priority feasible interventions and implementation strategy for sustainable wood fuel cooking systems in both rural and urban areas - A report on priority communication processes and implementation strategy for sustainable wood fuel cooking systems - Design of the sustainable wood fuel cooking system training | A synthesis report on local context comprising deliverables a-f was published as a book in December 2018 A blog was published on the stakeholder consultation process on mapping the local context of woodfuel systems ICRAF, TAREA and COSTECH representatives participated in all the workshops. This book is available on the project site of CTCN. |
| - Developing capacity and awareness for sustainable wood fuel cooking systems | - Training course manual on sustainable wood fuel systems - Training of trainers on sustainable wood fuel systems for stakeholders in urban and rural areas of the three regions: Target 25 people - One training course on sustainable woodfuel cooking system held by those trained in the trainers course per site comprising of stakeholder in the woodfuel system: Target 75 people | Trainers course for training of trainers (ToT) was carried out in March 2018 and 16 men and 5 women were trained. Grassroots training were carried out by graduates of the trainer’s course in October 2018 and 2 more trainers trained and 76 men and 42 women trained. Brief of the trainings were prepared and submitted to CTCN ICRAF, TAREA and COSTECH representatives participated in all the trainings. A grassroots training manual prepared and published both in English and Kiswahili versions This training manuals and training reports are available on the project site of CTCN. |
| - Develop a proposal on scaling up sustainable wood fuel cooking systems in Tanzania | - Opportunities to secure financing for scaling up wood fuel cooking systems including rural-urban linkages for sustainable production and efficient utilizations identified and articulated - Strategy for promoting the proposal + list of potential donors - Preparation of a proposal for sustainable wood fuel system proposal integrating rural and urban areas - Updated proposal after meetings with donors | Round table stakeholder consultations and writing meeting was held in Bagamoyo, Tanzania in and 15 people participated. Donor consultations held with DFID and Finish Embassy in Tanzania. Finish Embassy indicated that there were interested and waiting for recommendations of the charcoal task force on the future of woodfuel in Tanzania Proposal delivered to CTCN and TAREA and COSTECH |
| - Evaluation and learning | - Drafting and finalization of the closure report and data summary for the assistance (template has been provided by CTCN). | Report being finalized. |

Annex 2 (for internal use – to be filled in by the CTCN)

CTCN evaluation

This section will be completed by the relevant CTCN Technology Manager.

- Evaluation of the timeliness of the TA implementation as measured against the timeline included in the response plan;

- Evaluation of TA quality as defined in the response plan;

- Overall performance of the Implementers;

- Overall engagement of the NDE and Proponent;

- Lessons learned on the CTCN process and steps taken by the CTCN to improve.