SALINE WATER PURIFICATION TECHNOLOGY AT HOUSEHOLD LEVEL AND LOW-COST DURABLE HOUSING TECHNOLOGY 
FOR COASTAL AREAS OF BANGLADESH

TA Monitoring and Evaluation plan

Submitted to

Climate Technology Centre and Network (CTCN)

By

Green Technology Center,

Korea Institute of Civil Engineering and Building Technology

Glory & Tech.

| (A) Outputs and Activities as described in the Response Plan | (B) Response Plan target for the Output or Activity | (C) Indicator | (D) Method and frequency for data collection | (E) Value for Output/Activity produced using the indicator in column C | (F) Difference between targeted and delivered Output and activity values |
| --- | --- | --- | --- | --- | --- |
| Output 1: Engagement of national level and district level stakeholders | One (1) report on the stakeholder consultations and engagement One (1) project inception report | Number of consultation reports presented Number of inception reports presented | Record of reports produced and communicated to stakeholders | One (1) stakeholder consultation report One (1) project inception report | 0 0 |
| Output 2: Identification and prioritization on the most promising and low-cost domestic climate-resilient housing technology solutions for the local conditions | At least six (6) international and national literature sources are reviewed. One (1) fact-finding report on technology solutions implemented nationally and in other countries One (1) report on consultations with stakeholders At least Ten (10) stakeholders consulted (10 % women) One (1) report including recommendations for conceptual and operational design information | Number of literature sources reviewed. Number of fact-finding reports presented Number of consultation reports presented Number of stakeholders consulted - Number of men - Number of women Number of conceptual and operational design information reports presented | Record of reports produced and communicated to stakeholders Reports on consultations Data collection, surveys | Six (6) international and national literature sources reviewed One (1) fact-finding report One (1) stakeholder consultation report Ten (10) stakeholder consulted (10% Women) One (1) technology solution report | 0 0 0 0 0 |
| Output 3. Identification and prioritization of the most promising and low-cost technologies for purification of saline water at household level | At least six (6) international and national literature sources are reviewed. One (1) fact-finding report on technology solutions implemented nationally and in other countries One (1) report on consultations with stakeholders At least Ten(10) stakeholders consulted (10 % women) One (1) report including recommendation for conceptual and operational design information | Number of literature sources reviewed. Number of fact-finding reports presented Number of consultation reports presented Number of stakeholders consulted - Number of men - Number of women Number of conceptual and operational design information reports presented | Record of reports produced and communicated to stakeholders Reports on consultations Data collection, surveys | Nine (9) international and national literature sources reviewed One (1) fact-finding report One (1) stakeholder consultation report Twenty Five (25) stakeholder consulted (16% Woman) One (1) technology solution report | 3 sources more reviewed 0 0 15 people more consulted 0 |
| Output 4: Capacity building of communities on proposed technology solutions and identification of possible sites for future pilot project | One (1) set of training materials produced and used during the training One (1) training report At least 40 people trained (30% women) One (1) list of at least 2 potential sites for piloting | Number of training manuals presented Number of training reports presented Number of people received the training - Number of men - Number of women Number of lists presented | Record of training manuals produced Attendance registers from training workshops Workshop reports Photos Site visits | One (1) set of training materials One (1) training report 56 people trained (10% women) One (1) list of potential sites for piloting | 0 0 16 people more trained 0 |
| Output 5: Support to identifying financing opportunities to upscale the deployment of technologies identified | At least three (3) stakeholder organizations consulted One (1) general project concept document | Number of stakeholders consulted Number of concept document presented to all stakeholders | Reports on meetings and consultations Records of concept document produced and communicated to the stakeholders | Three (3) stakeholder organization consulted (DOE, PKSF, NGF) One (1) GCF concept note | 0 0 |