## Template for TA Monitoring and Evaluation plan

Objective for the TA Monitoring and Evaluation plan:

- The TA Monitoring and Evaluation plan must be designed based on the TA Response Plan and must enable the Implementer to complete the TA Closure and Data Collection Report at the end of the assignment.

Process for designing and using the TA Monitoring and Evaluation plan:

- The Implementer must identify all relevant indicators as specified in the TA Closure and Data Collection Report. The TA Closure and Data Collection Report contains 31 generic TA indicators and the Implementer must build the TA Monitoring and Evaluation plan around a select number of relevant indicators.

- The Implementer may want to identify other specific, measurable, achievable, relevant, and time-bound indicators suitable to monitor Outputs and Activities and add these to the Monitoring and Evaluation plan.

- During implementation of the TA, the Implementer must collect all relevant data as described in the Monitoring and Evaluation plan. Aggregated data for the entire TA will be presented in the TA Monitoring and Data Collection Report for relevant indicators at the end of the assignment.

| (A) Outputs and Activities as described in the Response Plan | (B) Response Plan target for the Output or Activity | (C) Indicator | (D) Method and frequency for data collection | (E) Value for Output/Activity produced using the indicator in column B | (F) Difference between targeted and delivered Output and activity values |
| --- | --- | --- | --- | --- | --- |
| Output 1: Add title from the Response Plan | Add the expected quantitative target/value of the Output or Activity (e.g. number of studies, policy recommendations, etc.). | Select a relevant indicator from the TA Monitoring and Data Collection Report or other relevant indicator | Describe the expected method and frequency for data collection (e.g. survey, head count at a training workshop, factory scada extraction, etc.) | Add the monitored quantitative value | Column E minus column B |
| Output 1: Development of the work plan and related communication documents |  |  |  |  |  |
| Activity 1.1: First project mission. In-country planning mission (Paraguay) | In-country planning mission. Document: Report of the mission | Report of the mission | Meetings with counterparts |  |  |
| Activity 1.2: Development of the work plan | Document: work plan | Delivered work plan | Meetings, desk research |  |  |
| Output 2: Knowledge development analysis of Integrated Water Resource Management (IWRM) at river basin levels |  | CTCN indicators: 5. Tools, technical reports and information material |  |  |  |
| Activity 2.1: Knowledge development of Integrated Water Resource Management (IWRM) at river basin levels | Documents: 2.1: Knowledge development of environmental flows 2.2: Knowledge development of integrated water resource management (IWRM) in Latin America and the Caribbean | Number of new tools, technical reports and information material developed by the TA (indicator 5 of the TA) Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by international experts and consultants Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by national experts and consultants Number of for external communication and outreach activities conducted to showcase the assistance (news release, newsletters, articles on website, etc.) closure report) | Internal system of registering working hours, Counting and listing of: Scientific references General bibliography. Legal framework at National level. IWRM practices worldwide. IWRM in South America. | 1 |  |
| Output 3: Application of a tool for defining EF at river basin levels |  | CTCN indicators: 5. Tools, technical reports and information material 6. Institutions 10. Policies |  |  |  |
| Activity 3.1 Analysis of data availability | Document: 3.1. Analysis of data availability | Number of new tools, technical reports and information material developed by the TA (indicator 5 of the TA closure report) | Counting and listing of evaluated data incorporated in geodatabase. | 1 |  |
| Activity 3.2: Determination of a river basin-scaled tool to define EF in Paraguay | In-country mission Document: 3.2. Determination of a river basin-scaled tool to define EF in Paraguay | Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by international experts and consultants (indicator 1 of TA closure report) Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by national experts and consultants (indicator 1 of TA closure report) Number of for external communication and outreach activities conducted to showcase the assistance (news release, newsletters, articles on website, etc.) (indicator 3 of TA closure report) Number of new tools, technical reports and information material developed by the TA (indicator 5 of the TA closure report) | Internal system of registering working hours Count of post published in web pages. Record of communications in IHCantabria, CTCN and SEAM Web sites Count of documents with technical reports |  |  |
| Activity 3.3: Application of the tool to define EF in the Tebicuary River Basin | Documents: 3.3. Field campaigns of level and flow measurements in the Tebicuary River Basin 3.4. Application of the tool to define EF in the Tebicuary River Basin | Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by international experts and consultants (indicator 1 of TA closure report) Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by national experts and consultants (indicator 1 of TA closure report) Number of for external communication and outreach activities conducted to showcase the assistance (news release, newsletters, articles on website, etc.) (indicator 3 of TA closure report) Number of new tools, technical reports and information material developed by the TA (indicator 5 of the TA closure report) | Internal system of registering working hours, Surveys: Record of working days. Record of number of representative sections, locations and stations. Count of documents with technical reports |  |  |
| Output 4: Development of a framework for an IWRM plan |  | CTCN indicators: 3. Training 5. Tools, technical reports and information material 6. Institutions 10. Policies |  |  |  |
| Activity 4.1: Proposal of a general framework for the IWRM and Adaptation to Climate Change in Paraguay, and its application for the Tebicuary river basin | In-country mission Documents: Proposal of a general framework for the IWRM and Adaptation to Climate Change in Paraguay Guidelines for the development of an IWRM Plan for the Tebicuary river basin (Paraguay) | Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by international experts and consultants (indicator 1 of TA closure report) Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by national experts and consultants (indicator 1 of TA closure report) Number of for external communication and outreach activities conducted to showcase the assistance (news release, newsletters, articles on website, etc.) (indicator 3 of TA closure report) Number of new tools, technical reports and information material developed by the TA (indicator 5 of the TA closure report) | Internal system of registering working hours, Record of adaptation measures for IWRM and its prioritization Evaluation of IWRM plans. Guidelines for IWRM plan in the Tebicuary river basin |  |  |
| Activity 4.2: Training activity of local technicians in the use of the hydraulic model HEC-RAS and its application to flood management | Workshop: Training Activity Document: Report on the development of the training workshop, including documentation and materials. | Indicator 3: Number of training sessions and capacity strengthening activities Number of people who received the training Number of men Number of women Total number of organisations trained Number of research organisations, laboratories and universities Number of private companies Number of cities and local government Number of communities Number of ministries Number of specialised governmental institutions Number of non-profit organisations Level of satisfaction of participants after the training (from training feedback form). Categories include: From very satisfied, satisfied, partly not satisfied, not satisfied at all Percentage of participants that increased their capacities thanks to the training (from training feedback form). Categories include: Significantly, very, moderately, to none. Percentage of men Percentage of women Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by international experts and consultants (indicator 1 of TA closure report) Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by national experts and consultants (indicator 1 of TA closure report) Number of for external communication and outreach activities conducted to showcase the assistance (news release, newsletters, articles on website, etc.) (indicator 1 of TA closure report) Number of new tools, technical reports and information material developed by the TA (indicator 5 of the TA closure report) | Workshop reports, participant feedback |  |  |
| Output 5: Monitoring and evaluation |  |  |  |  |  |
| Activity 5.1: Development of the monitoring and evaluation of results plan |  |  |  |  |  |
|  | Documents: TA Impact description TA closure and data collection report TA Monitoring and evaluation plan | In addition to the indicators presented before: Indicator 17: Anticipated laws, policies, regulations, strategies and plans where climate change adaptation will be mainstreamed as a result of the TA 26. Anticipated number of people improving their livelihood as co-benefits as a result of the TA 27. Anticipated technology types effectively deployed in the country 31. Anticipated improved climate change observation systems and related information management in developing country Parties. | Review of delivered documents, meetings/conversations with national counterparts, cadastral surveys… |  |  |

Please see: https://www.ctc-n.org/sites/www.ctc-n.org/files/ta_closure_report_template._final._march_2017.doc