| Activities | Deliverables | Key Action Steps | Deliverable submission by week (W)/Month | Person Days | Person Responsible | Comments |
| --- | --- | --- | --- | --- | --- | --- |
| Work area 1: Work area 1: Planning and communication |  |  |  |  |  |  |  |
| A.1.1: Development of implementation planning and communication documents | D.1.1 A detailed work plan D.1.2 A monitoring and evaluation plan D.1.3 Draft one page description of intended outcomes and impacts D.1.4 Closure and Data Collection Report | 1.1.1 Prepare detailed work plan 1.1.2 Prepare monitoring and evaluation plan 1.1.3 Prepare of other relevant documents | W2/Sept | 14.5 days | Lead: GFV Support: LI, ND, SA, RB, MB, NZ | AAE suggests to discuss the following topics at the kick-off meeting in addition to the topics establish in the Methodology: (1) Setting of revision timeline - AAE proposes that revisions from stakeholders on draft documents need to take max. 10 working days (2 Weeks - 2W). This would allow for the timely submission of final deliverables. The proposed timeline envision 5 working days (1 Week - 1W) for AAE team to incorporate comments in the revised documents. (2) It is recommended that Stakeholders prepare a list with prioritized NPAs as a starting point for the selection process of the 4 pilot sites. (3) It is recommended to discuss the proposed budget for the implementation of the trainings, given the change of dates and the possible implication this might have on the stated budget. |
| A.1.2: Planning and preparation of stakeholder engagement activities | D.1.5 Stakeholder engagement and logistics plan | 1.2.1 Identify of key stakeholders 1.2.2 Define ways to promote gender equality in stakeholder engagement activities 1.2.3 Decide what kind of communication is required at what stage of the work 1.2.4 Confirm the timing for review of interim outputs by different stakeholders | W4/Sept | 31.5 days |  |  |
| A.1.3: Kick-off meeting | D.1.6 Brief summary report | 1.3.1 Conduct a kick off meeting | W4/Sept | 18 days |  |  |
| Activities | Deliverables | Key Action Steps | Deliverable submission by week (W)/Month | Person Days | Person Responsible | Comments |
| Work area 2: Development of a manual to incorporate the EbA approach into the process of planning and management of NPAs in Peru |  |  |  |  |  |  |  |
| A.2.1: Review of literature and experiences in planning and development of the EbA approach |  | 2.1.1 Confirm with the stakeholders that all needed literature is in the list and all key questions are identified. | W4/Sept | 21 days | Lead: ND Support: LI, SA, RB, MB | AAE proposes to prepare a document as internal deliverable as an outcome of this activity. This internal deliverable can be shared with stakeholders. Depending on the need of stakeholders, this document can be translated in English and Spanish. |
|  |  | 2.1.2 Revise listed literature and categorization according to guiding questions |  |  |  |  |
|  | Internal deliverable: Summary document from literature review with list of literature and key messages | 2.1.3 Submit draft document with responses/key messages to guiding questions | W1/Oct |  |  |  |
| A.2.2: Development of draft version of the manual | D.2.1 Draft EbA Manual for NPAs | 2.2.1 Validate the detailed outline of the "Manual EbA for NPAs" with stakeholders | W1/Oct | 19 days | Lead: SA Support: LI, ND, RB, MB |  |
|  |  | 2.2.2 Submit 1st draft version of "Manual EbA for NPAs" for revision | W3/Nov |  |  |  |
|  |  | 2.2.3 Receive comments from SERNANP/MINAM | W5/Nov |  |  | AAE considers the timeline of 10 working days for revision by stakeholders |
|  |  | 2.2.4 Integrate comments and submit 2nd draft version "Manual EbA for NPAs" | W1/Dec |  |  |  |
| Activities | Deliverables | Key Action Steps | Deliverable submission by week (W)/Month | Person Days | Person Responsible | Comments |
| A.2.3: Application of the draft version of the manual |  | 2.3.1 Select four pilot sites for the implementation of training workshops | W2/Oct | 37 days | Lead: LI Support: ND, SA, RB, MB, CL, NZ | AAE recommends that one of the 4 pilot sites is Cerro Amatope National Park. This would facilitate the data collection phase for the preparation of the Action Plan and Training in A.3.1 and A3.2. |
|  |  | 2.3.2 Revise Master Plans for the selected pilot sites | W4/Oct |  |  |  |
|  |  | 2.3.3 Submit draft version of training materials for revision | W5/Nov |  |  |  |
|  |  | 2.3.4 Submit draft version of training methodology and agenda and submission for revision | W1/Dec |  |  |  |
|  |  | 2.3.5 Receive comments from SERNANP/MINAM | W3/Dec |  |  |  |
|  |  | 2.3.6 Submit final version of training materials and agenda | W3/Jan |  |  |  |
|  |  | 2.3.7 Implement Trainings 1/2/3/4 (2 days/workshop) | W4/Jan - W2/Mar |  |  |  |
|  | D.2.2: Report on the pilot implementation of the draft "Manual EbA for NPAs" | 2.3.8 Submit report from Trainings 1/2/3/4 | W2/Mar |  |  |  |
| A.2.4: Revision of the draft EbA manual | D.2.3: Final Draft "Manual EbA for NPAs" | 2.4.1 Submit 3rd draft version of "Manual EbA for NPAs" for revision | W3/Mar | 8.5 days | Lead: LI Support: SA, RB, MB, NZ |  |
| Activities | Deliverables | Key Action Steps | Deliverable submission by week (W)/Month | Person Days | Person Responsible | Comments |
| A.2.5: Preparation of and training on the use of the EbA manual | D.2.4: Materials created for Workshop 5 - Training of Managersof NPAs (workshop 5) | 2.5.1 Submit revised version of training materials, methodology and agenda | W1/Apr | 46 days | Lead: SA +RB Support: LI, GFV, MB, ND, NZ |  |
|  |  | 2.5.3 Receive comments from SERNANP/MINAM | W2/Apr |  |  | AAE considers the timeline of 10 working days for revision by stakeholders |
|  |  | 2.5.4 Implement of Training 5 (4 days) | W3/Apr |  |  |  |
|  | D.2.5: Report from Training 5 | 2.5.5 Submit report from Training 5 | W4/Apr |  |  |  |
|  | D.2.6: Final version "Manual EbA for NPAs" | 2.5.6 Submit final version of "Manual EbA for NPAs" | W1/May |  |  |  |
| A.2.6: Development of conceptual framework surrounding EbA in Peru’s NPAs |  | 2.6.1 Define the objective and use of the "EbA for NPAs conceptual framework" – possible interviews with MINAM/SERNANP | W4/Sept | 11.5 days | Lead: SA Support: LI, ND, RB, GFV, MB, NZ | AAE suggests extending this activity until W4/May. It is considered that deliverable for this activity is very close to the Trainings and time would be limited. It is not a product that will hinder other activities. |
|  |  | 2.6.2 Submit draft version of "EbA for NPAs conceptual framework" | W2/Jan |  |  |  |
|  |  | 2.6.3 Receive comments from MINAM/SERNANP | W4/Feb |  |  |  |
|  | D.2.7: Review document on the "EbA for NPAs conceptual framework" for Peru’s protected areas | 2.6.4 Submit final version of "EbA for NPAs conceptual framework" | W2/Apr |  |  |  |
| A.2.7: Revised and updated Working Document 14 | D.2.8 Present the revised and updated Working Document 14 | 2.7.1 Submit draft revised and updated version of Document 14 to include climate change and EbA concepts | W4/Apr | 10 days | Lead: RB Support: GFV | AAE has been requested to adapt an existing working document (num 14) designed to assist area managers to prepare their management plans taking into consideration climate change and EbA approach. |
|  |  | 2.7.2 Receive comments from MINAM/SERNANP | W1/May |  |  |  |
|  |  | 2.7.3 Submit final version of revised Document 14 | W2/May |  |  |  |
| Work area 3: Development of an Action Plan for EbA approach integration in NPAs |  |  |  |  |  |  |  |
| A.3.1: Integration of EbA measures in the Cerros de Amatope National Park's master plan |  | 3.1.1 Collect data through interviews and field visit of the CA National Park to define: (i) EbA aims and measures that support the objectives National Park; (ii) identification of indicators for monitoring; (iii) identification of the location for implementation and timeline; (iv) capacity needs of staff; (v) preliminary budget and (vi) potential funding sources. | W1 - W2/Jun | 35 days | Lead: LI+RB Support: SA, ND, RB, MB, NZ | AAE considers the timeline of 07 working days for revision by stakeholders |
|  |  | 3.1.2 Submit 1st draft version of "Action Plan for integration of EbA measures into the Master Plan of CA National Park" | W2/Jun |  |  |  |
| Activities | Deliverables | Key Action Steps | Deliverable submission by week (W)/Month | Person Days | Person Responsible | Comments |
|  | D.3.1: Draft version "Action Plan for integration of EbA approaches into the master plan of the Cerro de Amotape National Park" | 3.1.3 Submit 2nd draft version of "Action Plan for integration of EbA measures into the Master Plan of CA National Park" | W4/Jun |  |  |  |
| A.3.2: Preparation of and managers training on how to define EbA measures and apply them in project documents | D.3.3: Material including final methodology for defining EbA measures and apply them to project documents | 3.2.1 Submit draft version training materials, methodology of training and agenda | W3/May | 30 days | Lead: SA+ RB Support: LI, ND, GFV, MB, NZ |  |
|  |  | 3.2.2 Receive comments from SERNANP/MINAM | W4/May |  |  | AAE considers the timeline of 07 working days for revision by stakeholders |
|  |  | 3.2.3 Submit final version of of "Methodology for managers training on how to define EbA measures and apply them in project documents", training materials, methodology of training and agenda | W1/Jun |  |  |  |
| Activities | Deliverables | Key Action Steps | Deliverable submission by week (W)/Month | Person Days | Person Responsible | Comments |
|  |  | 3.2.4 Implement Training 6 (2 days) | W2/Jun | 33.5 days | Lead: SA+RB Support: MB, NZ, ND, LI |  |
|  | D.3.5: Report from Training 6 | 3.2.5 Submit report from Training 6 | W3/Jun |  |  |  |
| A.3.3: Provision of feedback and mentorship on collection of EbA measures elaborated by NPA managers |  | 3.3.1 Define the number and methodology for providing feedback to the development of EbA measures | W2/Mar |  |  | AAE suggests clarifying in advance with the stakeholders, the number of envisioned EbA measures to be defined by NPAs, what is meant by mentorship and the timelines envisioned for this. To be taken into consideration that the timeline assigned for this activity is 2 month. |
|  |  | 3.3.2 Presentation of the Instructive and draft format on identification of EbA measures for NPAs | W4/Apr |  |  |  |
|  | D.3.6: Document compiling the feedback on EbA Measures presented by NPAs managers | 3.3.3 Provide feedback and mentoring on the development of EbA measures | W1/Jul |  |  |  |
| Work area 4:Mainstreaming EbA into the SERNANP budgeting process |  |  |  |  |  |  |  |
| A.4.1: Development of diagnostic of Peru's operational budget program model |  | 4.1.1 Review, analysis and mapping of the operational budget program model used in Peru | W1/Feb | 5.5 days | Lead :NZ Support: MB, LI, RB |  |
|  |  | 4.1.2 Identify entry points and methods to incorporate an EbA approach, as well as possible financing mechanisms. | W4/Feb |  |  |  |
| Activities | Deliverables | Key Action Steps | Deliverable submission by week (W)/Month | Person Days | Person Responsible | Comments |
| A.4.2: Formulation of recommendations on the incorporation of EbA into the SERNANP budgeting system | D.4.1: Draft version "Guidelines for incorporation of EbA into budget system of SERNANP" | 4.2.1 Submit draft version of "Guidelines for incorporation of EbA into budget system of SERNANP" | W4/May | 6.5 days | Lead :NZ Support: MB, LI, RB |  |
|  |  | 4.2.1 Receive comments from MINAM/SERNANP | W2/June |  |  | AAE considers the timeline of 10 working days for revision by stakeholders |
| A.4.3: Sharing of results | D.4.2: Final version "Guidelines for incorporation of EbA into budget system of SERNANP" | 4.3.1 Submit final version of "Guidelines for incorporation of EbA into budget system of SERNANP" | 3W/Aug | 14.5 days | Lead :NZ Support: MB, LI, RB |  |
|  | D.4.3: Summary report from Training 6 | 4.3.2 Submit report from Training 6 | 4W/Aug |  | Lead :LI Support: MB, RB, SA |  |

Legend:

1) GFV – Guido Fernandez de Velasco; MB - Monika Bertzky; LI – Lili Ilieva; ND – Nathalie Doswand;, NZ - Nancy Zapata; Renzo Barron; SA - Stanley Arguedas

2) 1W – 1 Week

| Work area/activity/deliverable | sept |  |  |  | oct |  |  |  |  | nov |  |  |  | dec |  |  |  | jan |  |  |  | feb |  |  |  | march |  |  |  | april |  |  |  | may |  |  |  | jun |  |  |  | jul |  |  |  | august |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Work area 1: Planning and communication |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.1: Development of implementation planning and communication documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.1.1 A detailed work plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.1.2 A monitoring and evaluation plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.1.3 Draft one page description of intended outcomes and impacts |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.1.4 Closure and Data Collection Report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.2: Planning and preparation of stakeholder engagement activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.1.5: Stakeholder engagement and logistics plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.1.3: Kick-off meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work area/activity/deliverable | sept |  |  |  | oct |  |  |  |  | nov |  |  |  | dec |  |  |  | jan |  |  |  | feb |  |  |  | march |  |  |  | aprl |  |  |  | may |  |  |  | jun |  |  |  | jul |  |  |  | augst |  |  |  |
| D.1.6: Brief summary report from kick-off meeting |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work area 2: Development of a manual to incorporate the EbA approach into the process of planning and management of NPAs in Peru |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.1: Review of literature and experiences in planning and development of the EbA approach |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.2: Development of draft version of the manual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.2.1: Draft EbA Manual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.3: Application of the draft version of the manual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  | 1 |  | 2 |  | 3 |  | 4 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.2.2: Report on the pilot implementation of the draft manual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.4: Revision of the draft EbA manual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.2.3: Final Draft EbA Manual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work area/activity/deliverable | sept |  |  |  | oct |  |  |  |  | nov |  |  |  | dec |  |  |  | jan |  |  |  | feb |  |  |  | march |  |  |  | april |  |  |  | may |  |  |  | jun |  |  |  | jul |  |  |  | august |  |  |  |
| A.2.5: Preparation of and training on the use of the EbA manual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.2.4: Material created for first training of managers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.2.5: Training report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.2.6: Final Manual |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.5: Development of conceptual framework surrounding EbA in Peru’s NPA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.2.7: Review document on the conceptual framework surrounding EbA in Peru’s protected areas |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.7.1: Submit draft revised and updated doc 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.7.2: Receive comments from MINAM/SERNANP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.2.7.3: Submit final version of revised doc 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work area/activity/deliverable | sept |  |  |  | oct |  |  |  |  | nov |  |  |  | dec |  |  |  | jan |  |  |  | feb |  |  |  | march |  |  |  | aprl |  |  |  | may |  |  |  | jun |  |  |  | jul |  |  |  | augst |  |  |  |
| D.2.8: Revised and updated working document 14 |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work area 3: Development of an Action Plan for EbA approach integration in NPAs |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.3.1: Integration of EbA measures in the Cerros de Amatope National Park's master plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.3.1: Draft Action Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.3.3: Material including final methodology for defining EbA measures and apply them to project documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.3.2.1: Submit draft version training materials, methodology of training and agenda |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.3.2.2 Receive comments from MINAM/SERNANP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.3.2.3: Submit final version |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work area/activity/deliverable | sept |  |  |  | oct |  |  |  |  | nov |  |  |  | dec |  |  |  | jan |  |  |  | feb |  |  |  | march |  |  |  | aprl |  |  |  | may |  |  |  | jun |  |  |  | jul |  |  |  | augst |  |  |  |
| A.3.2.4 Training implementation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.3.5: Training report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.3.3: Provision of feedback and mentorship on collection of EbA measures elaborated by NPA managers |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.3.3.1 Define number and methodology for providing feedback to the development of EbA measures |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.3.3.2 Presentation of instructive and draft format on EbA identification |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.3.6: Feedback report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work area 4: Mainstreaming EbA into the SERNANP budgeting process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.4.1: Development of diagnostic of Peru's operational budget program model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Work area/activity/deliverable | sept |  |  |  | oct |  |  |  |  | nov |  |  |  | dec |  |  |  | jan |  |  |  | feb |  |  |  | march |  |  |  | april |  |  |  | may |  |  |  | jun |  |  |  | jul |  |  |  | august |  |  |  |
| A.4.2: Formulation of recommendations on the incorporation of EbA into the SERNANP budgeting system |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.4.1: Draft guidelines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| A.4.3: Sharing of results |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.4.2: Final guidelines |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| D.4.3: Summary report from the final event |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |