| Proposal title: | Technical guidance and support to conduct a sectoral technology needs assessment and a technology action plan for Sierra Leone |
| --- | --- |
| Country: | Sierra Leone |
| National designated authority: | Prof. Foday Jaward Executive Chairman Environmental Protection Agency |
| Implementing Institution: | UNEP – The Climate Technology Centre and Network (CTCN) |
| Date of first submission: | 1 May 2020 |
| Date of current submission / version number | 1 May 2020 V.1 |

How to complete this document?

This document should be completed by National Designated Authorities (NDA) or focal points with support from their Delivery Partners where relevant. Once completed, this document should be submitted to the GCF by the NDA or focal point via the online submission system, accessible through the Country Portal of the GCF website.

Please be concise. If you need to include any additional information, please attach it to the proposal.

If the Delivery Partner implementing the Readiness support is not a GCF Accredited Entity for project Funding Proposals, please complete the Financial Management Capacity Assessment (FMCA) questionnaire and submit it prior to or with this Readiness proposal. The FMCA is available for download at the Library page of the GCF website.

Where to get support?

If you are not sure how to complete this document, or require support, please send an e-mail to countries@gcfund.org.

You can also complete as much of this document as you can and then send it to countries@gcfund.org, copying both the Readiness Delivery Partner and the relevant GCF Regional Desks. Please refer to the Country Profiles page of the GCF website to identify the relevant GCF Country Dialogue Specialist and Regional Advisor.

We will get back to you within five (5) working days to acknowledge receipt of your submission and discuss the way forward.

Note: Environmental and Social Safeguards and Gender

Throughout this document, when answering questions and providing details, please make sure to pay special attention to environmental, social and gender issues, particularly to the situation of vulnerable populations, including women and men. Please be specific about proposed actions to address these issues. Consult Annex IV of the Readiness Guidebook for more information.

| - SUMMARY |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| 1.1 Country submitting the proposal | Country name: |  |  | Sierra Leone |  |  |
|  | Name of institution representing NDA or Focal Point: |  |  | Environmental Protection Agency |  |  |
|  | Name of contact person: |  |  | Prof. Foday Jaward |  |  |
|  | Contact person’s position: |  |  | Executive Chairman |  |  |
|  | Telephone number: |  |  | +23276423645 |  |  |
|  | Email: |  |  | fmjaward@hotmail.com |  |  |
|  | Full office address: |  |  | 21 Old Railway Line Brookfields, Freetown, Sierra Leone |  |  |
|  | Additional email addresses that need to be copied on correspondences: |  |  | Gabriel Kpaka gabrielkpaka@gmail.com |  |  |
| 1.2 Date of initial submission | 30 June 2020 |  |  |  |  |  |
| 1.3 Last date of resubmission | Click or tap to enter a date. (Please update for each resubmission.) |  | Version number |  |  | V.1 |
| 1.4 Which institution will implement the Readiness and Preparatory Support project? | ☐ National designated authority ☒ Accredited entity ☒ Delivery partner Please provide contact information if the implementing partner is not the NDA/focal point |  |  |  |  |  |
|  | Name of institution: |  |  | United Nations Environment Programme (UNEP) on behalf of The Climate Technology Centre and Network (CTCN) |  |  |
|  | Name of official: |  |  | Kelly West |  |  |
|  | Position: |  |  | GCF AE Focal Point |  |  |
|  | Telephone number: |  |  | +254-20 76 24147 |  |  |
|  | Email: |  |  | kelly.west@un.org; |  |  |
|  | Full office address: |  |  | United Nations Avenue, NFO Block 2-3 NW P.O. Box 30552-00100 Nairobi, Kenya |  |  |
|  | Additional email addresses that need to be copied on correspondences: |  |  | Rose Mwebaza, Director CTCN, mwebaza@un.org Rajiv Garg, gargr@un.org Hemini Vrontamitis, hemini.vrontamitis@un.org; unep-gcf@un.org |  |  |
| 1.5 Title of the Readiness support proposal | Technical guidance and support to conduct a sectoral technology needs assessment and a technology action plan for Sierra Leone |  |  |  |  |  |
| 1.6 Type of Readiness support sought | Please select the relevant GCF Readiness objective(s) below (click on the box – please refer to Annex I and II in the Guidebook): ☐ I. Capacity building ☒ II. Strategic frameworks ☐ III. Adaptation planning ☒ IV. Pipeline development ☐ V. Knowledge sharing and learning |  |  |  |  |  |
| 1.7 Brief summary of the request | The purpose of this proposal is to offer technical guidance and support to Sierra Leone to conduct a sectoral technology needs assessment and develop a technology action plan. The sectoral TNA will complement the national processes and enable technology transfer to aid in the realization of the country climate change and development strategies as contained in their NDC, NAPA, National Climate Change Strategy and Action Plan (NCCS&AP) and National Climate Change Policy (NCCP). The sectoral TNA assistance will focus on technology prioritization, whose process will focus on the costs and benefits of technologies within the national context. Additionally, it will focus on a technology action plan that will outline a group of measures for addressing barriers and accelerating the development and transfer of prioritized technologies. It will also incorporate components of capacity building to governmental and non-governmental institutions such as the private sector. This sectoral TNA work to be conducted in Sierra Leone will greatly contribute to establishment of coordination mechanism amongst the UNFCCC focal point as well as other key climate stakeholders within the country. These will enhance their capacity to effectively fulfil their roles and responsibilities to drive the country action on climate change. The output of this work which will include, development of technology Action Plans (TAP) and concept notes for the action plan implementation, will contribute to creation of a country programming process. The development of transformational pipeline projects concept note will thus create a framework to channel climate investment and funding in the country. The process involves institutional strengthening to enable effective coordination of action and will reflect a country-driven, participatory approach among the different actors in the prioritized sectors. The anticipated outcomes are envisioned to present strategies for long-term, participatory transformational measures across the identified and prioritized sectors that will drive climate resilient and low carbon growth. Crucial to its implementation is the achievement of high-level political support, fund mobilization and private sector and key stakeholders’ engagement. The work will be conducted taking into consideration the broader context of the Technology Needs Assessments conducted by many countries and recognized by the COP as a key element for technology identification and planning to address climate change challenges. The development of the reports will take into account the guidance developed and available on http://www.tech-action.org/ |  |  |  |  |  |
| 1.8 Total requested amount and currency | USD 384,327 | 1.9 Implementation period |  |  | 18 months |  |
| 1.10 Is this request a multiple-year strategic Readiness implementation request? |  | ☐ Yes ☒ No For more information on how a country may be eligible to access Readiness support through this modality, please refer to Annex III of the Readiness Guidebook. |  |  |  |  |
| 1.11 Complementarity and coherence of existing readiness support |  | ☐ Yes ☒ No Sierra Leone has not received GCF readiness and preparatory support. The activities to be conducted in this proposal will contribute to creating a coordination mechanism of the country UNFCCC focal points (NDA and NDE) as well as other relevant climate stakeholders including the private sector. The output of the work will also contribute to a country programming with a focus to climate technology deployment to drive climate action. Sierra Leone has previously received support from other various UN agencies including UNDP and GEF, that has mainly helped the country to develop its national climate change policies and strategies as well as National communications related to various conventions under the UNFCCC. This includes NAPA and NCCS&AP. This readiness proposal to develop the country TNA and its Action plan will leverage on the establish stakeholders’ channels established through this previous works and will also ensure consultation with these agencies to gather useful lessons and experiences learnt. |  |  |  |  |

- SITUATION ANALYSIS

Sierra Leone has been ranked as the most vulnerable nation after Bangladesh and Guinea Bissau to adverse effects of climate change. The population is highly vulnerable to climate change and due to high reliance to rain fed agriculture and natural resources-based livelihoods which are hard hit by resulted of the associated global temperature increase. This is despite that the country Greenhouse gases emissions (GHGs) are negligible. Thus, the country needs to plan accordingly and integrate climate change planning across its sectors. In this regard Sierra Leone is committed to mainstreaming inclusive green growth in her development process. Sierra Leone’s vision for 2013 to 2035 is to become a middle-income country. It would be an inclusive, green country, with 80% of the population above the poverty line. It would have gender equality, a well-educated, healthy population, good governance and rule of law, well-developed infrastructure, macroeconomic stability, with private sector, export-led growth generating wide employment opportunities. In addition, there would be good environmental protection, and responsible natural resources exploitation. Sierra Leone acceded to the United Nations Framework Convention on Climate Change (UNFCCC) in 1995 as a non-Annex I Party to the convention. Since signatories to the Conventions are requested to report periodically on their inventory of anthropogenic emissions and removal of greenhouse gases (GHGs) not controlled by the Montreal protocol as well as details of the activities the Party has undertaken to implement the Convention. Sierra Leone has thus presented 3 national communications with their respective greenhouse gases inventories to the UNFCCC. The country submitted its initial National communications (INC) in November 2005. The INC included a GHG inventory for the reference year 1994 in compliance with Article 4 and 12 of the UNFCCC and prepared in accordance with the intergovernmental Panel on Climate Change (IPCC) 1996 Revised Guidelines for preparation of National GHG Inventories. The INC also included vulnerability and adaptation assessment for the agriculture, water and coastal zone sectors. The second National communication (SNC) included GHG inventories for 2000-2005 and reference year 2000, prepared using the same 1995 IPCC inventory guidelines. The SNC also assessed climate change impacts for the key sector of health, human settlement, and tourism. Although not required as a non –Annex I party, Sierra Leone’s SNC also included an assessment of potential mitigation options to reduce GHG emissions without concrete targets that will, just as importantly, improve energy efficiency. This Third National Communication (TNC) included GHG inventories for 2005-10 and reference year 2005. Prepared using the 2006 IPCC inventory guidelines the TNC also assesses climate change impacts for the key sectors of agricultural, water, health, coastal areas, human settlement, and to some extent tourism. Sierra Leone’s TNC included an assessment of potential mitigation options to reduce GHG emissions without concrete targets that will just as importantly, improve energy efficiency. Sierra Leone has also developed and adopted its National Adaptation programme of Action (NAPA), National Climate Change Policy (NCCP) and National Climate Change Strategy and Action Plan (NCCS&AP) around which its NDC revolves. Since the year 2000, Sierra Leone has published three National Strategies on Climate Change and in 2009 adopted its first Special Program on Climate Change. The country’s NDC aims to transition to low emissions development involving decoupling carbon emissions from economic growth through a series of measures across all economic sectors. The main sector of focus includes: energy sector where the strategies includes to ensure a fair, equitable, sustainable supply and distribution of electricity for development. The sector also aims to shift from thermal power generation to cleaner energy mix, for example solar, hydro, ion-diesel gas, biogas, LPG etc. The transport sector is marked as a key sector that would contribute to climate change mitigation through improvement of bulk public transport system (buses, rail) as well as vehicle emissions control mechanisms. Waste sector is seen to contribute highly in GHGs emission and thus the sector is marked as a priority for mitigation. Agriculture is the key economic driver and the agricultural systems are small holders and rain fed which are highly vulnerable and thus the need to build the population capacity to adopt smart agriculture practices to build their resilience. That sector is also a key contributor to the emission of GHGs. Other sectors prioritized include mining, forestry, and water. Below is an illustrator of the country’s emission projections. Table 2: Projected GHG Emissions (MtCO2e) from Sierra Leone from 2015 to 2030.. Sierra Leone; 2015; 2020; 2025; 2030. All sources, Gases, sectors; 4.765; 5.239; 5.851; 6.551. CH4; 3.670; 4.029; 4.458; 4.970. N2O; 0.997; 1.069; 1.156; 1.271. Agriculture; 2.107; 2.224; 2.374; 2.575. Energy; 0.001; 0.001; 0.001; 0.001. Industrial processes; 0.097; 0.142; 0.238; 0.311. Waste; 2.559; 2.872; 3.239; 3.664. Source:http://www.epa.gov/climatechange/EPAactivities/economics/nonco2projections.html. Technology is an important aspect to be taken into consideration in climate change both in strengthening mitigation and adaptation measures and building resilience. The absence of a comprehensive Technological Need Assessment (TNA) for the country increases the difficulties in determining the level and extent of support needed for implementation of the National Determined Contribution (NDCs) and other national development priorities as well as the Sustainable Development Goals (SDGs). International cooperation is cited as an important prerequisite for leveraging of inputs for the implementations of the NDC. Among them is improving and adoption of technologies for climate change mitigation and adaption. Sierra Leone faces obstacles to advance climate technologies adoption needed to strengthen mitigation and adaptation measures and building resilience. The country faces lack of specialized skills required in climate technologies, innovations and knowledge. Other barriers include inadequate infastructure services to ease acquisition of appropriate technologies, lack of market awareness, lack of research and development of green technologies, inadequate incentives and enabling environment for technology transfer. Generally, these barriers affect the development and transfer of climate technologies in the country. This proposal will support the country to develop its sectoral technology needs assessment (TNA) and a technology Action Plan (TAP) that will guide the TNA implementation. The concept notes developed through this proposal for the TAP implementation will inform the country’s project pipeline that will spur national and multilateral climate financing to enable the country fulfil their NDCs ambitions. The sectoral TNA assistance will focus on technology prioritization for priority sectors guided by the NDC and will include costs and benefits of technologies within the national context. Additionally, it will focus on a technology action plan that will outline a group of measures for addressing barriers and accelerating the development and transfer of prioritized technologies. The sectoral TNA process of identification and prioritization of the climate technology will be conducted in a consultative manner that entail bring together various stakeholders including the NDA, NDE, and other key institutions: academic, research, indigenous group, private sectors among others. This will ensure enhancement of the stakeholders capacity to support the planning and country programming process and implementation of climate change activities in the country. The work will also incorporate components of capacity building to governmental and non-governmental institutions such as the private sector. The anticipated outcome is to present strategies for a long-term, participatory transformational measures across the identified and prioritized sectors that will drive climate resilient and low carbon growth.

- LOGICAL FRAMEWORK

| Outcomes | Baseline | Targets | Outputs | Activities (brief description) | Deliverables |
| --- | --- | --- | --- | --- | --- |
| Outcome 1.3 Relevant country stakeholders (which may include executing entities, civil society organizations and private sector) have established adequate capacity, systems, and networks to support the planning, programming, and implementation of GCF-funded activities | There is Communication initiated between NDA, NDE and other climate finance focal points. However, there is no formal channel for the execution of the TNA work. Also, the current communication mechanism is mainly limited to | Established Stakeholder coordination mechanism to include different climate actors in the country (government a non-governmental actors) with enhanced capacity to drive climate change action to achieve the countries climate commitments as per the NDC. | Output 1.3.1 Effective coordination mechanism between NDA and NDE for the UNFCCC Technology Mechanism and other climate finance focal points | Activity 1.3.1a Establishment of a coordinating mechanism for stakeholders’ engagement through creation of a national TNA committee. The TNA Committee is the key guiding body of the project. Its role is to provide high level guidance and help secure political acceptance for the TAP. The exact composition role and responsibilities will depend on national context. The TNA committee will be formed by approximately 10 members including the TNA coordinator. The TNA Committee will include representatives from the public, private, and academic sectors and consider gender balance and appropriate representation. The NDE and NDA will play a leading role in supporting the establishment of the TNA Committee. Preparation of the TNA Committee Constitution document where rules and procedures of the TNA process, and roles of the different members will be defined. Establishment of a centralized office for TNA coordination to enable the coordination mechanism to commence. Organization of a capacity building training on the TNA processes across all national stakeholders over 2 workshop sessions (Month 3-4) (2 days for each workshop). On the overall process and different steps for conducting the TNA (workshop 1), and on the participatory planning and prioritization tools (e.g. multi criteria assessment tool, stakeholder engagement tools, and approaches for gender inclusiveness) (workshop 2). The training will strengthen the knowledge about the TNA process to be followed and the engagement of the national stakeholders involved in the process. Additionally, it will include the importance of understanding and applying environmental and social safeguard approaches, including incorporation of gender considerations throughout the process, developing the sectoral TNA and prioritizing technologies. A work plan that will define and schedule TNA meetings to be conducted in country for stakeholders engaged in the TNA committee will be developed. The TNA Committee will be engaged at all important steps of the TNA process to ensure national consultation and country ownership of the process and results of the work, the TNA committee will meet on a quarterly basis in the duration of the project. | Deliverable 1.3.1a (i), Official government circular establishing the national TNA committee Deliverable 1.3.1a (ii), TNA Constitution document informing on the work of the TNA Committee Deliverable 1.3.1a (iii), TNA Committee Work plan Deliverable1.3.1a (iv), Report of quarterly TNA committee meetings Deliverable 1.3.1a (v); Set up of a central coordination office Deliverable 1.3.1a (vi), Training report for the 2 workshops |
|  |  |  |  | Activity 1.3.1b Conduct Stakeholders mapping for stakeholders to be involved in the sectoral TNA process. This activity will aim to Identify key stakeholders to be directly involved in the National TNA Committee running the project, including key ministries in charge of the different sectors and associated organizations, private sector, research organizations and gender focal points. Clarify roles and responsibilities of each stakeholder at the country level to be consistent with national objectives, recognizing the distinct roles, experience and contributions to technology use and adoption of men and women. During the activity, the type of participants to be invited to the various workshops will be defined. The approach will be to reach a representation of institutions, civil society, private sector, and academia enabling a proper outreach, dissemination, and institutionalization of the project results as well as local communities’ involvement. Gender aspects will be also considered through fair representation of women and men as well as through participation of gender focal points and associations that promote gender equality and the empowerment of women (GEEW). 2-day workshop for the stakeholders identified - expected to have participants between 30-40 persons. | Deliverable 1.3.1b (i), Stakeholder mapping report, where roles and responsibilities are specified. Deliverable 1.3.1.b (ii), Report of the 2 -day stakeholders’ workshop (including list of participants, photo and other relevant documentation) |
|  | There is no formal participation process that has been established for engagement of private sector climate technology deployment in the country. | Established Engagement mechanisms for private sector and enhancing their capacity to get involvement of private sector in climate technology deployment | Output 1.3.2 Strengthened Private sector (with a focus on SME) capacity and creation of an enabling environment for their participation in climate technology adoption through innovative new business identification training programme | Activity 1.3.2 Enhancing SME capacity and enabling environment through innovative new business identification training programme. The private sector will play a key role in achieving climate goals. This activity aims at engaging with the private sector/ SMEs within the country and assisting in the identification of the country’s’ business needs and exploring new business opportunities in climate technology. This activity will gain input of the private sector actors and perspective sharing on the market readiness of technologies and the potential deployment. A two-day workshop will be organized for up to 50 public and private stakeholders. The workshop will present the results of the outcome 2.2 activities, including but not limited to the technology identified and the Technology action plan. The workshop will share lessons learned coming from the private sector, engage public and private stakeholders in topic/sector roundtables, and identify innovative business and training programmes. The list of participants will be prepared in consultation with the TNA Committee and will target private sector actors in the country. The identification of these actors well in advance is essential for the success of this activity. | Deliverable 1.3.2, Workshop report, including a full list of participants and photos |
| Outcome 2.2 GCF recipient countries have developed or enhanced strategic frameworks to address policy gaps, improve sectoral expertise, and enhance enabling environments for GCF programming in low emission investment | There is no appropriate climate technologies identified and prioritized. | Identified and prioritized climate technology for deployment of technologies for adaptation and mitigation to be operationalized through a Technology Action Plan | Output 2.2.1 Identifying and prioritizing appropriate climate technology solutions identified and prioritized and their feasibility assessed and incorporated for mitigation and adaption planning processes | Activity 2.2.1a, Pre-selection of sub-sectors for the fulfilment of Sierra Leone sectoral TNA The objective of this activity is to identify and obtain consensus about priority sectors (and subsectors) to shape the TNA. An analysis of the sectorial priorities expressed in the national development policies and strategies (including national policies for private sector engagements and gender mainstreaming), the NDC, NAPA and National Communications to UNFCCC, and other key strategic framework documents will be undertaken. This will represent a participatory work that will contribute to harmonize the national initiatives on climate. The Country Programme will represent the main baseline to start from. The other national initiatives (NDC, NAPA, National Communications to UNFCCC, etc.) will complement the process serving as a cross-check reference to ensure country ownership. The TNA will then bring into the country programme the technology dimension and selection and will lay the basis for new projects preparation that can address PPF, full size scale and the PS facility of the GCF, in light of scale up funding purposes. Based on this analysis, 4 sectors will be selected by the TNA Committee during a series of meetings facilitated by the provision of selection methodologies. The implementor will organize a one 2-days consultation workshop with stakeholders identifies in the above activities. Further bilateral meetings with sectoral specific stakeholders will also be used to refine the sectors prioritized. | Deliverable 2.2.1a (i), Report on TNA-TAP alignment with national plans and strategies and how the TAP would enable creation of a country programming. Deliverable 2.2.1a (ii), Report on analysis of sectorial priorities expressed in national documents Deliverable 2.2.1a (iii), Report describing the methodology utilized for sector and subsector selection and prioritization Deliverable 2.2.1a (iv), Stakeholders consultation workshop report |
|  |  |  |  | Activity 2.2.1b, Assess, prioritize, and validate key technologies for the fulfillment of the sectoral TNA This activity will include a Multi-Criteria Analysis (MCA) for assessing adaptation and mitigation technologies. A data information system will be created for capturing input to technology prioritization and selection as well as for having the function of a repository of key documents produced during the assessment process. They could be reused for future updating and further deepening of the TNA process. Fact sheets and data information system will be gender responsive. The prioritization and validation will be done through a series of 4 workshops (one workshop per sector). The stakeholders invited will be selected together with the TNA committee and limited to 20 participants per workshop. Gender balance of participants and facilitators will be promoted. During the workshops, up to 3 technologies per sector will be prioritized using the MCA, based on criteria covering key economic, social, and environmental aspects as well as innovation and RD&D factors based on CP recommendations. This ensures that technologies selected are the best available solution to fulfill key environmental and social safeguards. | Deliverable 2.2.1b (i), 10 technology fact sheets. Deliverable 2.2.1b (ii)Report detailing the set of criteria for MCA exercise. Deliverable 2.2.1b (iii), Workshops reports including a full list of participants and photo documentations. Deliverable 2.2.1b(iv), Final reports including a mitigation TNA report and an adaptation TNA report. Deliverable 2.2.1b(v), Database in most suitable format |
|  |  |  |  | Activity 2.2.1c, Development of a Technology Action Plan per sector and /or sub sector. Technology Action Plan (TAP) comprising recommendations on project ideas for each of the analyzed sectors. It will quantify the potential impact of priority technologies. The process for the development of this TAP will involve interviews and bilateral consultations with key stakeholders across the public, private and academic setting and will target various experts depending on the (sub) sectors and technology prioritized. The TAPs will be gender mainstreamed. The TAP will include -Elaborate detailed project ideas (circa 10 pages), including time frames and estimated budget requirements for each prioritized technology. -Articulate project idea objectives, outputs, in relation to national policy priorities, deliverables, activities, and monitoring/evaluation methods. -Conduct barriers analysis and assessment of enabling environment for the development and deployment of the identified technology. -Elaborate on innovation and RD&D. This is a topic that has been introduced into the new Technology Framework at COP24. The country will also receive indications on how to strengthen its technology innovation. This may entail an assessment of endogenous technologies and consider elements such as RD&D within the prioritized technologies and action plan. -Evaluate capacity-building needs to support the implementation of the TAP. -Include a market assessment, that would entail analysis of financial schemes, value chains, risks, and overall barriers to implementation. -Present a clear financial plan with timelines, benchmarks, and indicators. -Include gender assessment of the technology. -Consider regulatory, institutional, financial and information frameworks that may prevent the accelerated development of markets for identified prioritized technologies. -Determine technology impact potential in terms of Sierra Leone’s GHG emissions reduction and adaptation targets (conditional and unconditional), employment impact, potential co-benefits (mitigation and adaptation) resulting from the implementation of technologies prioritized | Deliverable 2.2.1c Technology action plan report for the implementation of the TNA. |
|  | formal consultation process has not been established for climate technology identification process | A coordinated engagement of relevant stakeholders in a consultative process for the identification of adaptation and mitigation technologies | Output 2.2.2, Stakeholders engagement and information dissemination for enhanced country ownership and technology deployment | Activity 2.2.2a, Conduct national consultation workshops This activity aims to engage the TNA Committee and key stakeholders (up to 50 participants) in the discussion and validation of the TAPs prepared in activity above, during a two-day National Consultation Workshop. The workshop is also aiming at selecting the most relevant project idea within the TAP to be then transformed into a concept note. The workshop will enable experience sharing, idea generation, lessons learned and best practices. This is aimed at assisting identified stakeholders with the familiarization of identified technologies, to enhance technical capacity, operation and maintenance, and data collection. | Deliverable 2.2.2a (i), Workshop report |
|  |  |  |  | Activity 2.2.2b, Support the implementation of the Technology Action Plan with communications, guidance, and training The objective of this activity is to deliver a capacity building package for TNA key stakeholders including training and support materials for the development and application of prioritized technologies. Relevant participants will include the NDA, NDE, GCF and GEF focal points. The training will be delivered to the TNA stakeholders in 4 regional workshops (2days for each workshop). The location of the 4 workshops will be decided in consultation with the TNA Committee. The total number of participants per workshop is up to 20. Prior to the workshops, policy briefs and market-use cases for the selected technologies under activity 2.2.1b will be prepared. A dissemination strategy for the regions will also be prepared. Experts will be presenting the following modules: - market mapping and problem trees to enable them to become more familiar with identified technologies. - gender awareness tools to enhance implementation capacities. - access to financing of prioritized technologies across domestic and international sources. - environmental and social risk considerations of each of the technologies. - technical capacity, operation, maintenance, and data collection, - capacity building and technology development opportunities. | Deliverable 2.2.2b (i), Policy briefs and market-use cases for the selected technologies Deliverable 2.2.2b (ii), Report on the dissemination strategy Deliverable 2.2.2b (iii), Training materials for the regional workshops Workshops reports, including a full list of participants and photo documentation. |
| Outcome 4.3 An increase in the number of quality project concept notes developed and submitted that target SIDS, LDCs and African states | No quality project concept notes developed for climate technology deployment in the country | Development of quality CNs to enrich the country project pipeline | Output 4.3.1 Concept Notes for Technology Action Plans operationalization developed | Activity 4.3.1, Developing concept notes for priority sectors for submission to the GCF, Concept notes will be developed based on the Technology Action Plan on the sub-sectoral technologies prioritized. The concept note developed will enable the NDA to present a detailed project document GCF and/or other funding institutions). this activity will take in account discussions from stakeholders’ consultation under activity 2.2.2a. that will include discussions to select the most relevant project idea within the TAP to be then transformed into concept notes. | Deliverable 4.3.1, Four Concept notes developed |

- THEORY OF CHANGE

This proposal will support the country to develop its sectoral TNA and a technology Action Plan (TAP) that will guide the TNA implementation. The sectoral TNA assistance will focus on technology prioritization and will include costs and benefits of technologies within the national context. Additionally, it will focus on a technology action plan that will outline a group of measures for addressing barriers and accelerating the development and transfer of prioritized technologies. It will also incorporate components of capacity building to governmental and non-governmental institutions such as the private sector. The anticipated outcome is to present strategies for a long-term, participatory transformational measures across the identified and prioritized sectors that will drive climate resilient and low carbon growth. This grant will support the sectoral Technology Needs assessment process that will involve institutional strengthening to enable effective coordination of climate action that will reflect a country-driven, participatory approach among the different actors to drive effective climate technology deployment for Sierra Leone prioritized sectors. This proposed work is expected to lay a foundation to the country readiness and programming process, taking into account that the country has not received any readiness and preparatory support. The proposal contributes to the following key outcomes: - Relevant country stakeholders (NDA/NDE, civil society organizations and private sector) have established adequate capacity, systems, and networks to support the planning, programming, and implementation of GCF-funded activities - Enhancing Sierra Leone strategic frameworks to address policy gaps, improve sectoral expertise, and enhance enabling environments for GCF programming in low emission investment - Development of transformational quality project concept notes to in constitute the country’s project pipeline The grant under this proposal main goal is therefore to support Sierra Leone meet their climate change ambitions as elaborated in the country NDC, NAPA, NCCP AND NCCCS&AP, which will greatly advice the sectoral TNA process as the key inputs. This will thus make a major contribution toward the country paradigm shift towards low emission and climate resilient development pathways. The proposal outputs will be achieved through establishment of country coordination mechanism, technology prioritization / action plan / capacity building to all relevant parties: consultation and engagement with relevant stakeholders including the private sector to ensure country ownership of the process and technologies prioritized. The anticipated outcomes are envisioned to present strategies for a long-term, participatory transformational measures across the identified and prioritized sectors that will drive climate resilient and low carbon growth. The key assumption to effective TNA process is the achievement of high-level political support, and private sector and key stakeholders’ interest and engagement in the TNA process.

- IMPLEMENTATION ARRANGEMENTS AND OTHER INFORMATION

5.1 Budget plan

Please see the completed procurement plan developed in the specified GCF format and attached.

5.2 Procurement plan

Please see the completed procurement plan developed in the specified GCF format and attached.

Please note that overall financial management and procurement of goods and services under this readiness and preparatory support proposal will be guided by UN regulations, rules, policies and procedures and the Framework Agreement between the GCF and UNEP.

UNEP will be responsible for the implementation of the readiness activities and for procurement and contractual services, as well as reporting on the progress of this implementation in close coordination and strategic guidance from the NDA/FP. The procurement actions and the operational services will be carried forward in accordance with UN policies and procurement guidelines. None of the parties involved in the preparation of this GCF readiness proposal can bid for the implementation of the project in whole or in part.

CTCN procedure for procurement: for a request that is eligible and prioritized, the Climate Technology Managers in charge of the respective request sources the appropriate expertise to develop the Terms of Reference of the assistance (called ‘Response Plan’ as per CTCN procedures). The response plan provides specific information on the technical assistance to be delivered, including activities, outputs, expected outcomes and impacts, timeline, indicators or measuring assistance progress and success, stakeholders to be involved, etc. The response plan, once finalized, is signed by the national focal point of the CTCN in the concerned country (National Designated Entity), the institution which originated the CTCN request for technical assistance and the CTCN Director and constitutes the basis of the assistance to be implemented and monitored upon the approval and in cooperation with the NDA. Based on the needs and expertise required in the response plan, a CTCN Network Member will be selected to implement it.

The selection of the institution from the Network of CTCN for the execution of the technical assistance is conducted through a competitive procurement process as per UNEP Rules and Regulations, in line with CTCN procedures and with UN Rules and Regulations (being UNEP the host of the CTCN, and a specialized agency established under the UN Charter). The CTCN nurtures a Network of more than 450 expert organizations in the field of low-carbon and climate resilient technologies. The CTCN network members are drawn from organization from different countries worldwide and with work experiences across different countries including conflict and post conflict zones. The procurement criteria for execution of this work with ensure procuring of organization with pre-requisite working experience in such environments. The required expertise to carry out the activities that define this intervention will be sourced from the Network. For this, the following four principles shall be given due consideration when undertaking the procurement functions of UNEP:

i.	Best value for money principle;

ii.	Fairness, accountability, integrity and transparency of the procurement process;

iii.	Effective competition;

iv.	The best interest of the UNEP.

5.3 Implementation Plan

Please see the completed procurement plan developed in the specified GCF format and attached.

5.4 Disbursement schedule

UNEP as the Delivery Partner for this Readiness and Preparatory Support Proposal will submit requests for disbursement for approved proposals to the GCF in accordance with the Framework Readiness and Preparatory Support Grant Agreement between the GCF and UNEP. Disbursement requests will be signed by the authorized representative of the UNEP and will include details of the bank account into which the grant will be deposited. UNEP, the Delivery Partner for this R&P Support Proposal for Sierra Leone, will administer the grant disbursed by the GCF in accordance with UNEP’s regulations, rules, and procedures including maintenance of records of grant, disbursements and expenditure.

Please choose one option among the two below and delete the one that does not apply to you. Please fill in information under brackets: ☒ Readiness Proposal that falls within a Framework Agreement with the GCF Disbursements will be made in accordance to Clause 4 “Disbursement of Grants” and Clause 5 “Use of Grant Proceeds by the Delivery Partner” of the Framework Readiness and Preparatory Support Grant Agreement entered into between GCF and UN Environment Programme on 11 October 2016 as further amended and restated on 2 June 2020 . The Delivery Partner is entitled to submit 2 request(s) for disbursement each year and is also entitled to request one interim request for disbursement within 30 days of notification of approval ☐ Readiness Proposal that requires a bilateral Grant Agreement - Please include an indicative disbursement table showing the expected amounts to be requested and keep to multiples of USD 5,000. - The first disbursement amounting [Choose Currency] [Type the amount] will be transferred upon approval of the readiness request and effectiveness of the Grant Agreement; - The second disbursement amounting [Choose Currency] [Type the amount] will be transferred upon submission of an interim progress report [and audited financial report], in form and substance acceptable to the Fund, [including an audited expenditure statement]; and - The third disbursement amounting [Choose Currency] [Type the amount] will be made upon submission of a completion report and financial report, in form and substance acceptable to the Fund, including an audited expenditure statement.

- IMPLEMENTATION ARRANGEMENTS AND OTHER INFORMATION

6.1 Implementation arrangements

Please describe how implementation arrangements will be made and how funds will be managed by the NDA and/or the Delivery Partner.

As per UN regulations, rules, and procedures, UNEP will manage the funds for the activities under this readiness proposal. UNEP will agree on a plan with the Sierra Leone NDA/NDE to monitor the implementation of the activities. However, UNEP will be responsible for the implementation of the activities under this readiness and preparatory support proposal. The selected entity from the Network will report to UNEP as per their contractual arrangement and in line with UN rules and regulations. They will produce regular progress and financial reports and will submit deliverables to UNEP. Funds will only be released when the deliverables are satisfactory and cleared by UNEP. They will return any unspent funds within ninety days of expiry or notice of termination of the UNEP. The UNFCCC country focal points for technology (NDE) and finance (NDA) will provide active support to the selected Network Partner in the execution of this technical assistance. Their roles as country focal points will include, but not be limited to: Ensuring the activities associated with the implementation of this technical assistance are aligned with national climate priorities; promote and engage with key stakeholders as identified by the Network Partner; promote and present this technical assistance in climate change-related events; and participate in CTCN events and in national workshops affiliated with this technical assistance, if required. They will also be expected to provide guidance and review any relevant documents produced and will be kept apprised of the progress of the technical assistance. The role of the NDE and NDA is that of coordination and will play a key role in establishment of a TNA committee that will oversee the TNA process. The committee will ensure effective engagement of the country stakeholders to ensure country ownership of the process. In terms of Governance: Climate Technology Centre and Network (CTCN) was established by Conference of the Parties (COP) in Cancun in December 2010. The CTCN was established to provide technical assistance and capacity building activities responding to requests from developing country parties Following competitive bidding, the COP decided that the CTCN would be hosted by UNEP through a consortium to be co-led by UNIDO. This is the CTCN ‘host’. CTCN also has an extensive network of organizations that can collaborate to successfully deliver this project. A network of 550 organizations has subsequently joined the CTCN. The CTCN (hosted by UNEP-UNIDO) aims to provide technical assistance to the Government of Sierra Leone, as per its COP Mandate, and is thus supporting Sierra Leone to develop this readiness proposal. The CTCN Engagement with the Government of the Sierra Leone is strong with close co-operation between the NDA and NDE. For work under this proposal, UNEP will be responsible for the implementation of the readiness activities and for procurement and contractual services, as well as reporting on the progress of this implementation in close coordination and strategic guidance from the NDA/FP. The procurement actions and the operational services will be carried forward in accordance with UN policies and procurement guidelines. UNEP have significant experience of delivering and supporting similar projects among other projects in developing countries. They have a wide network of local/ regional offices and expertise of the West Africa region. The implementation map below summarizes the different interactions between the different parties involved in this technical assistance

6.2 Implementation and execution roles and responsibilities

Please briefly describe how the activities will be implemented and outputs delivered by project staff and consultants.

CTCN processes before the selection of the Network Partner (described in the implementation map) The CTCN process for managing technical assistance is the following: Requests for technical assistance can be prepared by any applicant organization from a developing country, but all requests must be submitted by the CTCN NDE (national focal point in the concerned country). Once submitted, all requests submitted by developing countries are assessed as per eligibility, balancing and prioritization criteria approved by the CTCN Advisory Board. The three eligibility criteria are the following: 1) The support provided will contribute to increased resilience and/or mitigate emissions, and is aligned with national plans; 2) The support will enhance endogenous capacities; and; 3) Processes are in place in the requesting country to monitor and evaluate any support provided (that is, project accountability is ensured). Balancing criteria are looking at inter and intra-regional a geographical balance (with a preference for requests submitted by LDCs and other highly vulnerable and low capacity countries; balance between adaptation and mitigation objectives, and balance between various types of support spanning the technology cycle. Prioritization criteria consider a number of elements that demonstrate project strengthen and potential for success, including the promotion of endogenous capacities and appropriate technologies, potential for scale up, for South-South cooperation, for leveraging public and private financing, for creating social, economic and social benefits, promoting gender equality etc. Once a request is deemed eligible and prioritized, the CTCN selects the best expertise among its consortium partners to develop a response plan. The criteria for selection are: Relevant technical expertise, Experience and network in national context, Relevant language capacity, Response Planning track record, Representative use of the consortium partners in Response Planning and Feedback/ preference from the NDE. Based on the discussion with the NDE, NDA and request proponent and feedback from the CTCN, the consortium partner develops the response plan. Once an advanced version is prepared, it is presented to CTCN’s director NDE and NDA for signature. Once the response plan is signed, the Network Partner will be contracted in line with UNEP operational modalities .

6.3 Risks and mitigation measures

Please include a set of identified risks and mitigation actions for each. Please utilize the risk table below that identifies the probability of a given risk occurring and the entity that will manage the risk. Please refer to Part III Section 6.3 of the Readiness Guidebook for further information on how to complete this section.

| Risk category | Specific risk(s) / Risk(s) description | Probability of occurrence (low, medium, high) | Impact level (low, medium, high) | Mitigation action(s) | Entity(ies) responsible to manage the risk(s) |
| --- | --- | --- | --- | --- | --- |
| Operational |  |  |  |  |  |
| Procurement risk: | Delay in implementation of readiness programme | Low | Medium | Project management procedures in place. UNEP/ UNIDO will seek Requests for proposals through a procurement process via the network of the Climate Technology Centre member organizations | UNEP/CTCN |
| Ownership of the results: | True ownership by the government and other national non-state actors are used and up scaled accordingly | Low | High | Set up of a TNA committee comprising national representatives representing key stakeholders to drive the TNA process and ensure country ownership | Network Partner NDA/NDE |
| Engagement risk | Lack of engagement from key stakeholders | Low | Medium | Dissemination strategy and an organizational targeting to enhance primary stakeholders attend TNA related events. Local consultants with local language skills and with knowledge of the local conditions (security, culture and social orientation) are critical. | Network Partner NDA/NDE |
| Financial | Money laundering and terrorist financing; Opportunities for money laundering, terrorist financing, or other prohibited practices | Low | Medium | Implementation of this proposal will be in line with UN regulation and rules. The contractual agreement with the Network Partner will oblige the Network Partner to comply with the principles of the Anti-Fraud and Anti-Corruption Framework of the United Nations Secretariat, as well as the Green Climate Fund Policy on Prohibited Practices. | UNEP/CTCN |
| Operational | Conflicts/ natural disasters/ Epidemics | Low | High | Adopting alternative working modalities, including a focus on virtual meetings, to ensure project continuity in a safe and suitable manner | Network Partner CTCN/UNEP |
| Gender Risk: | Resistance against or lack of interest in, the project activities from stakeholders, especially with regard to the active promotion of gender equality. Low participation rates of suitable female candidates due to lack of interest, inadequate project activity or missing qualified female population within the i.e. engineering sector. | Low | Medium | This Project will pursue thorough and gender responsive integration and ensure stakeholder involvement at all levels (especially in the establishment of the TNA Committee and targeting of stakeholder groups), with special regard to involving women and men.This will be done as per the GCF ESS policy. | Network Partner CTCN/UNEP NDE/NDA TNA committee |

6.4 Monitoring

Upon UNEP-CTCN contracting the Network partner, for execution of this proposal, the Network Partner will produce a detailed work plan and a monitoring and evaluation plan for the technical assistance. The monitoring and evaluation plan must include specific, measurable, achievable, relevant, and time-bound indicators that will be used to monitor and evaluate the timeliness and appropriateness of the implementation. The CTCN Technology Manager responsible for the technical assistance will monitor the timeliness and appropriateness of the work Plan and the M&E plan for implementation. Upon completion of all activities and outputs, evaluation forms will be completed by the (i) NDE about overall satisfaction level with the technical assistance service provided; (ii) the Lead Implementer about the knowledge and learning gained through delivery of technical assistance; and (iii) the CTCN Director about timeliness and appropriateness of the delivery of the activities and outputs. UNEP will submit semi-annual progress reports to GCF in line with the reporting requirements in the Framework Readiness and Preparatory Support Grant Agreement between UNEP and GCF.

6.5 Other Relevant Information

The CTCN (hosted by UNEP-UNIDO) is providing technical assistance to the Government of Sierra Leone, as per its COP Mandate, and supporting country to develop this readiness proposal. The CTCN has established close co-operation between the NDA and NDE to develop this readiness proposal. The implementing partner will be procured through formal tendering procedures if the Readiness proposal is approved for implementation. The relevant COP decisions are provided below for easy reference: (Decision 14/CP.22: Linkages between the Technology Mechanism and the Financial Mechanism of the Convention) Para 4. Welcomes the increased engagement between the Green Climate Fund and the Climate Technology Centre and Network, particularly with respect to utilizing the Readiness and Preparatory Support Programme and the Project Preparation Facility of the fund, noting the potential of such engagement in supporting developing country Parties to build their capacity for implementing technology projects and programmes; Para 6. Invites Green Climate Fund national designated authorities and focal points to use the support available to them under the Readiness and Preparatory Support Programme to, inter alia, conduct technology needs assessments and develop technology action plans. Para 7. Also invites developing country Parties to develop and submit technology-related projects, including those resulting from technology needs assessments and from the technical assistance of the Climate Technology Centre and Network, to the operating entities of the Financial Mechanism for implementation, in accordance with their respective policies and processes; (Decision 15/CP.22: Enhancing climate technology development and transfer through the Technology Mechanism) Para 13. Underlines the importance of well-functioning and strengthened collaboration between the national designated authorities for the Green Climate Fund, the focal points for the Global Environment Facility and the national designated entities for technology development and transfer Para 15. Welcomes the increased engagement between the Green Climate Fund and the Climate Technology Centre and Network, particularly with respect to utilizing the Readiness and Preparatory Support Programme and the Project Preparation Facility of the fund in order to respond to country-driven requests for technical assistance; Para 16. Encourages the advancement of the engagement referred to in paragraph 15 above, including through the strengthening of collaboration between national designated authorities for the Green Climate Fund and national designated entities for technology development and transfer; Para 17. Invites the Climate Technology Centre and Network to include the outcomes of the engagement referred to in paragraphs 15 and 16 above in its annual report to the Conference of the Parties at its twenty-third session.” This readiness proposal is as a result of discussions between Sierra Leone NDA (The Environmental Protection Agency- EPA) and the CTCN focal point the NDE. This resulted to submission of a technical assistance to CTCN to support the country to conduct its sectoral TNA though the request was submitted to CTCN the NDA endorsed the use of the readiness fund for the execution of this request through UNEP (which host the CTCN) as the delivery partner. The proposal provides a detailed collaboration mechanism between the NDA and the NDE in the execution of the proposal which will includes their collaboration in establishment of a TNA committee that will oversee the TNA process. The committee will ensure effective engagement of the country stakeholders to ensure country ownership of the process. Among the output for this proposal is development of concept notes that would ensure implementation of the Technology Action plan, the CN thus create quality potential project pipeline that can be further developed into proposal for GCF financing. The proposal recognizes the important role of the private sector in advance climate action in the country. The proposal has included a component for capacity building to private sector that would enhances their capacity and knowledge to engage in climate change. This is expected to enhance sustainability of this work. To avoid any possible conflicts of interest deriving from the delivery partner’s role as an accredited entity, the prioritization of investments and projects in the context of this readiness grant, will be made through a broad consultation process with relevant stakeholders, including other potential implementing entities. The final validation of these priorities will be carried out through the countries’ own relevant coordination mechanism and institutional arrangements, with the participation of other government agencies, as well as representatives from civil society and private sector as the NDA deems relevant, to ensure chosen priorities are fully aligned with national plans and strategies and adequately includes inputs from consulted stakeholders.

Please briefly elaborate on current baselines on which the proposed activities can be built on, processes that are in place that the current Readiness proposal can strengthen, or any gaps that the proposed activities would fill in. If more space is needed, please elaborate this in Section 4.

Please include tangible and specific deliverables for each activity proposed, please note that during implementation all deliverables should be included within the implementation reports for GCF consideration.

For second disbursement, audited financial report and audited expenditure statement are only required for readiness and preparatory support proposals expected to last over 12 months.