## Guidelines
This file contains three specific planning tools to complete the supplementary information required when submitting a proposal for Readiness Programme support (including for NAP/adaptation planning):
- Budget plan and accompany Budget notes - Procurement plan - Implementation plan
The following considerations are important when completing the budget:
1. Before preparing the Readiness and budget, procurement, and implementation plans, please read the full guidance contained in the Readiness Programme Guidebook, specifically Part III Section 5
2. You can select the appropriate budget categories from the dropdown list in the budget plan:
3. To insert additional rows, right click on the row number below where you wish to insert the new row and choose INSERT.
4. Additional budget categories may be added by manually typing them on the Budget Category sheet. :
5. The Budget Notes sheet should be used to record explanations, further details or cost breakdowns for individual lines
Project Management Cost:
Project management costs (PMC) are the direct administrative costs incurred to execute a project. They should cover only incremental costs incurred due to the GCF contribution. In most cases, these costs are directly related to the support of a dedicated project management unit which manages the day to day execution related activities of the project.
General Principles for PMC costs:
1. The percentage of PMC financed by GCF should not be more than the percentage share of the overall budget financed by GCF
2. PMC budget thresholds: Up to 7.5 per cent of total activity budget.
> PMC exceeding 7.5 per cent for the readiness (including NAPs) proposals, and PPF proposals, up to $ 3 million will require detailed documentation
and justification supporting the entire PMC budget.
> The PMC should be shown as a separate component in the project budget. A detailed breakdown of PMC should be provided by budget category.
> Indicative list of eligible project management costs:
> Project staffing and consultants: Project manager, Project Assistant, Procurement personnel, Finance personnel & Support/admin. Personnel
> Other direct costs: Office equipment, Mission related travel cost of the PMU, Project management systems and information technology,
Office supplies, Audit cost
Contingency :
1. Select the appropriate % of Contingency Budget from the dropdown list :
2. Contingency budget for unforeseen costs arising during the project implementation should not be included in the outcome budget separately.
3. Contingency budget must be used for any unforeseen programme (output level) cost that is unrelated to implementation/service fee.
4. Any use of contingency must be reported to and agreed by the GCF Secretariat in writing in advance provided with justifications that are acceptable to the GCF
5. If by the end of the grant implementation period, you have not spent Contingency, you may not increase the scope of the project or make any other expenditures using the Contingency.
If you are unsure about how to complete the budget template, please send your query to: countries@gcfund.org
Readiness Grant Budget Preparation Guidelines

## Budget Category
Budget Categories
Audio Visual & Printing
Audit Fee
Consultant - Individual - International
Consultant - Individual - Local
Travel - International
Travel – Local
Workshop/Training
Meetings | Indicate additional budget categories
Local travels for participants
Choose percentage
0
1%
2%
3%
4%
5%

## 5.1 Budget Plan
5.1 Budget Plan
Please add rows for Outcomes, Outputs and Cost Categories as required. Additional budget categories may be added by manually typing them on the Budget Category sheet.
Outcomes / Outputs |  | Detailed Budget (in US$) | [5 empty] | Total Budget (per outcome) | Expenditure Plan | [5 empty] | BUDGET NOTE
|  | Budget Categories choose from the drop-down list | Unit | # of Unit | Unit Cost | Total Budget (per budget category) | Total Budget (per sub-outcome) |  | 6m | 12m | 18m | 24m
Outcome 1.3: Relevant country stakeholders (which may include executing entities, civil society organizations and private sector) have established adequate capacity, systems and networks to support the planning, programming and implementation of GCF-funded activities. | Output 1.3.1 Steering Committee established and operationalised. | Consultant - Individual - International | W/Day | 15 | 650 | 9750 | 30550 | 72800 | 317700 | [5 empty] | 1
|  | Consultant - Individual - Local | W/Day | 40 | 250 | 10000 | [8 empty] | 2
|  | Local travels for participants | Trip | 70 | 100 | 7000 | [8 empty] | 3
|  | Meetings | Unit | 6 | 300 | 1800 | [8 empty] | 4
|  | Workshop/Training | Meeting/day | 1 | 2000 | 2000 | [8 empty] | 6
| Output 1.3.2 Stakeholder mapping and Sectoral working groups established and operationalised. | Consultant - Individual - International | W/Day | 5 | 650 | 3250 | 11000 | [7 empty] | 7
|  | Consultant - Individual - Local | W/Day | 25 | 250 | 6250 | [8 empty] | 8
|  | Meetings | Unit | 5 | 300 | 1500 | [8 empty] | 10
| Output 1.3.3 Transfer skills and knowledge to local personnel is completed | Consultant - Individual - International | W/Day | 25 | 650 | 16250 | 31250 | [7 empty] | 11
|  | Consultant - Individual - Local | W/Day | 40 | 250 | 10000 | [8 empty] | 12
|  | Workshop/Training | Meeting/day | 1 | 2000 | 2000 | [8 empty] | 13
|  | Local travels for participants | Trip | 30 | 100 | 3000 | [8 empty] | 15
Outcome 2.2: GCF recipient countries have developed or enhanced strategic frameworks to address policy gaps, improve sectoral expertise, and enhance enabling environments for GCF programming in low-emission investment | Output 2.2.1 Assessment of institutional, policy and regulatory gaps for investments in renewable IPPs developed and validated | Consultant - Individual - International | W/Day | 96 | 650 | 62400 | 104400 | 244900 | [6 empty] | 16
|  | Consultant - Individual - Local | W/Day | 100 | 250 | 25000 | [8 empty] | 17
|  | Travel - International | Trip | 2 | 2500 | 5000 | [8 empty] | 18
|  | Local travels for participants | Trip | 10 | 100 | 1000 | [8 empty] | 19
|  | Workshop/Training | Meeting/day | 1 | 2000 | 2000 | [8 empty] | 20
|  | Meetings | Unit | 30 | 300 | 9000 | [8 empty] | 21
| Output 2.2.2 A de-risking mechanism is validated | Consultant - Individual - International | W/Day | 50 | 650 | 32500 | 54000 | [7 empty] | 22
|  | Consultant - Individual - Local | W/Day | 50 | 250 | 12500 | [8 empty] | 23
|  | Travel - International | Trip | 2 | 2500 | 5000 | [8 empty] | 24
|  | Local travels for participants | Trip | 20 | 100 | 2000 | [8 empty] | 25
|  | Workshop/Training | Meeting/day | 1 | 2000 | 2000 | [8 empty] | 26
| Output 2.2.3 Investment framework for renewables IPP programme, and a roadmap to create an enabling environment for the creation of a IPP market for renewable energy in Liberia developed and validated by the Steering Committee and by the technical working group. | Consultant - Individual - International | W/Day | 70 | 650 | 45500 | 86500 | [7 empty] | 27
|  | Consultant - Individual - Local | W/Day | 100 | 250 | 25000 | [8 empty] | 28
|  | Travel - International | Trip | 2 | 2500 | 5000 | [8 empty] | 29
|  | Local travels for participants | Trip | 30 | 100 | 3000 | [8 empty] | 30
|  | Workshop/Training | Workshop | 4 | 2000 | 8000 | [8 empty] | 31
Outcome 4.3 An increase in the number of quality project concept notes developed and submitted that target SIDS, LDCs and African states | Output 4.3.1 Financial model for the 100 MW Renewable Energy IPPs programme established, financing arrangements and terms developed and validated. | Consultant - Individual - International | W/Day | 65 | 650 | 42250 | 83750 | 189550 | 131150 | [5 empty] | 32
|  | Consultant - Individual - Local | W/Day | 100 | 250 | 25000 | [8 empty] | 33
|  | Travel - International | Trip | 3 | 2500 | 7500 | [8 empty] | 34
|  | Local travels for participants | Trip | 30 | 100 | 3000 | [8 empty] | 35
|  | Workshop/Training | Workshop | 3 | 2000 | 6000 | [8 empty] | 36
| Output 4.3.2 Environmental and social impact assessment study completed and management plan developed | Consultant - Individual - International | W/Day | 56 | 650 | 36400 | 47400 | [7 empty] | 37
|  | Consultant - Individual - Local | W/Day | 30 | 250 | 7500 | [8 empty] | 38
|  | Travel – Local | Trip | 10 | 100 | 1000 | [8 empty] | 39
|  | Travel - International | Trip | 1 | 2500 | 2500 | [8 empty] | 40
| Output 4.3.3 Project Concept Note for the 100 MW renewable IPP programme for Liberia developed, validated and submitted to GCF. | Consultant - Individual - International | W/Day | 18 | 650 | 11700 | 27200 |  |  |  | 27200 |  |  |  | 41
|  | Consultant - Individual - Local | W/Day | 40 | 250 | 10000 | [8 empty] | 42
|  | Travel - International | Trip | 1 | 2500 | 2500 | [8 empty] | 43
|  | Local travels for participants | Trip | 10 | 100 | 1000 | [8 empty] | 45
|  | Workshop/Training | Workshop | 1 | 2000 | 2000 | [8 empty] | 46
| Output 4.3.4 Engagement plan to empower leaders or other influential members designed | Consultant - Individual - International | W/Day | 18 | 650 | 11700 | 31200 |  |  | 31200 |  |  |  |  | 47
|  | Consultant - Individual - Local | W/Day | 40 | 250 | 10000 | [8 empty] | 48
|  | Workshop/Training | Workshop | 1 | 2000 | 2000 | [8 empty] | 49
|  | Local travels for participants | Trip | 50 | 100 | 5000 | [8 empty] | 51
|  | Travel - International | Trip | 1 | 2500 | 2500 | [8 empty] | 52
Total Outcome Budget | [7 empty] | 507250 | 448850 | 31200 | 27200 | 0 | 0 | 0
Project Management Cost (PMC) Up to 7.5% of Total Activity Budget |  | Travel - International | Trip | 1 | 1500 | 1500 | Actual amount and % of PMC requested: | Maximum PMC that can be requested: | [6 empty] | 53
|  | Audit Fee | Lumpsum | 1 | 2500 | 2500 | [8 empty] | 54
|  | Consultant - Individual - International | W/Day | 52 | 650 | 33800 | do not change the formula | do not change the formula | [6 empty] | 55
[6 empty] | 0 | 37800 | 38043.75
[6 empty] | 0 | 7.452% | 7.5%
FOR GREEN CLIMATE FUND SECRETARIAT'S USE ONLY
Breakdown (per budget category) |  | Total (per budget category)
Audio Visual & Printing |  | 0
Audit Fee |  | 2500 |  |  |  | FOR GREEN CLIMATE FUND SECRETARIAT'S USE ONLY
Consultant - Individual - International |  | 305500
Consultant - Individual - Local |  | 141250 |  |  |  | Total Outcome Budget | [6 empty] | 507250
#REF! |  | 0 |  |  |  | Project Management Cost (PMC) |  | 7.452% | requested |  |  |  | 37800
#REF! |  | 0 |  |  |  | Contingency | 2% |  | requested |  |  |  | 10145
#REF! |  | 0
Travel - International |  | 31500
Travel – Local |  | 1000 |  |  |  | Sub-Total (Total Outcome Budget + Contingency + PMC) | [6 empty] | 555195
Workshop/Training |  | 26000
Meetings |  | 12300 |  |  |  | Delivery Partner Fee (DP) - Up to 8.5% of the Sub-Total | [6 empty] | 47191.575
Local travels for participants |  | 25000
0 |  | 0
0 |  | 0 |  |  |  | Total Project Budget (Total Activity Budget + Contingency + PMC + DP) | [5 empty] | 602387
0 |  | 0
Total Outcome Budget + PMC |  | 545050
0

## Budget Notes
Budget Note | Detailed Description
1 | Working days of an International consultant (I1) at 650 USD / day -
2 | Working days of a local consultant at 250 USD / day (N1, N2, N3)
3 | The Steering Committee workplan should include at least quartely meetings which equals to 6 meetings in 18 months, including the inception workshop (first meeting)planned in Activity 1.3.1b. Thus a total of 6 meetings. The Steering Committee will be composed by a maximum of 10 persons. Each travel is estimated at 100 USD/person/event as the Steering Committee Member could be travelling from outside of the state capital.
4 | Steering Commitee meetings - 6 meetings arre expected (Activity 1.3.1.c ) estimated at 300 USD/meeting. The Steering Committee will be composed by a maximum of 10 persons.
6 | Inception workshop in presence of the Steering Commitee (max 10persons) is organized, all cost included (cost of facility, refreshments, stationary, PA system etc.).
7 | Working day of an International consultant at 650 USD / day (I1)
8 | Working days of a local consultant at 250 USD / day (N1, N2, N3)
10 | 5 meetings with the technical working group are planned to discuss the activities 2.2.2, 2.2.3 and 4.3.1. Each meeting will be attended by the 4 sectoral working groups, each composed by a maximum of 5 members (thus a maximum participation of 20 persons).
11 | Working day of an International consultant at 650 USD / day (I1)
12 | Working days of a local consultant at 250 USD / day (N1, N2, N3)
13 | One capacity building workshop organized to familiarize stakeholders with the readiness proposal process. This capacity building workshop will be organized with the technical working groups (up to 20 persons) as well as the Steering Committee ( up to 10 persons). All cost are included (cost of facility, refreshments, stationary, PA system etc.).
15 | This workshop will be held in presence of the Steering Committee (8 to 10 persons) and the 4 sectoral working groups (3-5 experts each), thus a maximum participation of 30 persons is expected. The local travel for participants considered a budget of 100 USD / person / day to enable the participants to travel to the workshop. (inter city transport and local expenses)
16 | Working day of an International consultant at 650 USD / day (I1, I2, I3, I4)
17 | Working days of a local consultant at 250 USD / day (N1, N2)
18 | International trip for 2 experts including 5 working days in the country, accomodation and flight
19 | Participation of the Steering Committee (up to 10 persons) to the workshop at 100 USD / each to enable them to travel to the meeting. (inter city transport and local expenses)
20 | Consultative workshop as part as 2.2.1b in presence of the Steering Committee (8 to 10 persosn)
21 | 30 bilateral or virtual meetings held in relation to Activity 2.2.1.
22 | Working day of an International consultant at 650 USD / day (I1, I2, I3, I4, I5)
23 | Working days of a local consultant at 250 USD / day (N1, N2, N4, N5)
24 | International trip for 2 experts including 5 working days in the country, accomodation and flight
25 | 20 participants travelling for the workhop at 100 UDS/ person (inter city transport and local expenses)
26 | 1 workshop to validate the de-risking mechanisms in presence of the technical working group (max 20 persons)
27 | Working day of an International consultant at 650 USD / day (I1, I2, I3, I4, I5)
28 | Working days of a local consultant at 250 USD / day (N1, N2, N4)
29 | 2 international experts travelling for the workshop planned in activity 2.2.3c
30 | Steering Committee and the technical working group participating to the workshop (up to 30 persons) at 100 USD/each (inter city transport and local expenses)
31 | 4 days workshops for activity 2.2.3c at 2000 USD each day all cost included (cost of facility, refreshments, stationary, PA system etc.). Up to 30 persons expected (Steering Commitee and the Technical working group).
32 | Working day of an International consultant at 650 USD / day (I5)
33 | Working days of a local consultant at 250 USD / day (N3)
34 | 2 international experts travelling for the workshop planned in activity 4.3.1b + 1 expert travelling for 4.3.1c (I1, I5)
35 | Steering Committee and the technical working group participating to the workshop (up to 30 persons) at 100 USD/each
36 | 1 day of workshop with Steering Commitee, and 1 day of workshop with the technical working group (up to 20 persons ) and one day of workshop with the private sector (up to 20 participants) for activity 4.3.1b at 2000 USD each day all cost included (cost of facility, refreshments, stationary, PA system etc.)
37 | Working day of an International consultant at 650 USD / day (I1, I2)
38 | Working days of a local consultant at 250 USD / day (N3, N4)
39 | 10 trips from the local consultant to travel away from the capital (in possible areas where the 10MW could be deployed). The cost is fixed to 100 USD / trip as a driver might be requested and no public transportation will be available.
40 | 1 international experts travelling for the workshop planned in activity 4.3.2 (I2)
41 | Working day of an International consultant at 650 USD / day (I5, I3)
42 | Working days of a local consultant at 250 USD / day (N3, N5)
43 | 1 international experts travelling for the workshop planned in activity 4.3.3 (I5)
45 | The Steering Committee (between 8 to 10 persons) will be participating to the workshop planned for activity 4.3.3. 100 USD/participants has been budgeted. (inter city transport and local expenses)
46 | 1 day of workshop for activity 4.3.3 in presence of the Steering Committee ( up to 10 persons) is organized at 2000 USD each day all cost included (cost of facility, refreshments, stationary, PA system etc.)
47 | Working day of an International consultant at 650 USD / day (I1)
48 | Working days of a local consultant at 250 USD / day (N1, N2, N3, N5)
49 | 1 capacity building workshop is organized for the private sector stakeholder representatives - up to 50 persons expected at 2000 USD each day all cost included (cost of facility, refreshments, stationary, PA system etc.)
51 | 50 persons attending the meeting to empower local leaders. 100 USD to pay for the transportation (inter city transport and local expenses)
52 | 1 international experts travelling for the workshop planned in activity 4.3.4 (I1)
53 | One travel requirement from the PMC consultant of the CTCN to supervise the implementation of the project. One travel is required either at the beginning or the end of the mission.
54 | Audit fee for the network member
55 | PMC Consultant in charge of ensuring coordination and project management by CTCN.
Local/ National Expert | Area of Expertise
N1 | Solar PV Grid Connected
N2 | Small Hydro Expert
N3 | Socio Economic Specialist
N4 | Gender Specialist
N5 | Communications Expert
I1 | Solar PV Grid Connected
I2 | Small Hydro Expert
I3 | Energy Engineer
I4 | Power Plant Expert
I5 | Finance Expert
PMC Consultant | CTCN PMC Consultant in charge of the coordination and project management of the project by the CTCN

## 5.2 Procurement Plan
5.2 Procurement Plan
For goods, services, and consultancies to be procured, please list the items, descriptions in relation to the activities in Section 3, estimated cost, procurement method, relevant threshold, and the estimated dates. Please include the procurement plan for at least the first tranche of disbursement requested below and provide a full procurement plan for the entire duration of the implementation period if available at this stage.
Item | Item Description | Estimated Cost (US$) | Procurement Method | Thresholds (Min-Max monetary value for which indicated procurement method must be used) | Estimated Start Date | Projected Contracting Date
Goods and Non-Consulting Services
Sub-Total (US$) |  | 0
Consultancy Services
Contract of services to implement the technical assistance/readiness support | Develop a renewables IPP framework for Liberia and conceptualise a funding proposal to GCF increase the share of renewable electricity technologies to achieve NDC commitments | 509750 | Follows CTCN prodecures* see below | Follows CTCN prodecures* see below | Within 1 month of approval | 9 months of approval
Sub-Total (US$) |  | 509750
Estimated cost equivalent to total outcome budget + contingency + audit fee
Overall financial management and procurement of goods and services under this readiness and preparatory support proposal will be guided by UN regulations, rules, policies and procedures.
UNEP will be responsible for the implementation of the readiness activities and for procurement and contractual services, as well as reporting on the progress of this implementation in close coordination and strategic guidance from the NDA/FP. The procurement actions and the operational services will be carried forward in accordance with UN policies and procurement guidelines.
CTCN Procedures | CTCN procedure for procurement: For a request that is eligible and prioritized, the Climate Technology Managers in charge of the respective request sources the appropriate expertise to develop the Terms of Reference of the assistance (called ‘Response Plan’ as per CTCN procedures). The response plan provides specific information on the technical assistance to be delivered, including activities, outputs, expected outcomes and impacts, timeline, indicators or measuring assistance progress and success, stakeholders to be involved, etc. The response plan, once finalized, is signed by the national focal point of the CTCN in the concerned country (National Designated Entity), the institution which originated the CTCN request for technical assistance and the CTCN Director and constitutes the basis of the assistance to be implemented and monitored upon the approval and in cooperation with the NDA. Once the response plan is signed, the contracting of the implementer starts.
Overall financial management and procurement of goods and services under this readiness and preparatory support proposal will be guided by UN regulations, rules, policies and procedures.
UNEP will be responsible for the implementation of the readiness activities and for procurement and contractual services, as well as reporting on the progress of this implementation in close coordination and strategic guidance from the NDA/FP. The procurement actions and the operational services will be carried forward in accordance with UN policies and procurement guidelines.
CTCN procedure for procurement: For a request that is eligible and prioritized, the Climate Technology Managers in charge of the respective request sources the appropriate expertise to develop the Terms of Reference of the assistance (called ‘Response Plan’ as per CTCN procedures). The response plan provides specific information on the technical assistance to be delivered, including activities, outputs, expected outcomes and impacts, timeline, indicators or measuring assistance progress and success, stakeholders to be involved, etc. The response plan, once finalized, is signed by the national focal point of the CTCN in the concerned country (National Designated Entity), the institution which originated the CTCN request for technical assistance and the CTCN Director and constitutes the basis of the assistance to be implemented and monitored upon the approval and in cooperation with the NDA. Based on the needs and expertise required in the response plan, a CTCN Network Member will be selected to implement it.
The selection of the institution from the Network of CTCN for the execution of the technical assistance is conducted through a competitive procurement process as per UN Rules and Regulations, in line with CTCN procedures and with UN Rules and Regulations. The CTCN nurtures a Network of more than 550 expert organizations in the field of low-carbon and climate resilient technologies. The required expertise to carry out the activities that define this intervention will be sourced from the Network. For this, the following four principles shall be given due consideration when undertaking the procurement functions of UNEP:
i. Best value for money principle;
ii. Fairness, accountability, integrity and transparency of the procurement process;
iii. Effective competition;
iv. The best interest of the UNEP.

## 5.3 Implementation Plan
5.3 Implementation Plan
Please list all the deliverables (e.g. D.1.1.1a) per activity (e.g. A1.1.1) with the identifierand mark the planned duration as show in the example. Please also indicate milestones for any deliverables to be completed during the implementation period of the activity in question.
Make sure the identifier number of each activity and deliverable matches with the proposal as this table does not require its name or description. Please refrain from adding descriptions.
For more guidance on how to fill out this tables, please see Part III Section 5 of the Readiness Guidebook
|  |  |  | Planned duration | [6 empty] | Milestone (deliverable) | [7 empty] | Target completion date
Activities & Deliverables |  |  | Estimated Timeline
|  | M1 to M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36 | M37 | M38 | M39 | M40 | M41 | M42
A1.3.1 | D1.3.1a (i); (ii) | bar: Estimated Timeline M7 to Estimated Timeline M9
D1.3.1b (i); (ii) | bar: Estimated Timeline M9
D1.3.1c (i); (ii) | bar: Estimated Timeline M9
A1.3.2 | D1.3.2a (i); (ii); | bar: Estimated Timeline M7 to Estimated Timeline M9
D1.3.2b (i); (ii) | bar: Estimated Timeline M12; Estimated Timeline M15; Estimated Timeline M18; Estimated Timeline M21; Estimated Timeline M24
A1.3.3 | D1.3.3 (i); (ii) | bar: Estimated Timeline M7 to Estimated Timeline M9
A2.2.1 | D2.2.1a (i); (ii) | bar: Estimated Timeline M8 to Estimated Timeline M11
D2.2.1b (i); (ii); (iii) | bar: Estimated Timeline M11 to Estimated Timeline M12
A2.2.2 | D2.2.2 a(i) | bar: Estimated Timeline M11 to Estimated Timeline M12
D2.2.2 b(i); (ii) | bar: Estimated Timeline M11 to Estimated Timeline M12
A2.2.3 | D2.2.3a (i) | bar: Estimated Timeline M13 to Estimated Timeline M15
D2.2.3b (i) | bar: Estimated Timeline M13 to Estimated Timeline M15
D2.2.3c (i); (ii); (iii) | bar: Estimated Timeline M15 to Estimated Timeline M16
A4.3.1 | D4.3.1 a (i) | bar: Estimated Timeline M18 to Estimated Timeline M23
D.4.3.1b (i); (ii) | bar: Estimated Timeline M18 to Estimated Timeline M23
D.4.3.1c (i); (ii) | bar: Estimated Timeline M18 to Estimated Timeline M23
A4.3.2 | D4.3.2 (i) | bar: Estimated Timeline M20 to Estimated Timeline M21
A4.3.3 | D4.3.3 (i); (ii); (iii) | bar: Estimated Timeline M20 to Estimated Timeline M30
A4.3.4 | D4.3.4a (i); (ii) | bar: Estimated Timeline M21 to Estimated Timeline M23
D4.3.4b (i); (ii) | bar: Estimated Timeline M23