Grant Agreement Number (GNQ-RS-003)

Mr. Gabriel Ngua Ayecaba / UNIDO

Sections in this report:

- Section 1: General Information

- Section 2: Reporting on Country Readiness Logical Framework

- Section 3: Actual Implementation Timetable

- Section 4: Expenditure Reporting

- Section 5: Procurement

- Annex: Final Disbursement Request Form

For more information, please refer to the GCF Readiness and Preparatory Support Programme guidebook available online. Please submit the Completion Report to opm@gcfund.org.

Project completion report should be prepared and signed by Delivery Partner (DP) and/or National Designated Authority (NDA).

| Name and Title (DP): Mr. Ciyong Zou Position: Managing Director, Directorate of Programmes, Partnerships and Field Coordination, UNIDO | Signature: | Date: |
| --- | --- | --- |
| Name and Title (NDA): Mr. Gabriel Ngua Ayecaba Position: Director-General, Department of Environment, Ministry of Fisheries and Environment | Signature: | Date: |

| FOR GREEN CLIMATE FUND’S SECRETARIAT USE ONLY |  |  |
| --- | --- | --- |
| Received by: | Signature | Date (DD-MM-YYYY) |

EXECUTIVE SUMMARY

The Readiness and Preparatory Support proposal was approved on 30 December 2019 and the notification of approval was sent on 10 January 2020. The first disbursement of USD 261,397 was received on 19 June 2020. The Climate Technology Centre and Network (CTCN) awarded the contract of this assignment through UNIDO to a consortium of members of the CTCN network. The implementation of this project started on 1 October 2020, with OIKO as the project executing entity (PEE), in partnership with INCOMA (the local counterpart), and the implementation was completed in October 2022. Due to COVID19 mobility restrictions and other difficulties, implementation of many activities has proven to be more time-consuming than previously envisaged. Activities affected by COVID19 restrictions included: Activity 1.2, Activity 1.3, Activity 1.4, Activity 2.1. Moreover, implementation started on October 2021, and considering the Grant Expiration Date is January 2022, only 16 months were available for the implementation of the project. As a result, a 9-month extension has been requested to the GCF, and consequently approved, in order to ensure the full implementation of the project and its corresponding activities. Activities conducted and outcomes achieved during the project implementation: Outcome 1: Institutional capacity and coordination mechanism in place to govern and coordinate climate action and finance Output 1.1: Effective coordination mechanism between NDA and National Designated Entity (NDE) for the UNFCCC Technology Mechanism and other climate finance focal points Activities 1.1 · 1.2. · 1.3. · 1.4: Institutionalization of a coordination mechanism for the implementation of the TNA Outcome 2: Country Programming process Output 2.1: Technology solutions identified and prioritized in accordance with national strategies and plans Activities 2.1 · 2.2. · 2.3: Prioritization of technologies and relevant action for increased access to finance Output 2.2.: Stakeholder engagement consultative processes Activity 2.4: National Consultation workshop to ensure national ownership and technology deployment Activity 2.5: Support the implementation of the Technology Action Plan with communications, guidance and training Outcome 3: Climate finance strategies strengthened, private sector mobilized, and project pipeline enhanced Outcome 3.1: Private sector engagement Activity 3.1: Enhancing SME capacity and enabling environment through innovative new business identification training programme Key deliverables of the Technology Needs Assessment and Technology Action Plan phases: - Final Mitigation and Adaptation Report (D2.2) - Report and executive summary of each Technology Action Plan for each of the priority technologies in compliance with the TNA (D2.3)

| SECTION 1: GENERAL INFORMATION This section provides information on completing the General Information of the Readiness Support Completion Report template. |  |
| --- | --- |
| - Country | Equatorial Guinea |
| - Grant agreement number | GNQ-RS-003 |
| - Date of grant agreement signed | 03/12/18 |
| - Grant effectiveness date | 10/01/20 |
| - Date of 1st disbursement received from GCF | 19/06/20 |
| - Project completion date | 30/10/22 |
| - Planned/Actual date of financial completion | Planned: 30/10/22 / Actual: Click or tap to enter a date. |
| - Planned/Actual project duration | Planned project duration: 16 months / Actual project duration: 25 months |
| - Total approved grant amount | USD 226,440 |
| - Disbursement from GCF made to date to Delivery Partner or NDA | USD 170,740 |
| - Final disbursements from GCF to Delivery Partner or NDA to be requested (if any) | USD 55,700 |
| - Final Unspent Balance Refund from Delivery Partner or NDA to GCF (if any) | N/A |

SECTION 2: REPORTING ON COUNTRY READINESS LOGICAL FRAMEWORK This section requires an overview of key achievements and deliverables in implementing the Readiness Support activities. Any key deliverables to the agreed outputs should be submitted with the project completion report.

| Outcome 1: Country capacity strengthened |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome narrative: Activity 1.1., Activity 1.2, Activity 1.3. and Activity 1.4. have been completed. A coordination mechanism has been established, focal points have been identified, more stakeholders have been identified, and meetings are conducted regularly. The TNA committee has been established; two capacity-building workshops have been conducted. |  |  |  |  |  |  |  |  |
| Outputs | Activities | Post-completion targets achieved | Progress against baseline | Indicators | Milestones and deliverables achieved | Variance explanation | Qualitative assessment of activities undertaken | Lessons learned and best practices |
| 1.1 NDA/focal point lead effective coordination mechanism | . Activity 1: Institutionalization of a coordination mechanism for the implementation of the TNA. Activity 1.1 Development of planning and communication documents Activity 1.2. Conduct stakeholder’s analysis Activity 1.3 Support the establishment of a TNA Committee Activity 1.4: Development and endorsement of TNA Committee work plan for monitoring and oversight | 2. NDA/focal point leads an effective coordination mechanism, allowing for an overview of all operational sectors and meets regularly | Communication achieved between NDA, NDE and other climate finance focal Points. Stakeholder analysis conducted. TNA committee in place. TNA Work plan developed. Closure report delivered. | Activity 1.1: 1 Consolidated project work plan 1 Monitoring and evaluation plan 1 Impact Description Closure and Data Collection report Activity 1.2 - 1 Stakeholder mapping report Activity 1.3 - 1 Official government circular establishing the national TNA committee. - 1 TNA Constitution document informing on the work of the TNA Committee. 1 report of the training conducted. Activity 1.4 - 1 TNA Committee work plan - 1 Committee’s meeting report for each meeting held | Deliverable 1.1. - 1 Consolidated project work plan - 1 Monitoring and evaluation plan - 1 Impact Description - 1 Impact Description - Closure and Data Collection Report - National and international Team has been established Deliverable 1.2. -Stakeholder mapping report, where roles and responsibilities are specified. Final report submitted and approved in January 2021. - Signed letter by the CTCN for presentation to the project of the various ministries. Deliverable 1.3: - Official government circular establishing the national TNA committee. - TNA Constitution document informing on the work of the TNA Committee. - A full list of participants, photo documentations and a report of the training conducted. Deliverable 1.4. - TNA Committee work plan - 5th Committee Meeting Report - 6th Committee Meeting Report |  | Knowledge on the TNA has been increased in the country, especially by the key stakeholders in the government. The establishment of the TNA Committee has given more support to the project activities, as key stakeholders are becoming more familiar with the TNA process, and the sense of continuation of the project is greater. | Travel restriction for field missions and stakeholder engagement between 2020/2021, combined with communication barriers experienced due to lack of reliable internet connection. It is recommended to conduct skype calls that the local counterparts receive as usual call and the use of WhatsApp for voice messages, so the local team can respond when available and possible. |

3

| Outcome 2: Country Programme Established |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome narrative: Activities 2.1., 2.2, 2.3, 2.4 and 2.5. have been completed. Technologies have been prioritized and Technology Actions Plans have been developed. One Action Plan has been chosen for a Concept Note, after the approval from the NDE. |  |  |  |  |  |  |  |  |
| Outputs | Activities | Post-completion targets achieved | Progress against baseline | Indicators | Milestones and deliverables achieved | Variance explanation | Qualitative assessment of activities undertaken | Lessons learned and best practices |
| 2. 1 Technology solutions identified and prioritized in accordance with national strategies and plans. | Activity 2: Prioritization of technologies and relevant action for increased access to finance Activity 2.1: Pre-selection of sub-sectors for the fulfilment of Equatorial Guinea’s TNA Activity 2.2: Assess, prioritize and validate key technologies for the fulfillment of Equatorial Guinea’s TNA Activity 2.3: Development of Technology Action Plan(s) per sector and /or sub (sector). | Technology solutions identified and prioritized | GCF CP is developed, and appropriate climate technologies have been identified and prioritized. | Activity 2.1 - 1 Report on TNA-TAP on alignment with CP and national plans - 1 Report on analysis of sectoral priorities expressed in national documents. - 1 Report describing the methodology utilized for sector and subsector selection and prioritization. - 1 Meetings minutes. Deliverable 2.2 - 1 Technology fact sheet for each selected technology - 1 Set of criteria for MCA exercise - 1 Workshop report including a full list of participants, photo documentations for each one of the 4 workshops held - 1 Database in most suitable format - 2 Final Reports including a mitigation TNA report and an adaptation TNA report Deliverables 2.3 - Report and executive summary of each TAP for each of the priority technologies in compliance with the TNA. | Deliverable 2.1: -1 Report on TNA-TAP on alignment with CP and national plans - Report on analysis of 1 sectoral priorities expressed in national documents. - 1 Report describing the methodology utilized for sector and subsector selection and prioritization. - Meetings minutes (7). - 2 Workshops report including a full list of participants with photo documentations: 1st Committee Meeting Report (Workshop 1) & 2nd Committee Meeting Report (Workshop 2) Deliverable 2.2 - 1 Technology fact sheet for each selected technology (Final Version) - 1 Set of criteria for MCA exercise (Final Version) - 1 Database in most suitable format (Updated) - 1 Workshop report including a full list of participants, photo documentations for each one of the 4 workshops held (Final Version) - 2 Final Reports including a mitigation TNA report and an adaptation TNA report Deliverables 2.3 - 1 Report and executive summary of each TAP for each of the priority technologies in compliance with the TNA |  | Weekly meetings have given the NDA and the local counterpart a sense of continuance and of ownership of the project. Some stakeholders other than government officials are engaged, and the TNA Committee is getting involved in the development and the validation of project activities. | The sectorial workshops held for each prioritized sector has been key in order to receive feedback from local stakeholders, finish Technology Fiches and draft Final Mitigation and Adaptation reports. Finally, the sectorial workshops were held in April 2022, due to the project delays caused by the COVID 19-crisis in the beginning of the project. |
| 2.2 Stakeholders engaged in consultative processes | Activity 2.4: National Consultation workshop to ensure national ownership and technology deployment Activity 2.5: Support the implementation of the Technology Action Plan with communications, guidance and training | 2. Stakeholders engaged in consultative processes (governments, private sector, associations, civil society, academia and others) | Formal consultation process has been established for climate technology identification process. | Activity 2.4 Deliverable 2.4 - 1 Workshop report including a full list of participants and photo documentations. - 1 Concept note of a TAP - 1 Terms of reference to be shared with GCF, training material and tools. Deliverable 2.5 - 1 Policy brief and market-use cases for each of the selected technologies - 1 Dissemination Strategy - 1 set of training materials for the regional workshops - 1 Workshop report for each workshop held including a full list of participants and photo documentation. | Activity 2.4 Deliverable 2.4 - 1 Workshop report including a full list of participants and photo documentations. - 1 Concept note of a TAP - 1 Terms of reference to be shared with GCF, training material and tools. Deliverable 2.5 - 1 Policy brief and market-use cases for each of the selected technologies - 1 Dissemination Strategy - 1 set of training materials for the regional workshops 1 Workshop report for each workshop held including a full list of participants and photo documentation. | As agreed with CTCN Project Manager, and due to the project implementation local characteristics, Deliverable 2.4 (i) Workshop report was replaced by interviews with representatives of ministry of Energy and Industry, Ministry of Mines and Hydrocarbons, General direction of Forests, General Direction of Agriculture and General direction of waste management. As agreed with CTCN Project Manager, and due to the project implementation local characteristics, Deliverable 2.4 (ii) Concept Note has been submitted in Spanish, so the local stakeholders could review it. | Interviews and workshops held allowed quality participation from local counterparts. | The importance of individual communication with every stakeholder is to be remarked. Despite the workshops as a strategic tool to foster networking among participants, the individual interviews allowed deep exchange of information and integration of experience and knowledge on internal institutional challenges or specific cases and opportunities. This exchange allowed the production of specifically targeted project ideas that would generate tangible changes. Based on this potential, the proposal with a broadest impact assumed was selected for a Concept Note. |

| Outcome 3: Climate finance strategies strengthened, private sector mobilized, and project pipeline enhanced |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome narrative: Activity 3.1. has been completed. |  |  |  |  |  |  |  |  |
| Outputs | Activities | Post-completion targets achieved | Progress against baseline | Indicators | Milestones and deliverables achieved | Variance explanation | Qualitative assessment of activities undertaken | Lessons learned and best practices |
| 3.1 Private sector engaged in country consultative processes | Activity 3.1: Enhancing SME capacity and enabling environment through innovative new business identification training programme | 2. Private sector engagement is systematically part of the country consultative processes and structured dialogues with the NDA/FP, accredited entities and the GCF Secretariat | Some private sector actors have been engaged during the TNA and TAP processes. | Activity 3.1 Deliverable 3.1 - 1 Workshop report for each workshop held | Activity 3.1 Deliverable 3.1 - 1 Workshop report for each workshop held | As agreed with CTCN Project Manager, Deliverable 3.1 (i) Workshop report was replaced by a report of interviews with representatives of the private sector. | Even though the activity had a characteristic of individual engagement instead of workshop, meaningful private sector engagement has been achieved. | Stakeholders of the private sector had presented a view of the country that points to the difficulty of developing small scale industries. This is one of the key causes of the weakness of the agricultural sector. |

SECTION 3: ACTUAL IMPLEMENTATION TIMETABLE Please provide an update of the overall timeline of the Readiness Support activities and deliverables described in the outcomes in the below Gantt chart according to the actual duration of the activity and month in which the deliverable was completed. Please ensure the outcomes/outputs/activities match those highlighted in Section 3.

| Outcome 1: Institutional capacity and coordination mechanisms in place to govern and coordinate climate action and finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outputs | Activities | Actual Overall Timeline of Implementation of Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1-9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 |
|  |  | Jan -Sep 20 | Oct 2020 | Nov 2020 | Dec 2020 | Jan 2021 | Feb 2021 | Mar 2021 | April 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | April 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 |
| 1.1 Effective coordination mechanism between NDA and National Designated Entity (NDE) for the UNFCCC Technology Mechanism and other climate finance focal points | Activity 1.1 Development of planning and communication documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 1.1. - Consolidated project work plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Monitoring and evaluation plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Impact Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | -Closure and Data Collection report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.2. Conduct stakeholder’s analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 1.2. Stakeholder mapping report, where roles and responsibilities are specified. Experience and contributions to technology use as well as adoption of men and women will be also included. It will be used to define and ensure a more targeted selection of the stakeholders to engage in the process. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.3 Support the establishment of a TNA Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 1.3: Official government circular establishing the national TNA committee. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - TNA Constitution document informing on the work of the TNA Committee. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - A full list of participants, photo documentations and a report of the training conducted. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.4: Development and endorsement of TNA Committee work plan for monitoring and oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 1.4. - TNA Committee work plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | -Committee’s meetings |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Outcome 2. Country Programming Process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outputs | Activities | Actual Overall Timeline of Implementation of Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1-9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 |
|  |  | Jan -Sep 20 | Oct 2020 | Nov 2020 | Dec 2020 | Jan 2021 | Feb 2021 | Mar 2021 | April 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | April 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 |
| 2.1 Technology solutions identified and prioritized in accordance with national strategies and plans | Activity 2.1: Pre-selection of sub-sectors for the fulfilment of Equatorial Guinea’s TNA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 2.1: - Report on TNA-TAP on alignment with CP and national plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Report on analysis of sectoral priorities expressed in national documents. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Report describing the methodology utilized for sector and subsector |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Meetings minutes. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 2.2: Assess, prioritize and validate key technologies for the fulfillment of Equatorial Guinea’s TNA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 2.2 - Technology fact sheets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Set of criteria for MCA exercise |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Workshops reports including a full list of participants, photo documentations. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Final reports including a mitigation TNA report and an adaptation TNA report. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | -Database in most suitable format |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 2.3: Development of Technology Action Plan(s) per sector and /or sub (sector). |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 2.3. Report and executive summary of each Technology Action Plan for each of the priority technologies in compliance with the TNA. It will consist of a TAP providing projects implementation proposals for each prioritized sector. Each sector’s section will contain 10 sub-sections (chapters) as per the list presented above. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 Stakeholder engagement consultative processes | Activity 2.4: National Consultation workshop to ensure national ownership and technology deployment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 2.4 - Workshop report including a full list of participants, photo documentations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Concept note of a TAP |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Terms of reference to be shared with GCF, training material and tools. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 2.5: Support the implementation of the Technology Action Plan with communications, guidance and training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 2.5 - Policy briefs and market-use cases for the selected technologies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Dissemination Strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Training materials for the regional workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | -Workshops reports including a full list of participants and photo documentation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Outcome 3: Climate finance strategies strengthened, private sector mobilized, and project pipeline enhanced |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outputs | Activities | Actual Overall Timeline of Implementation of Activities |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1-9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 |
|  |  | Jan -Sep 20 | Oct 2020 | Nov 2020 | Dec 2020 | Jan 2021 | Feb 2021 | Mar 2021 | April 2021 | May 2021 | Jun 2021 | Jul 2021 | Aug 2021 | Sep 2021 | Oct 2021 | Nov 2021 | Dec 2021 | Jan 2022 | Feb 2022 | Mar 2022 | April 2022 | May 2022 | Jun 2022 | Jul 2022 | Aug 2022 | Sep 2022 |
| 3.1: Private sector engagement | Activity 3.1: Enhancing SME capacity and enabling environment through innovative new business identification training programme |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 3.1 - Workshops reports including a full list of participants and photo documentation. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

SECTION 4: EXPENDITURE REPORTING This section requires reporting of the expenditure of total approved amount of grant. Double-click the table to edit the spreadsheet.

See budget template here:

https://www.greenclimate.fund/sites/default/files/document/readiness-budget-and-expenditure-report-template_0.xlsx

SECTION 5: PROCUREMENT List the items procured for the project (including consultants), their costs, procedures used (direct procurement, open tender, other) and final disposition. Double-click the table to edit the spreadsheet.

| FOR GREEN CLIMATE FUND’S SECRETARIAT USE ONLY |  |  |
| --- | --- | --- |
| Comments |  |  |
| Reviewed by: Name and Title (Reviewer): Position: | Signature: | Date: (DD-MM-YYYY) |
| Final assessment by: (Satisfactory to GCF) Name and Title (Reviewer): Position: | Signature: | Date: (DD-MM-YYYY) |

SPECIAL ADDENDUM: COVID-19 RELATED IMPACTS This section provides information on temporary measures to support project implementation through the extension period. Please be advised that the measures do not constitute a permanent change in policy. If you have any questions, please feel free to send an inquiry to opm@gcfund.org.

GCF has granted up to six-months extension of the grant term/anticipated duration of readiness activities for specific grants that had been approved by the GCF prior to the pandemic having arisen and which expire after 1 March 2020 and are effective prior to 8 April 2020. GCF has granted additional flexibilities with guidelines as outlined below. No-Cost Extension - All grants will be automatically extended by six months. However, please be informed that the willingness on the part of the GCF to provide this six-month extension on the basis of the COVID-19 pandemic is not intended to prevent RPSP activities from being delivered under the pre-pandemic existing contractual timelines. Delivery partners and National Designated Authorities/Focal Points (NDA/FP) can complete the grant implementation sooner than the full no-cost extension period. Therefore, the GCF expects that delivery partners will fully coordinate with NDA/FPs in relation to the application of the said extension as a result of the COVID-19 pandemic. - Delivery partners should include a revised workplan for the new period in the next reporting cycle. - Grants requiring an extension longer than the six-months must submit well justified requests in line with standard practices and procedures for the GCF’s consideration and approval. - The originally agreed grant sum required to complete the activities under the respective legal agreements remains unchanged for grants accepting the no-cost extension. Project management costs: The project management costs (PMC) cap has been increased from 7.5 percent to 12.5 percent of the total activity budget approved. Partners can tap into the approved contingency fund to meet these additional costs up to the 12.5% cap. If the delivery partner increases the PMC, then the delivery partner is required to provide detailed documentation and justification supporting the increase in PMC and clearly outlining how the additional costs are related to the COVID-19 pandemic. This justification should be included in the interim progress report or completion reports due for submission as detailed in the grant agreement. Contingency budget: The approved contingency amount included in the budgets for these activities may be used to cover unforeseen costs relating the COVID-19 pandemic without prior approval from GCF. The contingency budget may be used for project management costs (PMC). The said contingency expenses will need to be justified and included in the detailed reports that are required to be submitted by the delivery partner/recipient under the respective legal agreement between the delivery partner/recipient and the GCF. Budget Re-allocation: The reallocation of approved budget among the budget line items can be made from one budget category to another up to 25 percent variation across the categories. The receiver and giver budget category can only take or give without prior fund approval up to 25 percent based on the previously approved budget. Budget can also be reallocated from outputs without changing the project scope to PMC if the contingency budget is insufficient to meet the increases in PMC. The delivery partner is required to provide detailed documentation and justification supporting the budget reallocation in the submitted reports in line with the grant agreement.

Types of Measures; Output No.; Activity No.; Implementation and Deliverables Schedule (Please provide details of the change to activities, deliverables, etc.); Budgetary Implications. Impact on delivery modality; Deliverable; Original Date; Revised Date. Choose an item.. Choose an item.. Choose an item.. Choose an item.. Choose an item.. In-country Status (Please provide an update of the status of the country due to COVID-19 pandemic.); In Equatorial Guinea, from 3 January 2020 to 31st December 2022, there have been more than 17,000 confirmed cases of COVID-19 with more than 180 deaths, reported to WHO. As of 24 July 2022, a total of 488,738 vaccine doses have been administered.. Justification for Requests and Implications (Please provide details of the changes to support utilization of temporary measures.). Mitigation Measures (Please provide details of how risks will be mitigated); Virtual meetings are being held where in-person meetings are not allowed. When in-person meetings are conducted, national sanitary measures are being followed (required distance, wearing masks, ventilation of spaces and offices where meeting are conducted.)..

Annex. Final Disbursement Request Form

Please fill the below form to request for the final disbursement when the financial audit report/certified financial statements and completion report has been submitted to GCF (please note that the final disbursement request can be processed only after these conditions are met).

| FINAL DISBURSEMENT REQUEST |  |
| --- | --- |
| - Total amount approved for the project |  |
| - Disbursement from GCF made to date/Percentage of Total Grant (%) |  |
| - Total expenditure to date |  |
| - Expenditure rate as of the Completion Report submission date (%) |  |
| - Total amount of the final disbursement to request/Percentage of Total Grant (%) |  |
| - Name of Beneficiary Bank and located country |  |
| - Account number |  |
| - Bank address |  |
| - SWIFT (BIC) |  |
| - IBAN Code |  |
| - Date of the final disbursement request |  |

| Name and Title*: | Signature: | Date:05/12/2022 |
| --- | --- | --- |

*The signatory of grant agreement (either NDA or Delivery Partner) or any authorised person who is certified in the letter of authorisation submitted to the Fund can sign here. When this is not plausible, please kindly consult with the Fund (opm@gcfund.org) prior to the submission of the disbursement request.

| FOR GREEN CLIMATE FUND’S SECRETARIAT USE ONLY |  |  |
| --- | --- | --- |
| Comments |  |  |
| Reviewed by: Name and Title: Position: DSS Finance | Signature: | Date: (DD-MM-YYYY) |
| Certified by: Name and Title: Position: DSS Finance | Signature: | Date: (DD-MM-YYYY) |
| Approved by: Name and Title: Position: CFO | Signature: | Date: (DD-MM-YYYY) |

| FOR GREEN CLIMATE FUND’S SECRETARIAT USE ONLY |  |  |
| --- | --- | --- |
| Comments |  |  |
| Reviewed by: Name and Title (Reviewer): Position: | Signature: | Date: (DD-MM-YYYY) |
| Final assessment by: (Satisfactory to GCF) Name and Title (Reviewer): Position: | Signature: | Date: (DD-MM-YYYY) |

The term completion refers to the operational completion date.

The date at which all funds have been utilized and remaining balances have been returned to GCF for re-programming.

If possible, please provide hyperlinks to supporting documents.

If possible, please provide hyperlinks to supporting documents.

If possible, please provide hyperlinks to supporting documents.

If needed, please adjust the outcomes based on the submitted readiness proposal.

If needed, please adjust the outcomes based on the submitted readiness proposal.

If needed, please adjust the outcomes based on the submitted readiness proposal.