Grant Agreement Number (COD-RS-004)

Mr. Hans Andre Lohayo Djamba /UNIDO

Sections in this report:

- Section 1: General Information

- Section 2: Reporting on Country Readiness Logical Framework

- Section 3: Actual Implementation Timetable

- Section 4: Expenditure Reporting

- Section 5: Procurement

- Annex: Final Disbursement Request Form

For more information, please refer to the GCF Readiness and Preparatory Support Programme guidebook available online. Please submit the Completion Report to opm@gcfund.org.

Project completion report should be prepared and signed by Delivery Partner (DP) and/or National Designated Authority (NDA).

| Name and Title (DP): Mr. Ciyong Zou Position: Managing Director, Directorate of Programmes, Partnerships and Field Coordination, UNIDO | Signature: | Date: |
| --- | --- | --- |
| Name and Title (NDA): Mr. Hans Andre Lohayo Djamba Position: GCF National Coordinator and Focal Point, National Coordination of the Green Climate Fund | Signature: | Date: |

| FOR GREEN CLIMATE FUND’S SECRETARIAT USE ONLY |  |  |
| --- | --- | --- |
| Received by: | Signature | Date (DD-MM-YYYY) |

EXECUTIVE SUMMARY

The Readiness and Preparatory Support proposal was approved on 24 December 2019 and the notification of approval was sent on 7 January 2020. The first disbursement was requested on 24 April 2020. It was not received until 20 October 2020 as the GCF Secretariat requested the delivery partner to seek the approval of the UN Security Council Sanctions Committee on the implementation of the activities within this Readiness and Preparatory Support proposal. The Climate Technology Centre and Network (CTCN) awarded the contract of this assignment through UNIDO to a member of the CTCN network – Deloitte Tohmatsu Financial Advisory LLC (DTFA). The agreement between the delivery partner and the PEE was countersigned on 1 February 2021. A 12-month extension and restructuring request was submitted to the GCF in August 2021 and included a new competitive workshop for young entrepreneurs. The request was approved by the GCF and the new completion date was set for 5 October 2022. All activities and deliverables associated with Activity 1 and 2 were completed. Due to the restructuring, the new tasks were implemented as part of the whole projects, which were conducting the students and young entrepreneur competitive workshop and development of a concept note derived from the shortlisted idea by the workshop’s competitors. (Less than half a page)

| SECTION 1: GENERAL INFORMATION This section provides information on completing the General Information of the Readiness Support Completion Report template. |  |
| --- | --- |
| - Country | Democratic Republic of the Congo |
| - Grant agreement number | COD-RS-004 |
| - Date of grant agreement signed | 03/12/18 |
| - Grant effectiveness date | 07/01/20 |
| - Date of 1st disbursement received from GCF | 20/10/20 |
| - Project completion date | 05/10/22 |
| - Planned/Actual date of financial completion | Planned: Click or tap to enter a date. / Actual: 05/10/22 |
| - Planned/Actual project duration | Please provide the planned and actual project duration if they differ. Example: Planned project duration: 12 months / Actual project duration: 14 months |
| - Total approved grant amount | USD 302,925 |
| - Disbursement from GCF made to date to Delivery Partner or NDA | Choose an item. Example: USD 250,000 |
| - Final disbursements from GCF to Delivery Partner or NDA to be requested (if any) | Choose an item. Example: USD 50,000 |
| - Final Unspent Balance Refund from Delivery Partner or NDA to GCF (if any) |  |

SECTION 2: REPORTING ON COUNTRY READINESS LOGICAL FRAMEWORK This section requires an overview of key achievements and deliverables in implementing the Readiness Support activities. Any key deliverables to the agreed outputs should be submitted with the project completion report.

| Outcome 1: Institutional capacity and coordination mechanisms in place to govern and coordinate climate action and finance |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome narrative: Activities and deliverables corresponding to Activity 1 have been completed. DRC’s TNA Committee has been established and institutionalized, which include representatives from the public, private, and academic sectors and NGOs. The NDA and NDE lead an effective coordination mechanism for the implementation of the TNA, through the TNA Committee. |  |  |  |  |  |  |  |  |
| Outputs | Activities | Post-completion targets achieved | Progress against baseline | Indicators | Milestones and deliverables achieved | Variance explanation | Qualitative assessment of activities undertaken | Lessons learned and best practices |
| [Example] 1.1 NDA/focal point lead effective coordination mechanism | [Example] 1.1.1 Develop operational guidelines/manuals for the functioning of the NDA, including a procedure to establish an effective coordination mechanism 1.1.2 etc | Please rate the status of targets achieved after completion of activities in the scale 0 to 2, against the baseline and the proposed targets in the proposal. | Please provide a brief summary of the new baseline scenario at the post-completion stage. | Based on your approved proposal, please outline the key indicators. | Please state the milestones and deliverables achieved as agreed in the Grant Agreement. [Example] Deliverable: An operational manual defining and describing NDA’s roles and functions | In this column, identify and explain the reasons for the difference, if any, between a planned activity and the corresponding actual activity that took place. | In this column, summarize some of the qualitative results achieved through activities undertaken. | Please summarize the key lessons learned and best practices which can be replicated or taken to scale. |
| 1.1 Effective coordination mechanism between NDA and National Designated Entity (NDE) for the UNFCCC Technology Mechanism and other climate finance focal points | Activity 1: Institutionalization of a coordination mechanism for the implementation of the TNA. Activity 1.1 Development of planning and communication documents Activity 1.2. Conduct stakeholder’s analysis Activity 1.3 Support the establishment of a TNA Committee Activity 1.4: Development and endorsement of TNA Committee work plan for monitoring and oversight | 2. NDA/focal point leads an effective coordination mechanism, allowing for an overview of all operational sectors and meets regularly | Baseline: Communication initiated between NDA, NDE and other climate finance focal Points. However, there is no TNA committee in place, nor TNA Work plan developed. Progress: The TNA committee has been established and institutionalised, together with the TNA committee constitution and TNA work plan. | Deliverable 1.1: - 1 Consolidated project work plan - 1 Monitoring and evaluation plan - 1 Impact Description - Closure and Data Collection report Deliverable 1.2 - 1 Stakeholder mapping report Deliverable 1.3 - Official government circular establishing the national TNA committee. - TNA Constitution document informing on the work of the TNA Committee - Rental contract of the centralized office for the coordination of activities - A full list of participants, photo documentations and a report of the training conducted Deliverable 1.4 - TNA Committee work plan - 8 Committee’s meetings reports | Activity 1.1 Development of planning and communication documents Deliverable 1.1: - 1 Consolidated project work plan - 1 Monitoring and evaluation plan - 1 Impact Description - Closure and Data Collection report Activity 1.2. Conduct stakeholder’s analysis Deliverable 1.2 - Stakeholder mapping report Activity 1.3 Support the establishment of a TNA Committee Deliverable 1.3: - Official government circular establishing the national TNA committee. - TNA Constitution document informing on the work of the TNA Committee - A full list of participants, photo documentations and a report of the training conducted Activity 1.4: Development and endorsement of TNA Committee work plan for monitoring and oversight Deliverable 1.4: - TNA Committee work plan - 8 Committee’s meeting reports. | Deliverable 1.1: 1 Monitoring and evaluation plan and 1 Impact Description were consolidated to one report. Deliverable 1.3: No rental contract of the centralized office for the coordination of activities was made. | Activity 1.1 is finalised. Activity 1.2 is finalised. Activity 1.3 is finalised. Activity 1.4 is finalised. | Identifying stakeholders in potential target sectors at early stage will ensure effective inputs for the TNA. Establishing communication channel with key stake holders is crucial to ensure smooth and efficient implementation of subsequent activities. |

3

| Outcome 2: Country Programme Established |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outcome narrative: Activities and deliverables related to Activity 2.1 to 2.3 have been completed. Sectors and subsectors for the TNA have been identified and prioritized. Activities including the identification of mitigation and adaptation technologies for the fulfilment of DRC’s TNA, the development of TAPs, the validation of TAPs, the development of concept notes and related documents, the implementation of training workshops have also been completed. |  |  |  |  |  |  |  |  |
| Outputs | Activities | Post-completion targets achieved | Progress against baseline | Indicators | Milestones and deliverables achieved | Variance explanation | Qualitative assessment of activities undertaken | Lessons learned and best practices |
| 2.1 Technology solutions identified and prioritized in accordance with national strategies and plans | Activity 2: Prioritization of technologies and relevant action for increased access to finance Activity 2.1: Pre-selection of sub-sectors for the fulfilment of DRC’s TNA Activity 2.2: Assess, prioritize and validate key technologies for the fulfilment of DRC’s TNA Activity 2.3: Development of Technology Action Plan(s) per sector and /or sub (sector) | 2. Stakeholders engaged in consultative processes (governments, private sector, associations, civil society, academia and others) | Baseline: GCF CP is developed but no appropriate climate technologies have been identified and prioritized. Progress: Sectors and sub-sectors were first analysed and prioritised against the climate change objectives. Following this potential climate technologies were analysed and prioritised against the climate change objectives as well as DRC’s development goals. The TAP for the prioritised technologies was developed and validated. Furthermore, two concept notes were developed (one derived from the TAP and the other derived from the shortlisted ideas by students and young entrepreneurs). | Deliverable 2.1 - Report on TNA-TAP on alignment with CP and national plans - Report on analysis of sectoral priorities expressed in national documents - Report describing the methodology utilized for sector and subsector selection and prioritization. - Meetings minutes Deliverable 2.2 - Technology fact sheets - Set of criteria for MCA exercise - Workshops reports including a full list of participants, photo documentations. - Final reports including a mitigation TNA report and an adaptation TNA report. - Database in most suitable format Deliverable 2.3 - Report and executive summary of each Technology Action Plan for each of the priority technologies in compliance with the TNA | Activity 2.1: Pre-selection of sub-sectors for the fulfilment of DRC’s TNA Deliverable 2.1 - Report on TNA-TAP on alignment with CP and national plans - Report on analysis of sectoral priorities expressed in national documents - Report describing the methodology utilized for sector and subsector selection and prioritization. - Meetings minutes Activity 2.2: Assess, prioritize and validate key technologies for the fulfilment of DRC’s TNA Deliverable 2.2 - Technology fact sheets - Set of criteria for MCA exercise - Workshops reports including a full list of participants, photo documentations. - Final reports including a mitigation TNA report and an adaptation TNA report. - Database in most suitable format Activity 2.3: Development of Technology Action Plan(s) per sector and /or sub (sector) Deliverable 2.3 - Report and executive summary of each Technology Action Plan for each of the priority technologies in compliance with the TNA | Deliverable 2.1: The three reports were consolidated to one report covering 1) report on TNA-TAP on alignment with CP and national plans, 2) report on analysis of sectoral priorities expressed in national documents, and 3) report describing the methodology utilized for sector and subsector selection and prioritisation. Deliverables 2.2: The technology fact sheets and the set of criteria for MCA exercise were consolidated to the final report including a mitigation TNA report and an adaptation TNA report. | Activity 2.1 is finalised. Activity 2.2 is finalised. Activity 2.3 is finalised. | In prioritising technologies, it was effective to take into account of the country’s characteristics. In case of DRC for instance, the recognition on the river networks lead the stakeholders to prioritise the technology “Modal shift in freight transport.” |
| 2.2 Stakeholder engagement consultative processes | Activity 2.4: National Consultation workshop to ensure national ownership and technology deployment Activity 2.5: Support the implementation of the Technology Action Plan with communications, guidance and training | 2. Country programmes developed and continuously updated and progress assessed regularly in a consultative manner | Baseline: Some stakeholders are being consulted under the first readiness grant, however a formal consultation process has not been established for climate technology identification process. Progress: Key stakeholders have been consulted through the TNA process. Furthermore, the consultation process has been established and institutionalised through the TNA committee. | Deliverable 2.4 - Workshop report including a full list of participants, photo documentations - 1 concept note derived from within the TAPs - 1 concept note derived from the ideas shortlisted in the competitive workshop - Terms of reference corresponding to be shared with GCF, training material and tools - Competitive workshop and mentoring report Deliverable 2.5 - Policy briefs and market-use cases for the selected technologies - Dissemination Strategy - Training materials for the workshops - Workshops reports including a full list of participants, photo documentations | Activity 2.4: National Consultation workshop to ensure national ownership and technology deployment Deliverable 2.4 - Workshop report including a full list of participants, photo documentations - 1 concept note derived from within the TAPs - 1 concept note derived from the ideas shortlisted in the competitive workshop - Terms of reference corresponding to be shared with GCF, training material and tools - Competitive workshop and mentoring report Activity 2.5: Support the implementation of the Technology Action Plan with communications, guidance and training Deliverable 2.5 - Policy briefs and market-use cases for the selected technologies - Dissemination Strategy - Training materials for the workshops - Workshops reports including a full list of participants, photo documentations | Deliverables 2.5: Four workshops were conducted and reported in one report. | Activity 2.4 is finalised. Activity 2.5 is finalised. | Conducting a students and young entrepreneurs workshop was an innovative opportunity to involve diverse stakeholders who are not currently in the political or administrative institutions. |

SECTION 3: ACTUAL IMPLEMENTATION TIMETABLE Please provide an update of the overall timeline of the Readiness Support activities and deliverables described in the outcomes in the below Gantt chart according to the actual duration of the activity and month in which the deliverable was completed. Please ensure the outcomes/outputs/activities match those highlighted in Section 3.

| Outcome 1: Institutional capacity and coordination mechanisms in place to govern and coordinate climate action and finance |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outputs | Activities | Actual Overall Timeline of Implementation of Activities (Number of months can be adjusted according to the actual project duration and milestones.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 |
|  |  | Jan 19 | Feb 20 | Mar 20 | Apr 20 | May 20 | Jun 20 | Jul 20 | Aug 20 | Sep 20 | Oct 20 | Nov 20 | Dec 20 | Jan 21 | Feb 21 | Mar 21 | Apr 21 | May 21 | Jun 21 | Jul 21 | Aug 21 | Sep 21 | Oct 21 | Nov 21 | Dec 21 | Jan 22 | Feb 22 | Mar 22 | Apr 22 | May 22 | Jun 22 | Jul 22 | Aug 22 | Sep 22 | Oct 22 |
| 1.1 Effective coordination mechanism between NDA and National Designated Entity (NDE) for the UNFCCC Technology Mechanism and other climate finance focal points | Activity 1.1 Development of planning and communication documents |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 1.1. - Consolidated project work plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Monitoring and evaluation plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Impact Description |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Closure and Data Collection report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.2. Conduct stakeholder’s analysis |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 1.2. - Stakeholder mapping report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.3 Support the establishment of a TNA Committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 1.3: - Official government circular establishing the national TNA committee |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - TNA Constitution document informing on the work of the TNA Committee. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - A full list of participants, photo documentations and a report of the training conducted. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 1.4: Development and endorsement of a work plan for monitoring and oversight |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 1.4. - TNA Committee work plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Committee’s meetings. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

| Outcome 2. Country Programming process |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Outputs | Activities | Actual Overall Timeline of Implementation of Activities (Number of months can be adjusted according to the actual project duration and milestones.) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 32 | 33 | 34 |
|  |  | Jan 19 | Feb 20 | Mar 20 | Apr 20 | May 20 | Jun 20 | Jul 20 | Aug 20 | Sep 20 | Oct 20 | Nov 20 | Dec 20 | Jan 21 | Feb 21 | Mar 21 | Apr 21 | May 21 | Jun 21 | Jul 21 | Aug 21 | Sep 21 | Oct 21 | Nov 21 | Dec 21 | Jan 22 | Feb 22 | Mar 22 | Apr 22 | May 22 | Jun 22 | Jul 22 | Aug 22 | Sep 22 | Oct 22 |
| 2.1 Technology solutions identified and prioritized in accordance with national strategies and plans | Activity 2.1: Pre-selection of sub-sectors for the fulfilment of DRC’s TNA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 2.1: - Report on TNA-TAP on alignment with CP and national plans |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Report on analysis of sectoral priorities expressed in national documents. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Report describing the methodology utilized for sector and subsector selection and prioritization. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Meetings minutes. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 2.2: Validate, prioritize and assess feasibility of key technologies for the fulfilment of the DRC’s TNA |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 2.2 - Technology fact sheets |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Set of criteria for MCA exercise |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Workshops reports including a full list of participants, photo documentations. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Final reports including a mitigation TNA report and an adaptation TNA report. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Database in most suitable format |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 2.3: Development of Technology Action Plan(s) per sector and /or sub (sector), quantifying the impact of priority technologies within each sector per action plan. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 2.3. - Report and executive summary of each Technology Action Plan |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| 2.2 Stakeholder engagement consultative processes | Activity 2.4: National Consultation workshop to ensure national ownership and technology deployment |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 2.4 - Workshop report including a full list of participants, photo documentations |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Terms of reference to be shared with GCF, training material and tools. |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Concept notes |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Competitive workshop and mentoring report |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Activity 2.5: Support the implementation of the Technology Action Plan with communications, guidance and training |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | Deliverable 2.5: - Policy briefs and market-use cases for the selected technologies |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Dissemination Strategy |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Training materials for the regional workshops |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
|  | - Workshops reports including a full list of participants and photo documentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

|  | Completed activities |
| --- | --- |
|  | Completed deliverables |

SECTION 4: EXPENDITURE REPORTING This section requires reporting of the expenditure of total approved amount of grant. Double-click the table to edit the spreadsheet.

See budget template here:

https://www.greenclimate.fund/sites/default/files/document/readiness-budget-and-expenditure-report-template_0.xlsx

SECTION 5: PROCUREMENT List the items procured for the project (including consultants), their costs, procedures used (direct procurement, open tender, other) and final disposition. Double-click the table to edit the spreadsheet.

| FOR GREEN CLIMATE FUND’S SECRETARIAT USE ONLY |  |  |
| --- | --- | --- |
| Comments |  |  |
| Reviewed by: Name and Title (Reviewer): Position: | Signature: | Date: (DD-MM-YYYY) |
| Final assessment by: (Satisfactory to GCF) Name and Title (Reviewer): Position: | Signature: | Date: (DD-MM-YYYY) |

SPECIAL ADDENDUM: COVID-19 RELATED IMPACTS This section provides information on temporary measures to support project implementation through the extension period. Please be advised that the measures do not constitute a permanent change in policy. If you have any questions, please feel free to send an inquiry to opm@gcfund.org.

GCF has granted up to six-months extension of the grant term/anticipated duration of readiness activities for specific grants that had been approved by the GCF prior to the pandemic having arisen and which expire after 1 March 2020 and are effective prior to 8 April 2020. GCF has granted additional flexibilities with guidelines as outlined below. No-Cost Extension - All grants will be automatically extended by six months. However, please be informed that the willingness on the part of the GCF to provide this six-month extension on the basis of the COVID-19 pandemic is not intended to prevent RPSP activities from being delivered under the pre-pandemic existing contractual timelines. Delivery partners and National Designated Authorities/Focal Points (NDA/FP) can complete the grant implementation sooner than the full no-cost extension period. Therefore, the GCF expects that delivery partners will fully coordinate with NDA/FPs in relation to the application of the said extension as a result of the COVID-19 pandemic. - Delivery partners should include a revised workplan for the new period in the next reporting cycle. - Grants requiring an extension longer than the six-months must submit well justified requests in line with standard practices and procedures for the GCF’s consideration and approval. - The originally agreed grant sum required to complete the activities under the respective legal agreements remains unchanged for grants accepting the no-cost extension. Project management costs: The project management costs (PMC) cap has been increased from 7.5 percent to 12.5 percent of the total activity budget approved. Partners can tap into the approved contingency fund to meet these additional costs up to the 12.5% cap. If the delivery partner increases the PMC, then the delivery partner is required to provide detailed documentation and justification supporting the increase in PMC and clearly outlining how the additional costs are related to the COVID-19 pandemic. This justification should be included in the interim progress report or completion reports due for submission as detailed in the grant agreement. Contingency budget: The approved contingency amount included in the budgets for these activities may be used to cover unforeseen costs relating the COVID-19 pandemic without prior approval from GCF. The contingency budget may be used for project management costs (PMC). The said contingency expenses will need to be justified and included in the detailed reports that are required to be submitted by the delivery partner/recipient under the respective legal agreement between the delivery partner/recipient and the GCF. Budget Re-allocation: The reallocation of approved budget among the budget line items can be made from one budget category to another up to 25 percent variation across the categories. The receiver and giver budget category can only take or give without prior fund approval up to 25 percent based on the previously approved budget. Budget can also be reallocated from outputs without changing the project scope to PMC if the contingency budget is insufficient to meet the increases in PMC. The delivery partner is required to provide detailed documentation and justification supporting the budget reallocation in the submitted reports in line with the grant agreement.

Types of Measures; Output No.; Activity No.; Implementation and Deliverables Schedule (Please provide details of the change to activities, deliverables, etc.); Budgetary Implications. Impact on delivery modality; Deliverable; Original Date; Revised Date. Choose an item.. Choose an item.. Choose an item.. Choose an item.. Choose an item.. In-country Status (Please provide an update of the status of the country due to COVID-19 pandemic.); As of 28th November 2022, there have been 94,203 confirmed cases of COVID-19 with 1,455 deaths, reported to WHO. As of 22 October 2022, a total of 6,185,534 vaccine doses have been administered. In this reporting period, cases have decreased, with 339 cases confirmed in the week of 4th July 2022 against 49 cases in the week of 23rd November 2022. Although restrictive measures have been relaxed, some of them are still remaining. For instance, unvaccinated travelers entering to and travelling within DRC are required to present a negative COVID-19 test. Upon leaving DRC, unvaccinated travelers are required to present a negative COVID-19 test from the designated institutions.. Justification for Requests and Implications (Please provide details of the changes to support utilization of temporary measures.). Mitigation Measures (Please provide details of how risks will be mitigated); The PEE took a hybrid approach as agreed with the NDE and NDA in holding trainings and workshops, with events being held in-person and virtually..

Annex. Final Disbursement Request Form

Please fill the below form to request for the final disbursement when the financial audit report/certified financial statements and completion report has been submitted to GCF (please note that the final disbursement request can be processed only after these conditions are met).

| FINAL DISBURSEMENT REQUEST |  |
| --- | --- |
| - Total amount approved for the project | Choose an item. Example: USD 300,000 |
| - Disbursement from GCF made to date/Percentage of Total Grant (%) | Choose an item. Example: USD 120,000 /40 % (refer to Grant Agreement) |
| - Total expenditure to date | Choose an item. Example: USD 118,000 |
| - Expenditure rate as of the Completion Report submission date (%) | Please divide the received amount (2) by the executed amount (3). Example: 70% |
| - Total amount of the final disbursement to request/Percentage of Total Grant (%) | Choose an item. Example: USD 130,000/43 % (refer to Grant Agreement) |
| - Name of Beneficiary Bank and located country |  |
| - Account number |  |
| - Bank address |  |
| - SWIFT (BIC) |  |
| - IBAN Code |  |
| - Date of the final disbursement request | Click or tap to enter a date. |

| Name and Title*: Position: | Signature: | Date: |
| --- | --- | --- |

*The signatory of grant agreement (either NDA or Delivery Partner) or any authorised person who is certified in the letter of authorisation submitted to the Fund can sign here. When this is not plausible, please kindly consult with the Fund (opm@gcfund.org) prior to the submission of the disbursement request.

| FOR GREEN CLIMATE FUND’S SECRETARIAT USE ONLY |  |  |
| --- | --- | --- |
| Comments |  |  |
| Reviewed by: Name and Title: Position: DSS Finance | Signature: | Date: (DD-MM-YYYY) |
| Certified by: Name and Title: Position: DSS Finance | Signature: | Date: (DD-MM-YYYY) |
| Approved by: Name and Title: Position: CFO | Signature: | Date: (DD-MM-YYYY) |

| FOR GREEN CLIMATE FUND’S SECRETARIAT USE ONLY |  |  |
| --- | --- | --- |
| Comments |  |  |
| Reviewed by: Name and Title (Reviewer): Position: | Signature: | Date: (DD-MM-YYYY) |
| Final assessment by: (Satisfactory to GCF) Name and Title (Reviewer): Position: | Signature: | Date: (DD-MM-YYYY) |

The term completion refers to the operational completion date.

The date at which all funds have been utilized and remaining balances have been returned to GCF for re-programming.

If possible, please provide hyperlinks to supporting documents.

If possible, please provide hyperlinks to supporting documents.

If needed, please adjust the outputs based on the submitted readiness proposal.

If needed, please adjust the outcomes based on the submitted readiness proposal.