## EBT
STRUCTURING OF ACTIVITIES
| Project |  | Technical Guide for Updating the Technology Needs Assessment (TNA) and Developing a Technology Action Plan for the Implementation of NDC Côte d'Ivoire |  |  |  | Period | 2023-06-01 | 2024-12-31
Prioritization of objectives | [5 empty] | Responsibility | Implementation structure | Start date | End date | Activity Tracking | Expected results | Performance indicators | Verification Sources | Indicative targets | Assumptions / Risks | Comments
Overall Objective |  |  | Update the Technology Needs Assessment (TNA) and develop a Technology Action Plan (TAP) for priority technologies to address climate change challenges in the most critical sectors of the economy.
OBS1: |  |  | Develop the Technology Needs Assessment (TEA) report
OBS2: |  |  | Establishing an Inclusive Climate Technology Innovation System (ICTIS)
OBS3: |  |  | Development of Technological Action Plans (PAT)
| OBS1: | Develop the Technology Needs Assessment (TEA) report | [14 empty] | 1 | 0 | 1.0 | 0 | #NAME?
|  | Activité 1.1 | Carry out documentary research to make a diagnosis and define the contours of the needs expressed | 1.1.1 | Identify reporting documents in the area of ​​climate change | OIKO | CSI | 2023-06-19 | 2023-06-30 | Achieved | Notification documents available and analyzed | Diagnostic analysis report available | ITUC Archive | Seven notification documents | - Lack of budget - Difficulty of access |  | 1 | 1 | 1.1 | 1 | #NAME?
|  |  |  | 1.1.2 | Identify sector documents related to climate technologies | OIKO | CSI | 2023-06-19 | 2023-06-30 | Achieved | [6 empty] | 1 | 1 | 1.1 | 2 | #NAME?
|  |  |  | 1.1.3 | Analyze identified documents | OIKO | CSI | 2023-06-19 | 2023-06-30 | In progress | [6 empty] | 1 | 1 | 1.1 | 3 | #NAME?
|  |  |  | 1.1.4 | Produce the diagnostic report on climate technology | OIKO | CSI | 2023-06-19 | 2023-06-30 | In progress | [6 empty] | 1 | 1 | 1.1 | 4 | #NAME?
|  | Activité 1.2 | Update national climate change circumstances | 1.2.1 | Identify relevant data and information to update and improve the national circumstances of the country | OIKO | CSI | 2023-06-19 | 2023-06-30 | Not Achieved | Updated information on national circumstances | National circumstances report available | ITUC Archive | Seven notification documents | - Lack of budget - Difficulty of access |  | 1 | 2 | 1.2 | 1 | #NAME?
|  |  |  | 1.2.2 | Organize a launch and capacity building workshop for stakeholders on the EBT process | OIKO | CSI | 2023-07-04 | 2023-07-05 | Not Achieved | [6 empty] | 1 | 2 | 1.2 | 2 | #NAME?
|  |  |  | 1.2.3 | Identify information on geography, climate, population, natural resources, socio-economic profile, economy and development and other policies related to climate change | OIKO | CSI | 2023-06-19 | 2023-06-30 | Not Achieved | [6 empty] | 1 | 2 | 1.2 | 3 | #NAME?
|  |  |  | 1.2.4 | Inventory information on geography, climate, population, natural resources, related to climate change to obtain the necessary data | OIKO | CSI | 2023-06-19 | 2023-06-30 | Not Achieved | [6 empty] | 1 | 2 | 1.2 | 4 | #NAME?
|  |  |  | 1.2.5 | Produce a report on the national context of the country | OIKO | CSI | 2023-06-19 | 2023-06-30 | Not Achieved | [6 empty] | 1 | 2 | 1.2 | 5 | #NAME?
|  | Activité 1.3 | Carry out the inventory of technological options by existing sector in the country | 1.3.1 | Identify and map stakeholders | OIKO | CSI | 2023-06-01 | 2023-06-15 | Achieved | Survey sheet and data collection missions carried out | Number of technology options available | ITUC Archive | xx technology options | - Unavailability of experts - Lack of collaboration from technology holders |  | 1 | 3 | 1.3 | 1 | #NAME?
|  |  |  | 1.3.2 | Identify the structures holding climate technology | OIKO | CSI | 2023-07-06 | 2023-07-13 | Not Achieved | [6 empty] | 1 | 3 | 1.3 | 2 | #NAME?
|  |  |  | 1.3.3 | Develop the survey sheet for the collection of information on technologies | CSI | experts | 2023-06-19 | 2023-06-30 | Not Achieved | [6 empty] | 1 | 3 | 1.3 | 3 | #NAME?
|  |  |  | 1.3.4 | Carry out field missions to collect technological options in predefined sectors | CSI | experts | 2023-07-15 | 2023-10-15 | Not Achieved | [6 empty] | 1 | 3 | 1.3 | 4 | #NAME?
|  |  |  | 1.3.5 | Organize a validation workshop of the technology options matrix | OIKO | CSI | 2023-11-07 | 2023-11-08 | Not Achieved | [6 empty] | 1 | 3 | 1.3 | 5 | #NAME?
|  | Activité 1.4 | Carry out the technology options prioritization process | 1.4.1 | Identify objectives and criteria for the evaluation of identified technologies | OIKO | CSI | 2023-08-01 | 2023-08-31 | Not Achieved | Technology prioritization report and EBT report prepared and validated | Number of documents available | ITUC Archive | Two reports on available technologies | - Unavailability of CSI experts - Lack of motivation of experts |  | 1 | 4 | 1.4 | 1 | #NAME?
|  |  |  | 1.4.2 | Strengthen experts on Multi-Criteria Decision Analysis (MCA), which aims to assess a coherent family of criteria to inform a decision-making process | OIKO | CSI and technology owners | 2023-10-18 | 2023-10-20 | Not Achieved | [6 empty] | 1 | 4 | 1.4 | 2 | #NAME?
|  |  |  | 1.4.3 | Organize a workshop on the technology prioritization process | OIKO | CSI and technology owners | 2023-10-18 | 2023-10-20 | Not Achieved | [6 empty] | 1 | 4 | 1.4 | 3 | #NAME?
|  |  |  | 1.4.4 | Develop Technology Needs Assessment reports | OIKO | CSI | 2023-11-01 | 2023-11-30 | Not Achieved | [6 empty] | 1 | 4 | 1.4 | 4 | #NAME?
|  |  |  | 1.4.5 | Organize an EBT report validation workshop | OIKO | CSI | 2023-12-19 | 2023-12-20 | Not Achieved | [6 empty] | 1 | 4 | 1.4 | 5 | #NAME?
| OBS2: | Establishing an Inclusive Climate Technology Innovation System (ICTIS) | [14 empty] | 2 | 0 | 2.0 | 0 | #NAME?
|  | Activité 2.1 | Make an inventory or inventory of existing information systems in order to analyze the advantages and disadvantages | 2.1.1 | Identify existing and ongoing applications in the field of environment and climate change | CSI | Experts in charge of development | 2023-06-19 | 2023-07-20 | In progress | The recommendations report on the implementation of a technological platform and the data dictionary | Number of documents for application development | ITUC Archive | xx application development documents | - Incompetence of developers - Lack of motivation |  | 2 | 1 | 2.1 | 1 | #NAME?
|  |  |  | 2.1.2 | Analyze existing climate change information systems | CSI | Experts in charge of development | 2023-07-20 | 2023-06-30 | Not Achieved | [6 empty] | 2 | 1 | 2.1 | 2 | #NAME?
|  |  |  | 2.1.3 | Carry out the mapping of information systems in terms of designer, status and hosting | CSI | Experts in charge of development | 2023-07-01 | 2023-07-31 | Not Achieved | [6 empty] | 2 | 1 | 2.1 | 3 | #NAME?
|  |  |  | 2.1.4 | Make a diagnostic report of existing applications | CSI | Experts in charge of development | 2023-07-01 | 2023-07-31 | Not Achieved | [6 empty] | 2 | 1 | 2.1 | 4 | #NAME?
|  | Activité 2.2 | Carry out the design and development of database management systems | 2.2.1 | Set up a working team with sector experts to collect the information necessary for the realization of the database systems | CSI | Development experts and sector experts | 2024-01-02 | 2024-01-31 | Not Achieved | The design of database management systems is carried out | Specifications are available | ITUC Archive | xx specifications | - Unavailability of developers - Insufficient budget |  | 2 | 2 | 2.2 | 1 | #NAME?
|  |  |  | 2.2.2 | Define the database model and choose the appropriate database management system (DBMS) | CSI | Development experts and sector experts | 2024-01-02 | 2024-01-31 | Not Achieved | [6 empty] | 2 | 2 | 2.2 | 2 | #NAME?
|  |  |  | 2.2.3 | Define the general architecture of the database management system | CSI | Development experts and sector experts | 2024-01-02 | 2024-01-31 | Not Achieved | [6 empty] | 2 | 2 | 2.2 | 3 | #NAME?
|  |  |  | 2.2.4 | Organize a validation workshop for the design of database management systems | CSI | Development experts, sector experts and resource persons | 2024-02-06 | 2024-02-06 | Not Achieved | [6 empty] | 2 | 2 | 2.2 | 4 | #NAME?
|  |  |  | 2.2.5 | Develop and put online the ICTIS platform integrating sectoral database systems | CSI | Development experts and sector experts | 2024-02-07 | 2024-03-31 | Not Achieved | [6 empty] | 2 | 2 | 2.2 | 5 | #NAME?
|  |  |  | 2.2.6 | Organize a workshop to present and validate the ICTIS platform | CSI | Development experts, sector experts and resource persons | 2024-04-16 | 2024-04-16 | Not Achieved | [6 empty] | 2 | 2 | 2.2 | 6 | #NAME?
|  | Activité 2.3 | Establish an Inclusive Climate Technology Innovation System (ICTIS) platform | 2.3.1 | List the National MRV system (Measurement, Notification and Verification) which is a system integrating the monitoring of technologies | CSI | Experts in charge of development | 2024-04-02 | 2024-04-30 | Not Achieved | ICTIS platform developed and linked to the national MRV system | The development report of the ICTIS platform and the software package made available | CSI archive and ICTIS platform URL | xx applications available | - Unavailability of developers - Insufficient budget |  | 2 | 3 | 2.3 | 1 | #NAME?
|  |  |  | 2.3.2 | Analyze the different options for integrating the two systems | CSI | Experts in charge of development | 2024-04-02 | 2024-04-30 | Not Achieved | [6 empty] | 2 | 3 | 2.3 | 2 | #NAME?
|  |  |  | 2.3.3 | Integrate the ICTIS platform into the National MRV System | CSI | Experts in charge of development | 2024-04-02 | 2024-04-30 | Not Achieved | [6 empty] | 2 | 3 | 2.3 | 3 | #NAME?
|  | Activité 2.4 | Strengthen the capacities of climate actors in the use of the ICTIS platform | 2.4.1 | Develop a training program and modules to familiarize stakeholders with the EBT process | CSI | Experts in charge of development | 2024-05-01 | 2024-05-31 | Not Achieved | Platform administrators and users are reinforced | Number of players in the ICTIS platform strengthened | ITUC Archive | xx actors of the ICTIS platform strengthened | - Unavailability of developers - Unavailability of actors |  | 2 | 4 | 2.4 | 1 | #NAME?
|  |  |  | 2.4.2 | Organize a training workshop for system administrators for skills transfer | CSI | Experts in charge of development | 2024-06-04 | 2024-06-05 | Not Achieved | [6 empty] | 2 | 4 | 2.4 | 2 | #NAME?
|  |  |  | 2.4.3 | Organize a training workshop for ICTIS system users | CSI | Experts in charge of development | 2024-06-06 | 2024-06-07 | Not Achieved | [6 empty] | 2 | 4 | 2.4 | 3 | #NAME?
|  | Activité 2.5 | Establish an institutional arrangement to sustain the system | 2.5.1 | Identify and list all legal provisions relating to climate change | CSI | Legal expert | 2024-05-02 | 2024-06-30 | Not Achieved | An institutional arrangement to sustain the system is available | Number of projects stopped for the operation and perinization of the system | ITUC Archive | xx stop projects for the operation and perinization of the system | - Unavailability of the legal expert |  | 2 | 5 | 2.5 | 1 | #NAME?
|  |  |  | 2.5.2 | Identify and catalog the members of the steering committee and those of the technical committee | CSI | Legal expert | 2024-05-02 | 2024-06-30 | Not Achieved | [6 empty] | 2 | 5 | 2.5 | 2 | #NAME?
|  |  |  | 2.5.3 | Develop a draft order for the operation and perinization of the system | CSI | Legal expert | 2024-05-02 | 2024-06-30 | Not Achieved | [6 empty] | 2 | 5 | 2.5 | 3 | #NAME?
| OBS3: | Development of Technological Action Plans (PAT) | [14 empty] | 3 | 0 | 3.0 | 0 | #NAME?
|  | Activité 3.1 | Develop and validate a technology appropriation action plan by sector and by technology | 3.1.1 | Conduct pre-workshop fact-finding missions to identify climate change impacts and technology implementation barriers | CSI | Development experts, sector experts and resource persons | 2023-07-15 | 2023-10-15 | Not Achieved | Technology ownership action plans are carried out | Number of technology ownership action plans | ITUC Archive | xx technology ownership action plans | - Unavailability of experts - Unavailability of resource persons |  | 3 | 1 | 3.1 | 1 | #NAME?
|  |  |  | 3.1.2 | Identify resource persons by technology and by sector to have reliable documents on technological options | CSI | Development experts, sector experts and resource persons | 2023-07-15 | 2023-10-15 | Not Achieved | [6 empty] | 3 | 1 | 3.1 | 2 | #NAME?
|  |  |  | 3.1.3 | Develop acquisition guides for identified technologies | CSI | Development experts, sector experts and resource persons | 2023-10-16 | 2023-12-31 | Not Achieved | [6 empty] | 3 | 1 | 3.1 | 3 | #NAME?
|  |  |  | 3.1.4 | Produce a financial plan for each technology and by sector | CSI | Development experts, sector experts and resource persons | 2023-10-16 | 2023-12-31 | Not Achieved | [6 empty] | 3 | 1 | 3.1 | 4 | #NAME?
|  |  |  | 3.1.5 | Propose a scale for the deployment of the selected technologies | CSI | Development experts, sector experts and resource persons | 2023-10-16 | 2023-12-31 | Not Achieved | [6 empty] | 3 | 1 | 3.1 | 5 | #NAME?
|  | Activité 3.2 | Set a framework for action | 3.2.1 | List feasible steps to overcome identified technology barriers | CSI | The experts | 2024-01-01 | 2024-03-31 | Not Achieved | The action framework is defined for each technology | Number of action frameworks for each technology | ITUC Archive | xx frame of actions by technology | - Unavailability of experts |  | 3 | 2 | 3.2 | 1 | #NAME?
|  |  |  | 3.2.2 | Define the actions necessary for the successful implementation of the technology in the country and define the related activities | CSI | The experts | 2024-01-01 | 2024-03-31 | Not Achieved | [6 empty] | 3 | 2 | 3.2 | 2 | #NAME?
|  |  |  | 3.2.3 | Identify the stakeholders in charge of implementing the TAP and define their respective roles and responsibilities | CSI | The experts | 2024-01-01 | 2024-03-31 | Not Achieved | [6 empty] | 3 | 2 | 3.2 | 3 | #NAME?
|  |  |  | 3.2.4 | Establish the timetable for the implementation of the PAT | CSI | The experts | 2024-01-01 | 2024-03-31 | Not Achieved | [6 empty] | 3 | 2 | 3.2 | 4 | #NAME?
|  |  |  | 3.2.5 | Organize a workshop to validate the framework of actions | CSI | Experts, resource persons | 2024-05-07 | 2024-05-07 | Not Achieved | [6 empty] | 3 | 2 | 3.2 | 5 | #NAME?
|  | Activité 3.3 | Define a favorable implementation framework | 3.3.1 | Identify the capacities needed to successfully implement the PAT | CSI | Experts, resource persons | 2024-04-01 | 2024-06-30 | Not Achieved | The implementation framework is defined for each technology | Number of action frameworks for each technology | ITUC Archive | xx action framework for each technology | - Unavailability of experts |  | 3 | 3 | 3.3 | 1 | #NAME?
|  |  |  | 3.3.2 | Estimate the cost of identified actions and activities and formulate a budget | CSI | Experts, resource persons | 2024-04-01 | 2024-06-30 | Not Achieved | [6 empty] | 3 | 3 | 3.3 | 2 | #NAME?
|  | Activité 3.4 | Monitor, report and track implementation progress | 3.4.1 | Prepare a contingency and risk management plan | CSI | The experts | 2024-07-01 | 2024-07-31 | Not Achieved | The document of the parameters, the chronology of the reports and the monitoring-evaluationi is available | Number of documents for parameters, chronology of reports and monitoring-evaluation | ITUC Archive | xx parameters xx reports xx monitoring report | - Unavailability of experts |  | 3 | 4 | 3.4 | 1 | #NAME?
|  |  |  | 3.4.2 | Set reporting and tracking parameters and timeline | CSI | The experts | 2024-07-01 | 2024-07-31 | Not Achieved | [6 empty] | 3 | 4 | 3.4 | 2 | #NAME?
|  | Activité 3.5 | Develop strategies to transform and attract private sector investment | 3.5.1 | Develop a roadmap to facilitate the formation of a climate technology market | CSI | Experts, resource persons | 2024-08-01 | 2024-08-31 | Not Achieved | The roadmap is established and validated | Number of roadmaps | ITUC Archive | xx roadmaps | - Unavailability of experts |  | 3 | 5 | 3.5 | 1 | #NAME?
|  |  |  | 3.5.2 | Initiate incentive and penalizing mechanisms to be introduced at the political and regulatory level to promote the transition to the use of clean technologies | CSI | Experts, resource persons | 2024-08-01 | 2024-08-31 | Not Achieved | [6 empty] | 3 | 5 | 3.5 | 2 | #NAME?
|  |  |  | 3.5.3 | Organize a roadmap validation workshop | CSI | Experts, resource persons | 2024-09-03 | 2024-09-03 | Not Achieved | [6 empty] | 3 | 5 | 3.5 | 3 | #NAME?
|  | Activité 3.6 | Develop quality project concept notes to be submitted in the climate windows | 3.6.1 | Identifying viable project ideas emerged from the TAP | CSI | Experts, resource persons | 2024-09-04 | 2024-10-04 | Not Achieved | Concept notes developed | Number of concept notes | ITUC Archive | xx concept notes | - Unavailability of experts - Unavailability of resource persons | 1 | 3 | 6 | 3.6 | 1 | #NAME?
|  |  |  | 3.6.2 | Support the development of up to 4 concept notes based on the TAP | CSI | Experts, resource persons | 2024-09-04 | 2024-10-04 | Not Achieved | [6 empty] | 3 | 6 | 3.6 | 2 | #NAME?
|  | Activité 3.7 | Write the final report of the technology needs assessment and the Technological Action Plan (TAP) | 3.7.1 | Collect and compile all industry reports on technologies | CSI | The experts | 2024-10-05 | 2024-10-31 | Not Achieved | Final report of the technology needs assessment is available | A final report of the technology needs assessment | ITUC Archive | The final report of the technology needs assessment | - Unavailability of experts - Unavailability of resource persons |  | 3 | 7 | 3.7 | 1 | #NAME?
|  |  |  | 3.7.2 | Write the draft report of the technology needs assessment | CSI | The experts | 2024-11-01 | 2024-11-30 | Not Achieved | [6 empty] | 3 | 7 | 3.7 | 2 | #NAME?
|  |  |  | 3.7.3 | Organize a validation workshop for the draft report of the technology needs assessment | OIKO | CSI | 2024-12-04 | 2024-12-06 | Not Achieved | [6 empty] | 3 | 7 | 3.7 | 3 | #NAME?
|  |  |  | 3.7.4 | Organize the policy approval ceremony for the delivery of the final report of the technology needs assessment | OIKO | CSI | 2024-12-19 | 2024-12-19 | Not Achieved | [6 empty] | 3 | 7 | 3.7 | 4 | #NAME?

## ChronoEBT
PROJECT : |  | Guide technique pour la mise à jour de l'évaluation des besoins technologiques (TNA) et l'élaboration d'un plan d'action en technologie pour la mise en œuvre de NDC Côte d'Ivoire
SPECIFIC OBJECTIVES : |  | Develop the Technology Needs Assessment (TEA) report |  |  |  |  | 2023-06-01 | 2023-07-01 | 2023-08-01 | 2023-09-01 | 2023-10-01 | 2023-11-01 | 2023-12-01 | 2024-01-01 | 2024-02-01 | 2024-03-01 | 2024-04-01 | 2024-05-01 | 2024-06-01 | 2024-07-01 | 2024-08-01 | 2024-09-01 | 2024-10-01 | 2024-11-01
Development of Technological Action Plans (PAT)
[7 empty] | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2023 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024 | 2024
[7 empty] | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11
No. | MAIN ACTIVITIES | ACTIVITIES | RESPONSIBLE | DELIVERABLES | START DATE | END DATE | 6: CHRONOGRAM OF ACTIVITIES | COMMENTS
[7 empty] | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18
[7 empty] | 4 | 7 | 4 | 1 | 4 | 1 | 4 | 1 | 5 | 7 | 4 | 7 | 4 | 7 | 4 | 1 | 4 | 1
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
| #N/A |  |  | #N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A
#N/A