## Guidelines
This file contains three specific planning tools to complete the supplementary information required when submitting a proposal for Readiness Programme support (including for NAP/adaptation planning):
- Budget plan and accompany Budget notes - Procurement plan - Implementation plan
The following considerations are important when completing the budget:
1. Before preparing the Readiness and budget, procurement, and implementation plans, please read the full guidance contained in the Readiness Programme Guidebook, specifically Part III Section 5
2. You can select the appropriate budget categories from the dropdown list in the budget plan:
3. To insert additional rows, right click on the row number below where you wish to insert the new row and choose INSERT.
4. Additional budget categories may be added by manually typing them on the Budget Category sheet. :
5. The Budget Notes sheet should be used to record explanations, further details or cost breakdowns for individual lines
Project Management Cost:
Project management costs (PMC) are the direct administrative costs incurred to execute a project. They should cover only incremental costs incurred due to the GCF contribution. In most cases, these costs are directly related to the support of a dedicated project management unit which manages the day to day execution related activities of the project.
General Principles for PMC costs:
1. The percentage of PMC financed by GCF should not be more than the percentage share of the overall budget financed by GCF
2. PMC budget thresholds: Up to 7.5 per cent of total activity budget.
> PMC exceeding 7.5 per cent for the readiness (including NAPs) proposals, and PPF proposals, up to $ 3 million will require detailed documentation
and justification supporting the entire PMC budget.
> The PMC should be shown as a separate component in the project budget. A detailed breakdown of PMC should be provided by budget category.
> Indicative list of eligible project management costs:
> Project staffing and consultants: Project manager, Project Assistant, Procurement personnel, Finance personnel & Support/admin. Personnel
> Other direct costs: Office equipment, Mission related travel cost of the PMU, Project management systems and information technology,
Office supplies, Audit cost
Contingency :
1. Select the appropriate % of Contingency Budget from the dropdown list :
2. Contingency budget for unforeseen costs arising during the project implementation should not be included in the outcome budget separately.
3. Contingency budget must be used for any unforeseen programme (output level) cost that is unrelated to implementation/service fee.
4. Any use of contingency must be reported to and agreed by the GCF Secretariat in writing in advance provided with justifications that are acceptable to the GCF
5. If by the end of the grant implementation period, you have not spent Contingency, you may not increase the scope of the project or make any other expenditures using the Contingency.
If you are unsure about how to complete the budget template, please send your query to: countries@gcfund.org
Readiness Grant Budget Preparation Guidelines

## Budget Category
Budget Categories
Audio Visual, Publication design & Printing
Audit Fee
Consultant - Individual - International
Consultant - Individual - Local
Professional Services – Companies/Firm
IT Equipment
Office Supplies
Travel - International
Travel – Local
Workshop/Training
Stakeholder Awareness Research | Indicate additional budget categories
Concept note development
Choose percentage
0
1%
2%
3%
4%
5%

## 5.1 Budget Plan
5.1 Budget Plan
Please add rows for Outcomes, Outputs and Cost Categories as required. Additional budget categories may be added by manually typing them on the Budget Category sheet.
Outcomes / Outputs |  | Detailed Budget (in US$) | [5 empty] | Total Budget (per outcome) | Expenditure Plan | [5 empty] | Budget notes
|  | Budget Categories choose from the drop-down list | Unit | # of Unit | Unit Cost | Total Budget (per budget category) | Total Budget (per sub-outcome) |  | 6m | 12m | 18m | 24m | 30m | 36m
Outcome 2.2 GCF recipient countries have developed or enhanced strategic frameworks to address policy gaps, improve sectoral expertise, and enhance enabling environments for GCF programming in low-emission investment (2.2) | 2.2.1 Output: National Market Readiness and Implementation Framework (to 2030) which will secure the platform for achieving Pakistan’s longer-term objectives for 2050 and drive investment decisions. | Consultant - Individual - International | W/Day | 80 | 625 | 50000 | 114000 | 190500 | 15000 | 15000 | 20000 |  |  |  | A
|  | Consultant - Individual - Local | W/Day | 120 | 300 | 36000 |  |  | 10000 | 10000 | 16000
|  | Travel - International | Trip | 4 | 1500 | 6000 |  |  | 2000 | 2000 | 2000
|  | Travel – Local | Trip | 60 | 200 | 12000 |  |  | 4000 | 4000 | 4000
|  | Concept note development | Total | 10 | 500 | 5000 |  |  |  | 5000
|  | Audio Visual, Publication design & Printing | Total | 1 | 5000 | 5000 |  |  |  |  | 5000
| 2.2.2 Output: Implementation Roadmap on optimum mix of regulatory, taxation and subsidy instruments to drive deployment of Evs | Consultant - Individual - International | W/Day | 60 | 625 | 37500 | 64500 |  | 37500
|  | Consultant - Individual - Local | W/Day | 90 | 300 | 27000 |  |  | 27000
|  | Audio Visual, Publication design & Printing | Total | 1 | 5000 | 5000 | 12000 |  | 5000
|  | Workshop/Training | Total | 2` | 1500 | 3000 |  |  | 3000
|  | Travel – Local | Trip | 20 | 200 | 4000 |  |  | 4000
Outcome 4.2 An increase in the number of quality funding proposals developed and submitted from accredited Direct Access Entities | 4.2.1 Output: Market feasibility study of eMobility and EV deployment | Consultant - Individual - International | W/Day | 60 | 625 | 37500 | 64500 | 78500 |  | 20000 | 17500
|  | Consultant - Individual - Local | W/Day | 90 | 300 | 27000 |  |  |  | 17000 | 10000
|  | Audio Visual, Publication design & Printing | Total | 1 | 5000 | 5000 | 14000 |  |  |  | 5000
|  | Concept note development | Total | 10 | 500 | 5000 |  |  |  |  | 5000
|  | Travel – Local | Total | 20 | 200 | 4000 |  |  |  |  | 4000
Outcome 5.2 Partnerships established to foster development and dissemination of methods, frameworks, and information systems for enhanced climate finance programming at subnational, national, and regional levels | 5.2.1: Output Enhanced Public Awareness and understanding of the potential of EV, electro-mobility | Consultant - Individual - International | W/Day | 20 | 625 | 12500 | 30500 | 49500 |  | 12500
|  | Consultant - Individual - Local | W/Day | 60 | 300 | 18000 |  |  |  | 18000
|  | Workshop/Training | W/Day | 8 | 1500 | 12000 | 19000 |  |  | 6000 | 6000
|  | Stakeholder Awareness Research | Total | 1 | 5000 | 5000 |  |  |  |  | 5000
|  | Travel – Local | total | 10 | 200 | 2000 |  |  |  | 1000 | 1000
Total Outcome Budget | [7 empty] | 318500 | 107500 | 110500 | 100500 | 0 | 0 | 0 |  | 0
Project Management Cost (PMC) Up to 7.5% of Total Activity Budget |  | Consultant - Individual - International | Days | 30 | 625 | 18750 | Actual amount and % of PMC requested: | Maximum PMC that can be requested:
|  | Audit Fee | Lumpsum | 2 | 2500 | 5000
[6 empty] | 0 | do not change the formula | do not change the formula
[6 empty] | 0 | 23750 | 23887.5
[6 empty] | 0 | 7.457% | 7.5%
FOR GREEN CLIMATE FUND SECRETARIAT'S USE ONLY
Breakdown (per budget category) |  | Total (per budget category)
Audio Visual, Publication design & Printing |  | 15000
Audit Fee |  | 5000 |  |  |  | FOR GREEN CLIMATE FUND SECRETARIAT'S USE ONLY
Consultant - Individual - International |  | 156250
Consultant - Individual - Local |  | 108000 |  |  |  | Total Outcome Budget | [6 empty] | 318500
Professional Services – Companies/Firm |  | 0 |  |  |  | Project Management Cost (PMC) |  | 7.457% | requested |  |  |  | 23750
IT Equipment |  | 0 |  |  |  | Contingency | 5% |  | requested |  |  |  | 15925
Office Supplies |  | 0
Travel - International |  | 6000
Travel – Local |  | 22000 |  |  |  | Sub-Total (Total Outcome Budget + Contingency + PMC) | [6 empty] | 358175
Workshop/Training |  | 15000
Stakeholder Awareness Research |  | 5000 |  |  |  | Delivery Partner Fee (DP) - Up to 8.5% of the Sub-Total | [6 empty] | 30444.875
Concept note development |  | 10000
0 |  | 0
0 |  | 0 |  |  |  | Total Project Budget (Total Activity Budget + Contingency + PMC + DP) | [5 empty] | 388620
0 |  | 0
Total Outcome Budget + PMC |  | 342250
0

## Budget Notes
Budget Note | Detailed Description |  | Outcomes/ Outputs
A | International Climate Change Consultant | Charges at $625 ($500 with 25% Security overhead) per day.
B | Local Climate consultant | Charged at $300 per day.
C | Travel Costs for International Consultant to data gather through stakeholder engagement | Costs of $3,000 per trip for international consultant
E | Local travel costs for local consultant - including local consultant meetings, engagement with individual actors, data collection. | Costs of $200 per trip
F | Workshops on stakeholder policy roadmap development, validation of findings and capacity building | Costed per workshop $1,500 per day | 2.2.2
G | Training on policy roadmap development is for 2 days | Costed per workshop $1,500 per day | 2.2.2
H | Audio-visual and printing of publication (policy roadmap, feasibility study, public sector framework, attitudinal survey ) | Costed per publication $5,000
I | Workshop on public awareness, Report on awareness of electro-mobility- input to increase consumer understanding and public confidence. | Costed per workshop $1,500 per day | 5.2.1
J | Local travel relates to travel costs of delivering workshop | Costed at $200 per day | 5.2.1
K | Concept note development (2 x 10) | Costed per publication $500 | 2.2.1 & 4.2.1

## 5.2 Procurement Plan
5.2 Procurement Plan
For goods, services, and consultancies to be procured, please list the items, descriptions in relation to the activities in Section 3, estimated cost, procurement method, relevant threshold, and the estimated dates. Please include the procurement plan for at least the first tranche of disbursement requested below and provide a full procurement plan for the entire duration of the implementation period if available at this stage.
Item | Item Description | Estimated Cost (US$) | Procurement Method | Thresholds (Min-Max monetary value for which indicated procurement method must be used) | Estimated Start Date | Projected Contracting Date
Goods and Non-Consulting Services
Sub-Total (US$) |  | 0
Consultancy Services
Contract of services to implement the technical assistance for The development of the implementation and regulatory framework for the deployment of electric vehicles in support of Pakistan’s Electric Vehicle Policy (2019) project |  | 388620
Sub-Total (US$) |  | 388620
Note: Included as procurement (contract to network member): activity costs +audit cost
Overall financial management and procurement of goods and services under this readiness and preparatory support proposal will be guided by UN regulations, rules, policies and procedures.
UNEP will be responsible for the implementation of the readiness activities and for procurement and contractual services, as well as reporting on the progress of this implementation in close coordination and strategic guidance from the NDA/FP. The procurement actions and the operational services will be carried forward in accordance with UN policies and procurement guidelines.
25% of executing agency project management cost will be utilized by UNEP/CTCN to provide support to the project execution by completing the following activities throughout the project duration: 1. Preparation of procurement plans 2. Preparation of the project withdrawal requests for disbursement 3. Preparation of TOR and procurement packages 4. Tracking and monitoring of project costs and deliverables to plan 5. Preparation of progress reports and financial management reports
CTCN procedure for procurement: For a request that is eligible and prioritized, the Climate Technology Managers in charge of the respective request sources the appropriate expertise to develop the Terms of Reference of the assistance (called ‘Response Plan’ as per CTCN procedures). The response plan provides specific information on the technical assistance to be delivered, including activities, outputs, expected outcomes and impacts, timeline, indicators or measuring assistance progress and success, stakeholders to be involved, etc. The response plan, once finalized, is signed by the national focal point of the CTCN in the concerned country (National Designated Entity), the institution which originated the CTCN request for technical assistance and the CTCN Director and constitutes the basis of the assistance to be implemented and monitored upon the approval and in cooperation with the NDA. Based on the needs and expertise required in the response plan, a CTCN Network Member will be selected to implement it.
The selection of the institution from the Network of CTCN for the execution of the technical assistance is conducted through a competitive procurement process as per UNEP Rules and Regulations, in line with CTCN procedures and with UN Rules and Regulations (being UNEP the co-host of the CTCN, and a specialized agency established under the UN Charter). The CTCN nurtures a Network of more than 500 expert organizations in the field of low-carbon and climate resilient technologies. The required expertise to carry out the activities that define this intervention will be sourced from the Network. For this, the following four principles shall be given due consideration when undertaking the procurement functions of UNEP:
i. Best value for money principle;
ii. Fairness, accountability, integrity and transparency of the procurement process;
iii. Effective competition;
iv. The best interest of the CTCN.

## 5.3 Implementation Plan
5.3 Implementation Plan
Please list all the deliverables (e.g. D.1.1.1a) per activity (e.g. A1.1.1) with the identifierand mark the planned duration as show in the example. Please also indicate milestones for any deliverables to be completed during the implementation period of the activity in question.
Make sure the identifier number of each activity and deliverable matches with the proposal as this table does not require its name or description. Please refrain from adding descriptions.
For more guidance on how to fill out this tables, please see Part III Section 5 of the Readiness Guidebook
|  |  | Planned duration | [6 empty] | Milestone (deliverable) | [7 empty] | Target completion date
Activities & Deliverables |  | Estimated Timeline
|  | M1 | M2 | M3 | M4 | M5 | M6 | M7 | M8 | M9 | M10 | M11 | M12 | M13 | M14 | M15 | M16 | M17 | M18 | M19 | M20 | M21 | M22 | M23 | M24 | M25 | M26 | M27 | M28 | M29 | M30 | M31 | M32 | M33 | M34 | M35 | M36
Reporting
EXAMPLE
Supporting the improvement of low emission vehicle market readiness assessment, including measures, regulatory frameworks and investment decisions. | Activity 2.2.1a | bar: Estimated Timeline M1 to Estimated Timeline M18
National Market Readiness and Implementation Framework (to 2030) | Deliverable 2.2.1a | bar: Estimated Timeline M16
Developing a number of concept notes for recommendations and priority actions | Activity 2.2.1b | bar: Estimated Timeline M4 to Estimated Timeline M7
Finalized concept notes (10) | Deliverable 2.2.1b | bar: Estimated Timeline M7
Implementation Roadmap on optimum mix of regulatory, taxation and subsidy instruments to drive deployment of Evs | Activity 2.2.2a | bar: Estimated Timeline M1 to Estimated Timeline M6
Finalized Implementation roadmap | Deliverable 2.2.2a | bar: Estimated Timeline M6
Validation of the roadmap by key stakeholders in a series of workshops | Activity 2.2.2b | bar: Estimated Timeline M3 to Estimated Timeline M5
Finalized consultation workshop report. | Deliverable 2.2.2b | bar: Estimated Timeline M5
Investigation of public procurement framework and steps to decarbonize the public transport fleet. | Activity 2.2.2c | bar: Estimated Timeline M7 to Estimated Timeline M10
Finalized public sector framework | Deliverable 2.2.2c | bar: Estimated Timeline M10
Assessing and incorporating the feasibility of technology supports and measures identified in the Implementation Framework and Market Readiness report. | Activity 4.2.1a | bar: Estimated Timeline M10 to Estimated Timeline M16
Finalized feasibility study on electro-mobility options | Deliverable 4.2.1a | bar: Estimated Timeline M16
Feasibility project concept notes ideas | Activity 4.2.1b | bar: Estimated Timeline M13 to Estimated Timeline M16
Finalized Concept notes | Deliverable 4.2.1b | bar: Estimated Timeline M16
Disseminating information and awareness raising material. | Activity 5.2.1a | bar: Estimated Timeline M7 to Estimated Timeline M18
Finalized Public Awareness Programme | Deliverable 5.2.1a | bar: Estimated Timeline M12
Finalized consultation workshop report | Deliverable 5.2.1b | bar: Estimated Timeline M13
Report on awareness of electro-mobility- input to increase consumer understanding and public confidence. | Deliverable 5.2.1c | bar: Estimated Timeline M15