## Slide 1
Zephyr Consulting | Omar Saleh The Netherlands, February 2024
PROJECT KICK-OFF
“RAINWATER HARVESTING”
Provision of technical assistance for the development of the locally led technology transfer action plan and a blueprint for action for the uptake of rainwater harvesting system at the local level in Pakistan.

## Slide 2
Table of Contents
Project Overview 2
Project Approach 4
Project Deliverables 5
Project Planning 6
Project Organisation 7
Project Risks 9
Annexes

## Slide 3: Project Overview (1/2)
1. Background and Introduction
Freshwater resources in Pakistan are under substantial stress due to growing population, urbanization, and unplanned land use. Water scarcity is expected to result in a wide range of socio-economic and environmental effects in Pakistan, especially impacting vulnerable communities including women and children.
While the application of rainwater harvesting system is important for sustainable water supply to local communities, there are barriers and limited capacity in identifying, deploying, and operating suitable technologies for the system at the local level.
A Consortium of organisations led by Zephyr Consulting, including PCRWR, WaterSprint will implement a Technical Assistance to assess and select innovative rainwater harvesting system(s)/approaches at the local level in Pakistan. Central to this initiative is the creation of a locally led technology transfer action plan and a blueprint for action, which focuses on the uptake of the best and innovative rainwater harvesting technologies.
2. Project Goal
The overall goal is to enhance water security and climate resilience in a targeted local area in Pakistan through the implementation of a locally led innovative rainwater harvesting system/approach. The project will create a technology transfer action plan and a blueprint for action, facilitating the uptake and sustainable operation of the rainwater harvesting system.
3. Scope
In scope of this project
Area and stakeholder selection.
Rainwater harvesting technology selection or design.
Action plan and blueprint development.
Capacity building and awareness raising.
Out of scope of this project
Piloting a new rainwater harvesting system at a large scale.

## Slide 4: Project Overview (2/2)
4. Project Requirements
In order to enhance water security and realise overarching goal and subsequent objectives, the project must:
Identify the target local areas where the rainwater harvesting system will be deployed.
Identify the stakeholders who will be involved in the project.
Identify best practices and technologies for rainwater harvesting.
Design/select innovative rainwater harvesting system/approach.
Develop a locally-led technology transfer action plan.
Develop a blueprint for action focused on rainwater harvesting.
Provide capacity building and awareness-raising activities.
The participation and interests of women shall be incorporated throughout the project.
5. Proposed Solution
The proposed solution for the objective of the project is to develop a locally led technology transfer action plan and a blueprint for action that focuses on the uptake of an innovative rainwater harvesting system(s) at the local level in Pakistan.
6. Key Project Deliverables
Identified local areas where the rainwater harvesting system(s) will be deployed.
Identified key stakeholders who will be involved in the project.
Identified best practices and technologies for innovative rainwater harvesting.
Locally-led technology transfer action plan.
Blueprint for action centered around a rainwater harvesting system.
Well-trained people, including adequate participation of women.
Enhanced climate resilience in the water sector with at the forefront the interests of vulnerable groups including women and youth.
7. Impact Project
Customized and adoption of rainwater harvesting technology tailored to local needs.
Strengthened local ownership and accountability for sustainable water management.
Enabled rapid deployment and replication of the system in other vulnerable areas.
Enhanced skills and awareness for sustainable water use and climate adaptation.
Increased ability to withstand climate-related shocks and stresses of the water sector.
Long-term sustainable and resilient who have a stable water supply.
Contribution to SDGs: 5, 6, 8, 11 and 13

## Slide 5: Project Approach
Target areas and stakeholders
Report stakeholder consultations
Report climate / water analysis
Selected project area(s)
Identified stakeholders selected area(s)
Locally led action plan
Stakeholder meetings
Final technology transfer action plan
Blueprint for action
Draft Concept Note (GCF / GEF)
Project closure
Final M&E plan
Impact statement
Project closure meeting / report
Project inception
Project Initiation Documentation (PID)
Kick-off meeting with the client
Finalise implementation plan
Draft M&E and Closure Report
Rainwater harvesting technology
Site visits and stakeholder consultations
Enumeration rainwater harvesting systems
Technical design newly developed system
Final proposed rainwater harvesting system
Capacity building and awareness raising
Capacity needs assessment
Stakeholder engagement plan
Communication materials
Capacity building workshop
1
2
3
4
5
6
[ The project approach comprises of six phases / work packages ]

## Slide 6: Key Project Deliverables
Task | Deliverable | Timeline
Phase 1 – Project inception |  | 
Prepare PID | Project Initiation Documentation (PID) | Week 15
Kick-off meeting | Kick-off meeting with the client | Week 15
Finalise PID | Finalise implementation plan | Week 16
Prepare M&E and Closure | Draft M&E and Closure Report | Week 16
Phase 2 – Target areas and stakeholders |  | 
Conduct consultations | Report stakeholder consultations | Week 18
Review CC impacts | Report climate / water analysis | Week 20
Assess and select area(s) | Selected project area(s) | Week 20
Identify stakeholders | Identified stakeholders selected area(s) | Week 20
Phase 3 – Rainwater harvesting technology |  | 
Visit sites and consultations | Site visits and stakeholder consultations | Week 24
Assess rainwater systems | Enumeration rainwater harvesting systems | Week 24
Develop technical design | Technical design innovative system | Week 28
Identify stakeholders | Identified stakeholders selected area(s) | Week 28
Task | Deliverable | Timeline
Phase 4 – Locally led action plan |  | 
Consult stakeholders | Stakeholder meetings | Week 32
Finalise transfer action plan | Final technology transfer action plan | Week 34
Develop blueprint for action | Blueprint for action | Week 40
Develop concept note | Draft Concept Note (GCF / GEF) | Week 48
Phase 5 – Capacity building and awareness raising |  | 
Conduct needs assessment | Capacity needs assessment | Week 45
Develop engagement plan | Stakeholder engagement plan | Week 45
Develop communications | Communication materials | Week 45
Conduct capacity building | Capacity building workshop | Week 46
Phase 6 – Project closure |  | 
Finalise M&E plan | Final M&E plan | Week 52
Develop impact statement | Impact statement | Week 52
Finalise closure report | Closure report | Week 52

## Slide 7: Project Planning
High-Level Gantt chart (Oct. 2023 to Oct. 2024) |  |  |  |  |  |  |  | 
Feb-24 | Mar-24 | Apr-24 | May-24 | Jun-24 | Jul-24 | Aug-24 | Sep-24 | Oct-24
PID
Kick-off
Final M&E plan
Impact statement
Project Closure
Design principles
Transfer action plan
CC / Water Analysis
Selected areas/stakeholders
Selected / designed rainwater harvesting system
Blueprint for action
Concept Note [GCF/GEF]
28 February 2024

## Slide 8: Project Organisation (1/2)
Bilal Siddiq (I2)
Supplier / User
Naveed Alam (I3)
Senior Supplier
CTCN / UNEP Rep.
Senior User
Omar Saleh (I1)
Project Manager
Lillian Kalela
Senior Consultant
Muhammad Abid (N2)
Water Expert
Rizwana Wariach (N1)
Gender Expert
Bilal Siddiq (I2)
Rainwater Expert
Steering Committee (SC)
Has final responsibility for the project outcome
Ensures coherent steering of the project
Delegates decisions & tasks effectively
Convenes once every six weeks
Project Management
Is central point for daily lead of the project
Is responsible for proper project execution
Ensures collaboration between team members
Heads delivery team meeting and guides SC
Project Delivery Team
Delivers project results according to planning
Actively collaborates
Adheres to decisions made by the SC
Convenes once every week
Target Areas Reps.*
SMEs
Naveed Alam (I3)
Technology Expert
PCRWR
Executive / Senior User

## Slide 9: Project Organisation (2/2)
Project Team’s Roles & Responsibilities |  |  | 
Project Team Member |  | Role | Responsibilities
1 | Dr. Saima Shafique | Final responsibility | Is the client who is ultimately responsible for a successful outcome of the project. In addition, they determine the requirements based on which the project is deemed successful or not.
2 | UNEP / CTCN representative | Client | Is the sponsor of the project and shall also determine the requirements based on which the project is deemed successful or not.
3 | PCRWR expert | Client / Resource provider | Is responsible for providing resources (staff) and for determining the requirements based on which the project is deemed successful or not.
4 | Dr. Naveed Alam | Resource provider | Is responsible for providing resources (staff) to meet the requirements set forth by the co-users whilst ensuring that the project stays within budget, time and according to the agreed quality standards.
4 | Omar Saleh | Project manager | Is central point for daily lead of the project and is authorised to execute the project on behalf of the steering committee.
5 | Lilian Kalela | Senior consultant | Support the project manager.
6 | Naveed Alam | Water technology expert | Is responsible for conducting stakeholder engagement and to develop a roadmap including promotion of blueprint of the new rainwater harvesting system.
7 | Muhammad Abid | Water export | Is responsible for capacity needs assessment and capacity building programs and implementing transfer technology plans.
8 | Rizwana Wariach | Gender expert | Is responsible for representing the interests of women and other vulnerable groups in the project to contribute to gender equality in Pakistan
9 | Bilal Siddiq | Rainwater harvesting expert | Is responsible for providing expertise to select/design the best possible rainwater harvesting system in line with the requirements by the design principles and the user panel.

## Slide 10: Project Risks (1/4)
Key Risks |  |  |  |  |  | 
# | Risk Description | Chance | Impact | Mitigation | PTA* | Due date
R1 | Risk that Pakistan is used as a tax haven during the project | L | H | The Consortium to pay extra attention to its tax and transfer pricing policy and that of its suppliers. | TBD | TBD
R2 | Risk that we encounter bribery and other corrupt practices | M | H | Send the recommendations of the OECD guidelines to the project team incl. staff and instruct full adherence Have procedure on what to do in case of corruption attempt Screen our partners and suppliers | TBD | TBD
R3 | Risk that there is inadequate supply of infrastructure, corruption, and access to financing to support the project. | M | H | See also mitigation R2 Arrange appropriate infrastructure and water supply with the local government / flood response team | TBD | TBD
R4 | Civil liberties of anyone involved in the project are impeded because of the regime | L | H | See also mitigation R2 Ensure availability of communication line to independent organisations | TBD | TBD
R5 | Political risks, such as conflicts, lead to a cancelation or postponed of the project | M | H | See also mitigation R2 – R4 Actively keep track of any developments in political risks throughout the project | TBD | TBD
R6 | Risk that we encounter terrorism attack | L | M | See also R5 Follow the recommendations of the UN Global Compact initiative (chapter 3, from p. 18). | TBD | TBD
[ * PTA = Person To Act ]

## Slide 11: Project Risks (2/4)
Key Risks |  |  |  |  |  | 
# | Risk Description | Chance | Impact | Mitigation | PTA | Due date
R7 | Risk that we are involved in or enable land grabbing | L | M | Follow a participatory approach when developing a blueprint and the concept note Stay in contact with the local community to monitor whether land grabbing takes place and have representatives in the project team | TBD | TBD
R8 | Risk that our project leads to damage to the environment and forced displacement of children as a result of land acquisition. | L | M | See also R7 Monitor and quantify the benefits of our project Conduct ESIA when developing a full proposal to rollout the blueprint | TBD | TBD
R9 | Risk that union / workers’ rights are violated | L | L | Follow the following recommendations of CNV International (chapter 3). Screen out partners and suppliers | TBD | TBD
R10 | Risk that the project is involved in or enables forced labor or human trafficking | L | H | Project team to follow the e-learning courses offered by Verité on forced labour and human trafficking. | TBD | TBD
R11 | Risk that the project is involved in or enables child labor | L | H | Follow the practical ILO steps and follow the Ethical Trade Initiative guide | TBD | TBD
R12 | Risk that this project is involved in or enables gender / religious discrimination | L | H | Involve gender expert in the project Keep contact with the local community incl. religious groups Ensure women are represented throughout the project | TBD | TBD
R13 | Risk that our project leads to damage to the environment such as deforestation | L | M | Conduct ESIA when developing a full proposal to rollout the blueprint Determine negative impact of the rainwater harvesting system | TBD | TBD

## Slide 12: Project Risks (3/4)
Key Risks |  |  |  |  |  | 
# | Risk Description | Chance | Impact | Mitigation | PTA | Due date
R14 | Risk that there we cannot select or design an appropriate rainwater harvesting system | M | H | Involve experts in rainwater harvesting systems and in members familiar with Pakistan Involve local beneficiaries and co-design the system Involve technology experts and experts in mobile barriers Test any newly designed rainwater harvesting systems | TBD | TBD
R15 | Risk that we lack financial resources to complete the project | M | H | Develop a detailed budget and monitor spendings and timely escalate in case of budget overruns | TBD | TBD
R16 | Risk we don’t get sufficient input from local beneficiaries | M | H | Involve a strong local partner in the project Include local beneficiaries in the project organisation Ensure frequent visits to ensure contact with beneficiaries | TBD | TBD
R17 | Risk that it will a long time before scale-up / implementation of the blueprint / concept note will take place | H | H | Select the best approach for funding the concept note / rollout of the blueprint across Pakistan Involve donors in a timely manner | TBD | TBD
R18 | Risk there is misalignment regarding the expected outcomes or tasks of the project | M | H | Establish a clear organisation with clear responsibilities Ensure frequent project team meetings | TBD | TBD
R19 | Risk project members are not available due to busy agendas | M | H | Ensure availability of the project members Establish back-ups in case project members are not available | TBD | TBD
R20 | Risk that the rainwater harvesting system is too costly for future scale-up | M | H | Select / design a rainwater harvesting system that is affordable | TBD | TBD
R21 | Risk that the wrong target locations are selected to implement the project | M | H | Develop selection criteria for the target locations Involve representatives of the selected target locations in the project | TBD | TBD

## Slide 13: Project Risks (4/4)
Key Risks |  |  |  |  |  | 
# | Risk Description | Chance | Impact | Mitigation | PTA | Due date
R22 | Risk that women are insufficiently involved in or benefiting from the implementation of this project | M | H | Set clear targets for women related to participation and project benefits. Involve a gender expert who keeps track of inclusion of women and women’s interests in the project activities. Ensure women are represented in the project organisation including the Steering Committee. | TBD | TBD