## Slide 1: Project Meeting – Raindrop Provision of technical assistance for the development of the locally led technology transfer action plan and a blueprint for action for the uptake of rainwater harvesting system at the local level in Pakistan. Week 6 10 April 2024

## Slide 2: Minutes (1/2)
Minutes
Minutes previous meeting
Action list
Project issues and risks
Project planning
Any other business
Opening
Omar opened the meeting and welcomed participants.
Action List
P2.1: NA and MA presented the different sites they included in their completed location selection matrices (see Annex 1). Each site has a score for each determinant based on which we prioritise the different sites to develop a blueprint and technology transfer plan. NA mentioned he has already discussed this project with a contact at Aitchison College, being one of the possible sites in the location selection matrix. He expressed his interest in having the Aitchison College as the selected site for this project. Should we select this project site, we need to prepare an email that he will send to the board to obtain a formal approval. NA emphasized that by selecting the Aitchison College, we can have access to students who can be an important resource for this project.
Continuing with the location matrix, NA mentioned that site L1 (P&D Department) is a 5-story building making it challenging to implement an innovative rainwater harvesting technology/approach. Site L2 (Government College University) is challenging to reach seeing as it’s a rather congested area. NA explains that site L3 (Aitchison College) is highly suitable as this is a large area in the centre of Lahore and highly suitable to implement the rainwater harvesting technology. This area also has a lot of options to repurpose the harnessed rainwater such as injection in the ground.
MA agrees with the commentary and recommendations provided by NA regarding his input on the location selection matrix. BS agreed as well and added that the Punjab local government academy is also a good option. RW also agrees with the commentary by NA but suggested we could also select an all-women college such as Lahore College for Women. That particular college lies in a rather congested area according to NA and might therefore not be the best option. NA did mention that Kinnaird College For Women might be a suitable option. In any case, all members agree that it would be good to involve women of these colleges in the project in order for them to learn about the project possibly as part of an internship.
MA enlightened his input in the location selection matrix (see Annex 1). Sites L2 (Hocky Stadium) and L3 (Gaddafi Cricket Stadium) could be good options. These sites have storage tanks underground and could use the stored water; however, it might be difficult to get permission from the stakeholders.

## Slide 3: Minutes (2/2)
Minutes
Minutes previous meeting
Action list
Project issues and risks
Project planning
Any other business
P2.1 (continued): MA added that L5 (University of the Punjab – New Campus) is also a good option just like L7 (Government College University). MA included various town areas (L8 – L11) as possible sites. He confirmed these are low-lying areas that have storage tanks to store stormwater. NA and other members agree that the town areas (L8 – L11) might be challenging as there are approvals needed by the governmental organisation WASA, who are not known to be the easiest organisations to work with. Project team members agree with the commentary provided by MA.
OS explained that we can select more than one sites to target, we could have one primary site and a secondary site. It would be best to select two sites that have different conditions as this would benefits the concept note and the intention to scale-up future projects.
In conclusion: members agree to have (1) Aitchison College as the first site for the project and the (2) Agricultural Department in Renala Khurd as the second location. The second site is highly visible and suitable to implement an innovative rainwater harvesting technology/approach.
P3.1 – P3.3: OS explained we can start with these actions once the steering committee approves the selected locations.
Issues and Risks
N/A
AOB
NA asked whether he should contact WaterAid; OS answered yes. [Action] NA will contact WaterAid and inform them of the project.
MA explained we should add an action in the action list aimed at asking permission from local stakeholders at the selected project sites to implement the project; OS agrees. [Action] OS will add action in the action list.
NA recommended to contact his formal colleague from the Technical University of Delft who might contribute to the development of an innovative rainwater harvesting technology. [Action] OS to contact the recommended contact from NA.

## Slide 4: Action List
Action List
Minutes previous meeting
Action list
Project issues and risks
Project planning
Any other business
No. | Feature / Action | PTA | Prio | Due Date | Status | Comment
Sprint 2 |  |  |  | 17 Apr. 2024 |  | 
P2.1 | Select location(s) to develop a locally led technology transfer action plan. | All | Critical | 27 Mar. 2024 | In Progress | Two sites have been selected by the project delivery team
P2.2 | Identify stakeholders of the selected location(s). | NA | High | 17 Apr. 2024 | In Progress | 
Sprint 3 |  |  |  | 02 May 2024 |  | 
P3.1 | Assess the climate change impacts on water resources at the selected location(s). | NA | High | 24 Apr. 2024 | Not Started | 
P3.2 | Assess rainwater harvesting technologies/approaches at the selected location(s). | BS | High | 24 Apr. 2024 | Not Started | 
P3.3 | Conduct stakeholder meeting with the identified stakeholders at the selected location(s). | AM | High | 02 May 2024 | Not Started | 
P3.4 | Request permission from relevant stakeholders at the selected project sites | NA | High | 02 May 2024 | In Progress | 
Sprint 4 |  |  |  | 16 May 2024 |  | 
P4.1 |  |  |  |  |  | 
P4.2 |  |  |  |  |  | 

## Slide 5: Project Issues and Risks
Issues/Risks
Minutes previous meeting
Action list
Project issues and risks
Project planning
Any other business
1. Key Issues and Risks about to materialize |  |  |  |  |  | 
# | Issue Description | Prio. | Impact | Mitigation | PTA | Due date
I1 |  |  |  |  |  | 
I2 |  |  |  |  |  | 
I3 |  |  |  |  |  | 
I4 |  |  |  |  |  | 

## Slide 6: Project Planning
Planning
Minutes previous meeting
Action list
Project issues and risks
Project planning
Any other business
10 April 2024

## Slide 7: Any Other Business
AOB
Minutes previous meeting
Action list
Project issues and risks
Project planning
Any other business
NA asked whether he should contact WaterAid; OS answered yes. [Action] NA will contact WaterAid and inform them of the project.
MA explained we should add an action in the action list aimed at asking permission from local stakeholders at the selected project sites to implement the project; OS agrees. [Action] OS will add action in the action list.
NA recommended to contact his formal colleague from the Technical University of Delft who might contribute to the development of an innovative rainwater harvesting technology. [Action] OS to contact the recommended contact from NA.

## Slide 8: Annex 1: Location Decision Matrix (Naveed Alam)
Annex 1
Location Decision Matrix
1. Target Areas Selection in Lahore |  |  |  |  |  |  | 
# | Name Location | Site Suitability | Potential Impact | Priority Government | Support Stakeholders | Visibility | Ease to Implement
L1 | P&D Department | 3 | 4 | 4 | 4 | 5 | 3
L2 | Government College University | 4 | 4 | 4 | 3 | 4 | 3
L3 | Aitchison College | 5 | 5 | 4 | 4 | 5 | 4
L4 | Airport | 3 | 4 | 4 | 2 | 3 | 2
L5 | Any other suitable government department (Punjab Agriculture or Irrigation or their engineering academy) | 4 | 4 | 4 | 4 | 5 | 4

## Slide 9: Annex 1: Location Decision Matrix (Muhammad Abid)
Annex 1
Location Decision Matrix
1. Target Areas Selection in Lahore |  |  |  |  |  |  | 
# | Name Location | Site Suitability | Potential Impact | Priority Government | Support Stakeholders | Visibility | Ease to Implement
L1 | P&D Department | 3 | 3 | 4 | 4 | 2 | 3
L2 | Gaddafi Cricket Stadium | 3 | 3 | 3 | 4 | 2 | 3
L3 | Hockey Stadium | 3 | 3 | 3 | 4 | 2 | 3
L4 | Airport | 4 | 4 | 4 | 2 | 4 | 4
L5 | University of the Punjab (New Campus) | 4 | 4 | 4 | 4 | 4 | 4
L6 | Atchison College | 4 | 4 | 4 | 4 | 4 | 4
L7 | Government College University | 3 | 3 | 3 | 4 | 2 | 2
L8 | Wagha Town | 4 | 4 | 4 | 4 | 3 | 3
L9 | Shalimar Town | 4 | 4 | 4 | 4 | 3 | 3
L10 | Ravi Town | 4 | 4 | 4 | 4 | 3 | 3
L11 | Iqbal Town | 4 | 4 | 4 | 4 | 4 | 4