## Monitoring & Evaluation (M&E) Plan and Impact Statement

Objective of the M&E Plan and Impact Statement:

- The M&E Plan and Impact Statement must be designed based on the Technical Assistance Response Plan and must enable the Implementer to complete the Closure Report at the end of the assistance.

Process for filling in the template:

- The Implementer must identify relevant quantitative and qualitative indicators as specified in the Closure Report. A sub-set of indicators to monitor and assess must be chosen among these.

- The Implementer may also identify other specific, measurable, achievable, relevant, and time-bound indicators suitable to monitor Activities, Outputs and anticipated Outcomes from the technical assistance and add to the M&E Plan and Impact Statement.

- During implementation of the TA or FTA, the Implementer must collect all relevant data as described in the Monitoring & Evaluation Plan. Aggregated data on selected indicators as well as an updated version of the Impact Statement will be presented in the Closure Report at the end of the assistance.

| Basic Information |  |
| --- | --- |
| Title of response plan | EC-CTCN Climate Change and Security Programme, Organic waste management project, targeting women and young people in particular, using inflatable tanks |
| Technical assistance reference number | CTCN-24/009 |
| Country/ countries | Haiti |
| NDE focal point and organisation | Direction Changements Climatiques du Ministère de l'Environnement (MdE-Haïti), Yves Bernard Remarais, Point Focal CTCN, ybremarais@gmail.com , Parc Industriel (SONAPI), Boulevard Toussaint Louverture, Port-au-Prince, HAÏTI |
| Sector(s) addressed | Renewable Energy Agro-industry Resilience |
| Technologies supported | Inflatable Biodigester |
| Implementation period and total duration | The project duration from July 2024 to October 2025 spans approximately 16 months in total |
| Total budget for implementation | Up to USD 180,000.00 |
| Designer of the response plan | Caribbean Centre for Renewable Energy and Energy Efficiency (CCREEE) |
| Implementer of response plan | - Caribbean Centre for Renewable Energy and Energy Efficiency (CCREEE)), - Local Consultant to be confirmed - Ministère de l'Environnement (MdE-Haïti) |

## Activity 1.3: Monitoring and Evaluation Plan

| (A) Outputs and Activities as described in the Response Plan | (B) Indicator | (C) Expected results | (D) Method and frequency for data collection | (F) Comments |
| --- | --- | --- | --- | --- |
| Output 1: Development of Response Plan, implementation planning and communication documents | Set of planning documents submitted to set the project baseline and establish a reference for project evaluation | 1 full set of planning documents submitted to set the project baseline and establish a reference for project evaluation | Prepare and submit to CTCN as part of project reporting | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 1.1: Development of detailed Response Plan | Detailed Plan | Detailed Plan submitted | Prepare and submit to CTCN as part of project reporting | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 1.2: Development of implementation plan of all activities, deliverables, outputs, deadlines, and responsible persons/ organizations, including a detailed budget | Detailed Plan | Detailed Plan submitted | Prepare and submit to CTCN as part of project reporting | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 1.3: Development of the monitoring and evaluation plan for the implementation of assistance | M&E plan including core indicators - Number of climate related- conflict -affected countries benefiting from the action. #Target value: 1 - Anticipated number of beneficiaries as a result of technical assistance #Target value: Number of direct beneficiaries: 1500 Number of indirect beneficiaries: 10000 % of women: 50% % of youth: 25% - Number of participants in the kickoff meeting by gender #Target value: 10 disaggregated by gender | M&E plan submitted | Prepare and submit to CTCN as part of project reporting | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 1.4: Description of Expected Impacts | Impact description document | Impact description document submitted | Prepare and submit to CTCN as part of project reporting | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Preparation of the closing and data collection report | Closing and Data Collection Report | Closing and Data Collection Report submitted | Prepare and submit to CTCN as part of project reporting | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Output 2: Report on Needs assessment and definition of specifications for inflatable biodigesters | Community needs baseline, and impact assessment | Needs assessment and definition of specifications for inflatable biodigesters submitted | Document submitted to CTCN for consideration | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 2.1: Creation of a restricted working group and organization of technical assistance kick-off meeting. | Restricted working group composition Meeting report | Diversity of institutions to ensure a multi stakeholders’ approach and gender balance Kick-off meeting report submitted | Screening of the composition and functions of SC representatives highlighting gender composition | N/A |
| Activity 2.2: Diagnosis of the technologies used by the commune of Kenscoff in its agricultural production. | Baseline definition document | Baseline definition document submitted | Document submitted to CTCN for consideration | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 2.3: Definition of the community's needs in terms of biogas production | Community biogas needs document | Community biogas needs document submitted | Document submitted to CTCN for consideration | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 2.4: Defining the impact the biodigester could have on the community. | Biodigester Impact document | Biodigester Impact document submitted | Document submitted to CTCN for consideration | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 2.5 Minutes of the validation workshop | Meeting minutes | Meeting minutes submitted | Prepare and submit to CTCN as part of project reporting | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Output 3: Definition of biodigester system architecture |  |  | Document submitted to CTCN for consideration | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 3.1: Analysis of existing biodigester technologies available in Haiti or in the region | Number of existing biodigester technologies analysed | At least 3 biodigester technologies in Haiti or the region analysed. | Identification of the list of biodigester technologies | N/A |
| Activity 3.2 Cost study of the technologies identified in the previous activity. | Cost study document | Cost study document submitted | Document submitted to CTCN for consideration | N/A |
| Activity 3.3 Meeting report with photos, presentations used and list of participants by gender/youth and vulnerable population. | Meeting report | Meeting report submitted | Prepare and submit to CTCN as part of project reporting | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 3.4 Complete architecture of the biodigester system adapted to the needs of the pilot commune, and presentation of a financing | System architecture document | System architecture document submitted | Document submitted to CTCN for consideration | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 3.5: System architecture and business model presentation workshop | Number of participants in system architecture and business model workshop | At least 30 participants ensuring a minimum representation of 30% women and 20% from the pilot community | Headcount and screening of the participants lists | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 3.6: Signing of a letter of commitment by the Ministry of the Environment and the representative of the commune of Fessard | Letter of commitment | Letter of commitment signed | Draft and submit to CTCN as part of project reporting | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Output 4: Biodigester system control and liquid fertilizer generation | Number of instances/processes in which groups collaborate with other partners to initiate and disseminate new technologies which address climate-related risks to peace and security | At least 2 training workshops conducted to initiate and disseminate new technologies | Headcount and screening of the participants lists | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 4.1: Deployment of selected technology in the commune of Fessard | Number of conflict sensitive climate change technological solutions | Conflict sensitive climate change technological solutions deployed | Count and specifications of conflict sensitive climate change technological solutions in the community | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 4.2: Demonstration workshop at the commune of Fessard | Number of participants in system demonstration workshop | At least 30 participants ensuring a minimum representation of 30% women and 20% from the pilot community | Headcount and screening of the participants lists | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 4.3: Organization of continuous training workshops | Number of training workshops Number of participants in continuous training workshops | At least 2 training workshops conducted At least 10 participants in each workshop ensuring a minimum representation of 30% women and 20% from the pilot community | Headcount and screening of participants for the two (2) training workshops | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 4.4: Review of project impact | Photos, videos, reports, and interviews with community users | At least 10 community members interviewed. | Identification of the list of relevant community members Development and deployment of a questionnaire for reviewing project impact Conducting one-to-one and focus group interviews | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Output 5: Communicating and creating an environment conducive to the deployment of biodigester technology on a larger scale. |  |  | Prepare and submit to CTCN as part of project reporting | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |
| Activity 5.1 Definition and deployment of communications strategy | Communications strategy document | Communications strategy document submitted | Prepare and submit to CTCN as part of project reporting | N/A |
| Activity 5.2 Roadmap for the development of a private sector for the production and marketing of biodigesters in Haiti | Roadmap | Roadmap submitted | Prepare and submit to CTCN as part of project reporting | Unforeseen situation may lead to delays in the submission All necessary efforts shall be made to ensure submission without affecting overall project timeline |

Note: The information in the table below will be used by the CTCN for public communication of the achieved and expected results of the Technical Assistance through the CTCN website www.ctc-n.org and other communication channels. See for example: https://www.ctc-n.org/sites/www.ctc-n.org/files/benin_a_ag_forestry.final_.pdf

## Activity 1.4: Impact Description (initial version)

| Impact Statement |  |
| --- | --- |
| Challenge | - Infrastructure limitations in rural areas: Limited access to organic fertilizer and clean cooking fuel due to underdeveloped supply chains and lack of proper waste management systems. - Security issues: Concerns regarding safety and stability in the project area, which can affect access to resources, community participation, and long-term sustainability of the intervention. - Rural population commitment: Encouraging continuous community engagement and participation, given existing socio-economic challenges and competing daily priorities. - Potential deficiencies in installed inflatable biodigester: Ensuring effective operation and maintenance of biodigesters in a setting where technical expertise and repair services are limited. - Effective stakeholder engagement: Addressing hesitancy from local authorities, farmers, and community members by demonstrating the benefits and reliability of biodigester technology. - Sustained funding and support: Securing ongoing financial and institutional backing to ensure that the project extends beyond initial technical assistance, particularly in a volatile economic and political climate. |
| CTCN assistance | Continued support from CTCN will be critical in - Fostering partnerships and collaborations among governments, the CCREEE team, and other stakeholders is essential for ensuring the project's success. - Knowledge Sharing, including facilitating knowledge exchange and best practices among stakeholders to foster innovation and adaptation. - Enhancing visibility and credibility through active communication necessary to attract additional funding for project sustainability and expansion |
| Anticipated impact | The project's overarching objectives are to promote sustainable development, enhance resilience to climate change impacts, and foster environmental stewardship in regions facing security challenges in Haiti. By focusing on economic diversification and improved energy security and clean cooking outcomes, the project aims to address critical socio-economic and environmental challenges while advancing climate action goals. The project will contribute to Core Impact Indicator 2: Anticipated increased economic, health, well-being, infrastructure, and built environment, and ecosystems resilience to climate change impacts as a result of technical assistance through: - Resilience of Vulnerable Economic Sectors: Diversification of livelihoods and reduced dependence on climate-sensitive sectors through sustainable biogas energy solutions. Creation of economic opportunities by integrating biogas production into local enterprises, supporting entrepreneurship, and promoting job creation in biodigester construction, maintenance, and organic fertilizer distribution. Encouraging the development of a private sector for biodigester production and marketing, ensuring long-term economic sustainability. - Resilience of Food Systems and Food Security: Enhanced agricultural productivity by improving soil health through the use of bio-slurry, a nutrient-rich organic fertilizer. Increased energy access for food processing and preservation, reducing post-harvest losses and improving food security. Reduced reliance on expensive and environmentally damaging fertilizers, making farming more affordable and sustainable for local communities. Supporting climate-smart agriculture initiatives that integrate renewable energy and sustainable farming practices. - Public Health Benefits: Reduction in indoor air pollution by replacing traditional biomass-based cooking fuels, significantly improving respiratory health, especially for women and children. Decreased exposure to harmful pollutants from open-fire cooking, leading to long-term health improvements in the community. - Educational and Training Benefits: Empowerment of local communities through continuous training on biogas usage, system maintenance, and waste-to-energy solutions. Increased technical capacity within the community to ensure long-term sustainability and self-sufficiency in operating the biodigester systems. - Environmental Resilience: Reduced deforestation and erosion by lowering dependence on firewood as an energy source. Improved waste management by converting organic waste into valuable biogas and fertilizer, minimizing landfill waste and environmental contamination. These efforts aim to build robust economic and food security frameworks that can withstand climate-related challenges, thereby enhancing the overall resilience of vulnerable populations in Haiti. |
| Anticipated co-benefits from the TA | Instruction: Please indicate expected co-benefits as described in the response plan and in the relevant deliverables Associated project co benefits include Economic and Social Empowerment: - Facilitates rural community access to financing and economic opportunities in clean energy - Reduces social disparities in economic participation empowering marginalized groups and promoting economic autonomy.. - Enhances food security through improved access to reliable energy for agriculture and food processing. - Strengthens community resilience to climate change impacts, particularly for marginalized groups - Improves energy affordability by replacing firewood with biogas, reducing household expenditures on traditional fuels and alleviating financial strain, particularly for low-income families. |
| Gender aspects of the TA | Instruction: Please indicate if technical assistance will be supported by a gender analysis. Describe expected gender benefits as described in the response plan and in the relevant deliverables The project will - Reduce women's workload through access to clean energy, freeing time for other activities. - Reduce women’s exposure to respiratory diseases caused by smoke from traditional cooking fuels - Empowers women economically by enhancing their participation in economic and climate responses. - Ensures gender-specific needs are considered in project implementation. |
| Anticipated contribution to NDC | Contribution to NDC Goals: - Promotes adoption of sustainable energy solutions, particularly biogas systems, in rural areas. - Aligns with Haiti's efforts to achieve NDC targets by enhancing energy access and resilience in rural communities. - Supports Haiti by building local community capacity to manage climate-related challenges. - Promotes sustainable development practices that reduce vulnerability and enhance resilience. |
| The narrative story | Approximately 1200 characters with spaces The Caribbean Centre for Renewable Energy and Energy Efficiency (CCREEE) is implementing this project in alignment with its CARICOM mandate to promote renewable energy and efficiency including the promotion of technology transfer to build a climate-resilient energy sector. CCREEE is engaging local stakeholders, particularly women and youth, in training programs for biodigester operation, ensuring sustainability and local expertise. The technical assistance requested by Agri Climatico All will lead to the replacement of firewood and charcoal with biodigester-produced biogas. This transition will improve energy access in Fessard, Kenscoff, reducing deforestation and air pollution while promoting a cost-effective, sustainable household cooking solution. The project emphasizes community training, long-term biodigester sustainability, and renewable energy entrepreneurship. Additionally, the bio-slurry byproduct from biodigesters serves as an organic fertilizer, improving soil health and supporting local agricultural productivity. By enhancing resilience, economic opportunities, and environmental protection, it serves as a model for sustainable rural development in Haiti. |
| Contribution to SDGs | To the extent possible, please describe contribution to approximately 3 SDGs, including SDG13, with a few sentences for each SDGs concerned. A complete list of SDGs and their targets is available here: https://sustainabledevelopment.un.org/partnership/register/. Project Contribution to Sustainable Development Goals (SDGs) - SDG 1: No Poverty: By providing affordable energy solutions to a rural community, the program helps reduce poverty by enabling households to save on energy costs and creating additional economic opportunities through access to reliable energy. - SDG 5: Gender Equality: The program integrates gender perspectives by encouraging women's participation in bioenergy projects, thereby enhancing their economic autonomy and leadership. The biogas produced could be used in gas cookers thereby benefiting women who are often the ones who have to do the cooking which is now primarily being done on wood fires. - SDG 7: Affordable and Clean Energy - 7.1 – By promoting the use of biodigester technology in rural Haiti, the Hatiti Biodigester Project aims to ensure access for all to reliable, modern, and affordable energy services, bridging the electricity access gap between urban and rural areas. - 7.3 – The CCREEE enhances education, awareness, and institutional capacity related to climate change mitigation and adaptation by deploying sustainable energy solutions and training local community members. The program strengthens local capacities to mitigate climate impacts and supports sustainable development. - SDG 13: Climate Action - 13.1 – The TA enhances resilience and adaptation to climate risks and disasters. - 13.3 – The T.A improves education, awareness, and institutional capacities related to climate change mitigation and adaptation. By training local technicians, raising community awareness, and strengthening institutional capacities, the program contributes to sustainable development and climate resilience. - 13.a – By promoting partnerships and facilitating access to climate finance, the TA supports significant mitigation actions in developing countries - 13.b – The program promotes mechanisms to enhance effective planning and management capacities related to climate change, focusing on women, youth, and marginalized communities in least developed countries and Small Island Developing States. |

