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[bookmark: _Hlk25135751]Technical Assistance Closure Report Template	
Objective of the technical assistance (TA) Closure Report:
· To communicate publicly in one document a summary of progress made and lessons learned during the TA towards the anticipated impact (sections 1-4). 
· To document qualitative and quantitative data collected during TA, for use in donor and UN reporting (Annex 1). 

Steps for completing the TA closure report:
1. The lead TA implementer submits the closure report at the end of the technical assistance as a final deliverable.  The TA closure report will capture outputs, outcomes and impacts of all activities conducted under the TA. Please copy and summarise relevant material from previous TA outputs/deliverables and the Response Plan, as relevant.  
2. A CTCN Manager will review and revise the closure report before final approval by the CTCN Deputy Director.   

Important note on public and internal use of the closure report: 
Once approved by the CTCN Deputy Director, the TA closure report will be a public document available on the CTCN website www.ctc-n.org. Selected content will be used for targeted communication activities. Annex 2 is for internal use only and will not be publicly available. 

Closure Report for CTCN Technical Assistance

1. Basic information 
	Title of response plan
	Evaluation and development of solar cooking technologies manufactured and assembled locally in Mali to strengthen the adaptive capacity of rural and urban/peri-urban populations and their resilience to climate change by reducing dependence on biomass for cooking in two pilot communities: Banamba Commune, Koulikoro Region (rural pilot) and Commune V, Bamako District (urban/peri-urban pilot)

	Technical assistance reference number
	2023000030

	Country / countries
	Mali

	NDE organisation 
	L’Agence Nationale de la Météorologie (Mali-METEO)

	NDE focal point
	Ms. Tandia Fanta Traore

	NDE contact information 
	courounytandia@gmail.com

	Proponent focal point and organisation 
	Seydou Coulibaly, Togo Tilé

	Designer of the response plan
	Keith Wingeard, Solar Cookers International (SCI), partnerships@solarcookers.org 

	Implementer(s) of technical assistance
	Solar Cookers International; Togo Tilé; Ms. Niang Korotimi Toure (gender expert) 

	Beneficiaries
	Community members from twelve pilot communities in two regions (Commune V, Bamako – peri-urban region; Banamba, Koulikoro – rural region)

	Sector(s) addressed 
	Renewable energy 

	Technologies supported 
	Solar – solar cooking 

	Implementation start date 
	21/05/2024

	Implementation end date
	15/10/2025

	Total budget for implementation 
	CTCN technical assistance budget: $ 194,500 USD

Total budget: $ 194,500 USD


	Description of delivered outputs and products as well as the activities undertaken to achieve them. In doing so, review the log frame of the original response plan and refer to it as appropriate
	Key outputs and deliverables included:
· Quick Needs Assessment of pilot communities in two pilot regions (peri-urban and rural).
· 170 locally manufactured and/or assembled solar cooker appliances.
· Enumerator and Training-of-trainer sessions for capacity building.
· Baseline and post-distribution surveys conducted by local employees of Togo Tilé and students, with data review and analysis led by SCI.
· Feasibility study, market assessment, and roadmap for scaling documents completed to guide opportunities for expanding on initial technical assistance phase.

	Methodologies applied to produce outputs and products  
	1) Quick Needs Assessment survey to assess pre-intervention cooking practices and community needs
2) Structured baseline and post-distribution survey to assess technology adoption and community impact
3) Training-of-trainer model for community engagement
4) Market assessment and Feasibility Study
5) Guided community feedback/focus group sessions in pilot communities


	Reference to knowledge resources
	The Climate Technology Progress Report 2024 (used to inform best practices for structuring technical assistance and guide relevant updates to the NDC 3.0 document)

	Deviations
	All intended activities, outputs, and deliverables were completed; deviations included a delayed implementation timeline (delayed approval of the initial MOU agreement between SCI and Mali-METEO and delayed bank transfers postponed the start of solar cookstove manufacturing), with the pilot phase reduced from the intended 6 months to approximately 1-3 months (1 month for peri-urban households, 3 months for rural households).


	Anticipated follow-up activities and next steps
	Mali-METEO has committed to signing an MOU extension with Solar Cookers International to explore opportunities for scaling the pilot technical assistance to a country-wide program. Togo Tilé has expressed interest in working with Solar Cookers International to assess carbon market opportunities to expand distribution, and the “Roadmap for Scaling Solar Cooking in Mali” has been reviewed and will form the basis for next steps, including potential grant and investment pathways.

Funding proposals are expected to focus on the Green Climate Fund (GCF), Green Environment Facility (GEF), and Adaptation Fund (AF).




2. Lessons learned
	
	Lessons learned
	Recommendations

	Lessons learned from the CTCN TA process 
	1. Strategic Planning and Multi-Stakeholder Coordination
2. Community Engagement and Ownership Are Central to Success
3. Adaptation of Technology to Local Context Is Essential
4. Capacity Building Strengthens Sustainability
5. Institutional Collaboration Enhances Impact
6. Strengthening Monitoring and Evaluation Builds Local Capacity and Ensures Reliable Data
7. Integrating Gender Expertise Enhances Participation and Adoption

	· Ensure regular coordination during early stages to ensure alignment on implementation planning.
· Include local community leaders while finalizing response plan and specify role of community in the technical assistance.
· If possible, assign a monitoring and evaluation lead or point person from the NDE office or other national position to ensure local data management capacity remains consistent.
· Continue to include gender requirements throughout planning and implementation components of technical assistance.

	Lessons learned related to climate technology transfer

	1. Managing Imported Supply Chains Requires Advanced Planning
2. Socioeconomic Benefits Drive Adoption
3. Affordability and Financing Mechanisms Must Be Addressed
4. Awareness Campaigns Are Key to Scale-Up
5. Behavioural Change and Continuous Support Are Essential for Technology Adoption
6. Community feedback enhances learning
	· Increase lead time for imported component parts and whenever possible, emphasize locally production with locally sourced materials; consider formalizing supply chain network to decrease lag in procurement of component parts.
· Accelerate turn-around time for approving response plan documentation and interim reporting to enable quicker disbursement of funds (a 3-month delay becomes significant if implementation is intended to be completed within 12 months).
· Prioritize clear communication of socioeconomic benefits related to technical assistance.
· Highlight behaviour change and awareness campaign elements as critical to success.
· Contributions from CTCN to support NDE and national stakeholders in review of financial opportunities for expanding technical assistance.




3. Illustration of the TA and photos 
For communication purposes, please provide 2-4 Power Point slides, including illustrations or charts, describing barriers, opportunities, methodology, activities, outputs and achieved results. The illustrations must be copied into the TA Closure report but must also be delivered as power point files. Also, please provide at least five high-resolution pictures in jpg format, capturing technical assistance. The pictures should illustrate how the TA has impacted the lives of the beneficiaries in particular and the communities in general.  

Illustrations from slide deck (PPT file attached to email):
Slide 1:
[image: ]
Slide 2:
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Slide 3:
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4. Impact Statement
The information in the table below will be used to communicate results and anticipated impacts of this technical assistance publicly. Please copy information from impact statement developed in the M&E Plan and update as relevant. 

	Challenge
	Women bear the brunt of domestic responsibilities, such as food preparation, fetching water, and collecting firewood. They are the most affected by deforestation. Rural women are forced to carry heavy loads of wood over increasingly long distances, which poses a risk in areas of growing insecurity. This creates a natural and security vulnerability associated with a conflict situation. Another aspect of the problem is that burning wood releases gases harmful to health. Urban families pay for firewood and charcoal, the cost of which places a heavy burden on their savings.

Mali's energy situation is characterized by an energy production deficit, growing demand, low access to modern energy services (a national rate of 52% in 2020), and significant spatial disparities, particularly in rural areas (24.08% in 2020). This is despite the country possessing substantial national renewable energy resources, notably solar.

	CTCN Assistance
	· 1) initial assessment and planning (included Quick Needs Assessment and technology review); 
· 2) production of solar cookers and piloting of the use of solar stoves (170 units locally manufactured and distributed across 2 pilot regions); 
· 3) data collection, feasibility study, market assessment, and scaling roadmap based on pilot project and recommendations on financial viability.

	Anticipated impact
	· Initial assessment included a Quick Needs Assessment of the two pilot regions (peri-urban and rural contexts) to identify households prioritized for inclusion in the pilot phase, along with a review of specific solar cookstove designs.
· Four designs were selected and built/assembled locally in Mali by the manufacturer Togo Tilé. Awareness campaign targeted households with an introduction to solar cooking technologies before distribution phase.
· SCI led training-of-trainer and enumerator training events to prepare local implementing partners to conduct baseline survey, introductory training, complementary technology training, and post-distribution survey data collection.
· Analysis of data resulted in feasibility study, market assessment, and roadmap for scaling document.

	Co-benefits: Achieved or anticipated co-benefits from the TA
	Co-benefits include gender indicators related to a reduction in time spent collecting fuel (16.5% reduction in average days per week spent collecting fuel, from 3.58 to 2.99) and time spent on cooking activities (14.4% reduction, from 6.9 hours per day to 5.9 hours per day) and health indicators (47.4% reduction in self-reported respiratory or ocular health problems, from 13.7% to 7.2% of households).


	Gender aspects of the TA
	Gender Analysis was integrated within every aspect of implementing the technical assistance, with a national gender expert participating in project planning meetings and contributing to training and community engagement events. Without a template for the gender assessment, SCI and the gender expert co-developed a gender action plan across each step of the response plan. Enumerators were selected to have equal gender balance, and female community leaders were encouraged to play key roles in community events. Survey analysis included review of gender disaggregated data.


	Anticipated contribution to NDC
	· Provides an initial estimate for potential emission reductions resulting from deployment of solar cookstoves.
· Initial Feasibility Study and Scaling Roadmap offer assessment of pathways to achieve NDC solar cooking goals in Mali.


	The narrative story
	Mali is a landlocked country in the Sahel region of West Africa. It covers an area of ​​1,241,248 km², 51% of which is desert. Extreme weather events are becoming increasingly frequent, resulting in degradation and desertification. Thus, year after year, open forest transforms into savanna, and savanna degrades into desert. Once abundant timber resources have almost disappeared. This phenomenon is primarily exacerbated by human activities. The forest cover is undergoing continuous degradation due, in part, to climate change, but mainly to unsustainable resource extraction. Rural communities depend on forest products, particularly for cooking fuel.

The main source of energy in Africa, and particularly in Mali, is biomass (organic matter of plant or animal origin), the use of which often generates very high levels of air pollution and serious consequences for public health. More than 80% of Malian households use wood and/or charcoal for cooking and heating. Only 15% of the rural population has access to electricity. The fuelwood resource, the main source of energy for Malian households, comes from the country's forests; 90% of the energy needed for meal preparation is met by wood. (With a firewood consumption rate of 1.35 kg/day/person), this is economically costly and contributes to pollution through CO2 emissions.

Given the environmental, social, and economic challenges, it is essential not only to inform and raise awareness among the population, especially in rural areas, about the local risks posed by climate change, but also to equip and train them in the use of available tools and technologies. This is where the technological concept of solar ovens comes in. Unlike ovens that run on gas or electricity, as the name suggests, a solar oven operates using the sun. Reflective mirrors concentrate the sun's rays to raise the temperature inside the oven. It helps to avoid the release of several tons of CO2, saves energy and lightens the workload of rural women.

	Contribution to SDGs

A complete list of SDGs and their targets is available here: https://sustainabledevelopment.un.org/partnership/register/
	SDG5 – Gender equality: the technical assistance specifically targeted reductions in time spent collecting wood as a cooking fuel by women and girls, and data indicated a reduction in days spent collecting wood, a reduction in the total time spent on cooking activities, and improved respiratory health of (primarily women) household cooks.

SDG7 – Affordable and clean energy: distribution of solar cookers provided pilot households with a device that transforms freely available sunlight into energy for cooking meals. Survey data indicated households spent an average of 66.7 % less on cooking fuel (wood and charcoal) compared to the pre-intervention baseline. Households averaged 8.64 uses of the solar cooker per week, with households indicating an intention to use the cookers 11.15 times per week going forward.

SDG13 – Climate action: households reported an average reduction of 563.8 kg of biomass consumed per month, translating to an estimated reduction of 1,872.2 tCO2e per year among the 140 pilot households. The Mali government plans to continue working with Solar Cookers International to explore carbon market pathways for scaling.






Annex 1 Technical assistance data collection 

Please add quantitative and qualitative values for the indicators selected in the M&E plan and monitored throughout the technical assistance in the tables below. Indicators which have been monitored in addition to the proposed indicators below may be added at the end of table A. Non-relevant indicators should be left blank.

A. Output and outcome indicators

	Indicator

Please note indicators below highlighted as anticipated 
	Quantitative value 
Numerals only; disaggregates must sum to the total 
	Qualitative description
List the various elements corresponding to the quantitative value as well as timelines and responsible institutions

	Total number of events organized by proponents and implementing partners
	24
	- Awareness campaign events (12 total, 1 per pilot community), 23 Feb-6 Mar 2025
- Solar cookstove demonstration events (12 total, 1 per pilot community) July and September 2025

	Number of participants in events organized by proponents and implementing partners 
	448
	Mostly the same participants in both events, so only reporting the totals to avoid double counting

	a) Number of men
	73
	Primarily women participating as the lead cook and target household event participant, although men also joined

	b) Number of women
	375
	Primarily women participating as the lead cook and target household event participant, although men also joined

	Number of climate technology RD&D related events
	12
	- Awareness Campaign events (12 total, 1 per pilot community: included explanation of the links between climate change and deforestation)

	Number of participants in climate technology RD&D events
	448
	Overlaps with “events” participants indicated above.


	a) Number of men
	73
	

	b) Number of women 
	375
	

	Number of training organized by proponents and implementing partners
	17
	- Enumerator Training, 15-Jan-2025 (led virtually by SCI, with in-person participation in Mali)
- Enumerator Adoption and Impact and Training-of-Trainers Training, 19-May-2025 + 20-May-2025
- Community Solar Cooking training (12 total, 1 per pilot community), July and September 2025
- Complementary technology training (use and fabrication of heat retention baskets, 2 total, 1 in urban region, 1 in rural region), 30 Jul 2025 and 20 Sep 2025
- Data collection training for post-distribution survey, 25-Sep-2025

	Number of participants in trainings organized by proponents and implementing partners
	468
	

	a) Number of men 
	83
	

	b) Number of women 
	385
	

	Total number of institutions trained
	2
	

	a) Governmental (national or subnational)
	1
	- Staff from Mali-METEO (2 representatives)

	b) Private sector (bank, corporation, etc.)
	1
	- Staff from Togo Tile (solar cookstove manufacturer and distributer)

	c) Nongovernmental (NGO, University, etc.)  
	0
	N/A

	Percentage of participants reporting satisfaction with CTCN training (from CTCN training feedback form)
	100 %
	Satisfied= 4+ on 5-pt scale
83% responded “5/very satisfied”
17% responded “4/satisfied”
 *Note: not all participants completed the training survey

	Percentage of participants reporting increased knowledge, capacity and/or understanding as a result of CTCN training (from CTCN training feedback form)
	100 %
	Increased knowledge, capacity and/or understanding= 4+ on 5-pt scale
58% responded “5/very satisfied”
42% responded “4/satisfied”
*Note: not all participants completed the training survey

	a) Percentage of men 
	100 %
	

	b) Percentage of women
	100 %
	

	Total number of deliverables produced during the assistance (excluding mission, progress and internal reports)
	11
	- 2.i Feasibility Study
- 2.ii Market Assessment
- 2.iii/2.iv Quick Needs Assessment Report
- 3.i Awareness Campaign Strategy document
- 3.ii/3.iii Demonstration events report
- 3.iv Recommendation of pilot households
- 4.i/4.ii Production budget and timeline
- 4.iv/4.v Complementary Technology Report
- 5.iii/5.v Distribution + Adoption and Impact Report
- 5.vi Lessons Learned report
- 5.vii Roadmap for Scaling Solar Cooking in Mali

	a) Number of communication materials, including news releases, newsletters, articles, presentations, social media postings, etc.
	3
	- 2.i Feasibility Study
- 2.ii Market Assessment
- 5.vii Roadmap for Scaling Solar Cooking in Mali

	b) Number of tools and technical documents strengthened, revised or developed 
	3
	- 3.i Awareness Campaign Strategy document
- 3.iv Recommendation of pilot households
- 4.i/4.ii Production budget and timeline

	c) Number of other information materials strengthened, revised or created (For example training and workshop reports, Power Points, exercise docs etc.)
	5
	- 2.iii/2.iv Quick Needs Assessment Report
- 3.ii/3.iii Demonstration events report
- 4.iv/4.v Complementary Technology Report
- 5.iii/5.v Distribution + Adoption and Impact Report
- 5.vi Lessons Learned report

	Total number of policies, strategies, plans, laws, agreements or regulations supported by the assistance
	4
	- 3.i Awareness Campaign Strategy document
- 2.i Feasibility Study
- 2.ii Market Assessment
- 5.vii Roadmap for Scaling Solar Cooking in Mali

	a) Adaptation related
	-
	

	b) Mitigation related
	-
	

	c) Both adaptation- and mitigation related 
	4
	- 3.i Awareness Campaign Strategy document
- 2.i Feasibility Study
- 2.ii Market Assessment
- 5.vii Roadmap for Scaling Solar Cooking in Mali

	Anticipated number of policies, strategies, plans, laws, agreements or regulations proposed, adopted or implemented as a result of the TA
	3
	- Revised “Roadmap for Scaling Solar Cooking in Mali” (after review in December 2025)
- Memorandum of Understanding (MOU) agreement between SCI and Mali-METEO to extend collaboration on scaling solar cooking beyond technical assistance (expected in Dec 2025)
- MOU agreement between SCI and Togo Tilé


	a) Adaptation related
	-
	

	b) Mitigation related
	-
	

	c) Both adaptation- and mitigation related
	3
	- Revised “Roadmap for Scaling Solar Cooking in Mali” (after review in December 2025)
- Memorandum of Understanding (MOU) agreement between SCI and Mali-METEO to extend collaboration on scaling solar cooking beyond technical assistance (expected in Dec 2025)
- MOU agreement between SCI and Togo Tilé

	Anticipated number of technologies transferred or deployed as a result of CTCN support  
	3
	Solar cooking: 
4 designs were selected, locally manufactured, and deployed (reflective panel “CooKit”, parabolic cooker, solar box oven, and PV/electric hot plate cooking system)


	Anticipated number of collaborations facilitated or enabled as a result of technical assistance
	0
	

	a) Number of South-South collaborations
	0
	

	b) Number of RD&D collaborations 
	0
	

	c) Number of private sector collaborations
	0
	

	Number of countries with strengthened National System of Innovation as a result of CTCN support
	1
	Mali

	Estimated weekly/monthly household cooking fuel expenses, compared to baseline data (economic well-being/health)
	
	- Baseline (monthly) = $ 16.98 USD
- Post-distribution (monthly) = $ 5.66 USD
- Difference = $ 11.32 USD reduction in cooking fuel expenses per month (66.6 % reduction)

	Estimated number of days per month that the solar cookstove was used (economic well-being/climate)
	
	All households: 37.5 days of usage per month


	Estimated time spent collecting wood, compared to baseline data (gender/climate)
	
	- Baseline: 3.58 days per week
- Post-distribution: 2.99 days per week
- Difference: Reduction of 0.59 days spent collecting wood per week (16.5% reduction)

	Estimated time spent on cooking activities, compared to baseline data (gender)
	
	- Baseline: 6.91 hours per day
- Post-distribution: 5.92 hours per day
- Difference: Reduction of 0.99 hours (about 59 minutes) spent on cooking activities per day (14.4% reduction)

	Self-reported respiratory health problems in the family, compared to baseline data (health)
	
	- Baseline: 13.7 % of households reporting health problems
- Post-distribution: 7.2 % of households reporting health problems
- Difference: 47.4% reduction in reported respiratory or eye problems

	Estimated reduction in biomass fuel used for cooking, per month, compared to baseline (economic well-being/climate)
	
	- Baseline: 661.83 kg
- Post-distribution: 98.04 kg
- Difference: 85.2% reduction in reported household consumption of wood among high usage households




B. Core impact indicators

Please fill in the tables for anticipated impacts of the CTCN assistance. Every technical assistance should contribute to at least one of the indicators below. For guidance on how to report on core indicators see the ‘M&E Guidance Document for TA Implementers’. 

	Core indicator 1
	Anticipated metric tons of CO2 equivalent (CO2e) emissions reduced or avoided as a result of CTCN TA 

Please add your calculations in word or excel format as an Annex to this Closure Report, where applicable.

	
	Anticipated metric tons of CO2e reduced or avoided as a result of the TA on annual basis
	Anticipated metric tons of CO2e reduced or avoided as a result of the TA in total

	Quantitative value
(emissions reductions)
	Total number (numerals only, no rounding or abbreviations)
	Total number (numerals only, no rounding or abbreviations)

	Unit
	tCO2e
	tCO2e

	GHG assessment boundary (project emissions)

Identify expected post-TA activities, associated effects and assess boundary for quantification of GHG emission reductions
	1,872.2 tCO2e per year

Includes emission reductions per year from all 170 solar cookstoves (140 households), based on average reduction in biomass consumption for cooking activities.
	16,691.2 tCO2e in total

Includes cumulative emission reductions from all 170 solar cookstoves over the full expected lifespan of each device, based on average reduction in biomass consumption for cooking activities.

	Baseline emissions

Describe baseline scenario, baseline candidates, emission factors and emissions calculated
	1,973.43 tCO2e per year

Calculated based on average of 661.83 kg of biomass consumed per pilot household per month at baseline.
	N/A

	Methodology 

Explain the method or process of verifying the indicator and how data was gathered
	Methodology explained in the Annex attached.
	

	Assumptions
Describe assumptions made during calculation and quantification of GHG reductions
	Assumptions include households with training will regularly use the solar cookstove in a consistent manner over the full lifetime of the cookstove, with the average reduction in biomass (wood and charcoal) consumed when comparing the baseline with the post-distribution survey used to estimate the CO2 emission reductions. At this stage, each cooker is assumed to have an equivalent reduction, but SCI plans to differentiate by type of cooker as the project looks to scale.
	




	Core indicator 2 
	Anticipated increased economic, health, well-being, infrastructure and built environment, and ecosystems resilience to climate change impacts as a result of technical assistance

Please provide a qualitative description of the anticipated impacts on the categories below

	Infrastructure and built environment
Anticipated increased infrastructure resilience (avoided/mitigated climate induced damages and strengthened physical assets) 
	170 solar cookstove appliances distributed to 140 households in twelve pilot communities as a result of the technical assistance. These households are expected to demonstrate improved resilience to climate shocks through a reduced reliance on scarce biomass fuel for cooking and improved health and economic well-being due to the capacity to solar cook a portion of meals.

	Ecosystems and biodiversity
Anticipated increased ecosystem resilience (areas with increased resistance to climate-induced disturbances and with improved recovery rates) 
	Forest areas surrounding two pilot regions (Bamako and Banamba) anticipated to have increased resilience as a result of the reduced demand for wood to cook food. With the pilot only including 140 households, the overall impact is expected to be modest; however, with scaling, the anticipated deployment of 15,000 + solar cookstove units by 2030 is expected to have a significant impact on the overall ecosystem resilience of Mali’s forested areas.

	Economic
Anticipated increased economic resilience (e.g. less reliance on vulnerable economic sectors or diversification of livelihood)
	- Across all households, spending on biomass as a source of cooking fuel decreased by 66.7%. This reduction represents a significant boost in household economic resilience.
- A subset of households participated in the “Complementary Technology” training/workshop to learn how to fabricate heat retention baskets, which can be used to keep solar cooked meals warm for several hours. This represents a new economic opportunity.

	Health and wellbeing
Anticipated increased health and wellbeing of target group (e.g. improved basic health, water and food security)
	- Health improvements for participants resulted from improved air quality due to a reduction in household air pollution caused by burning biomass like wood or charcoal for cooking activities. Survey results indicated:
- Baseline: 13.7 % of households reporting health problems
- Post-distribution: 7.2 % of households reporting health problems
- Difference: 47.4% reduction in reported respiratory or eye problems






	Core indicator 3
	Anticipated number of direct and indirect beneficiaries as a result of the TA

	
	Quantitative value
	Means of verification

	Total beneficiaries
	Direct – 2,471
Indirect – 10,000
	Direct beneficiaries calculated by sum of self-reported size of all pilot project households that received a solar cookstove (2,455 total) + trained Togo Tilé and Mali-METEO staff (16 total)
Indirect beneficiaries calculated based on assumption that each household would likely talk about solar cooking or other aspects of training sessions with an average of 4-5 non-participants, rounded up to account for other community members that will benefit from potential air quality improvements from a reduction in biomass cooking among pilot households.

	Number of adaptation beneficiaries
	10,016
	Calculated by estimating the number of people that become aware of solar cooking and will breathe improved air in pilot communities because of the total reduction in biomass consumed for cooking activities.

	Number of mitigation beneficiaries
	0
	All households include either adaptation or adaptation + mitigation.

	Number of adaptation-and mitigation beneficiaries
	2,455
	Calculated by summing the total household sizes of all 140 project households.







	Core indicator 4
	Anticipated amount of funding/investment leveraged (USD) as a result of TA (disaggregated by public, private, national, and international sources, as well as between anticipated/confirmed funding)

	
	Quantitative value confirmed in USD
	Quantitative value anticipated in USD
	Qualitative description
List the institutions, timelines, and description or title of the investment 
	Methods
Describe methods used for quantification of funds leveraged 

	Total funding 
	Total number in USD (numerals only, no rounding or abbreviations)
	Total number in USD (numerals only, no rounding or abbreviations)
	
	

	Anticipated amount of public funding mobilised from national/domestic sources 
	0
	TBD
	
	

	Anticipated amount of public funding mobilised from international/ regional sources 
	0
	$ 400,000
	To be confirmed - Roadmap for Scaling document proposes strategy to secure $ 400,000 USD in grant funding over 5 years (through 2030)
	Estimated funding required to proceed with scaling strategy to reach 17,500 solar cookstove units by 2030

	Anticipated amount of private funding mobilised from national/domestic sources
	0
	TBD
	
	

	Anticipated amount of private funds mobilised from international/regional sources 
	0
	$ 3,800,000
	To be confirmed - Roadmap for Scaling document proposes strategy to secure $ 3,800,000 USD in investment funding over 5 years (through 2030), which would be repaid via carbon credit revenue generated from large-scale solar cooking in Mali.
	Estimated funding required to proceed with scaling strategy to reach 17,500 solar cookstove units by 2030





Annex 2 (for internal use – to be filled in by the CTCN)
CTCN evaluation
This section will be completed by the relevant CTCN Technology Manager. 

· Evaluation of the timeliness of the TA implementation as measured against the timeline included in the response plan; 
· Evaluation of TA quality as defined in the response plan;
· Overall performance of the Implementers;
· Overall engagement of the NDE and Proponent;
· Lessons learned on the CTCN process and steps taken by the CTCN to improve. 
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