## Implementation Plan
Contract No: | UNEP/2025/680 (Umoja No. 4700031774)
Project title: | Technical capacity enhancement for climate-resilient agriculture through the revision of national policies and the improvement of data management systems.
NDE: | Matereti Mateiwai, Principal Adaptation Officer
Ministry: | Ministry of Environment and Climate Change
Implementation Period: | 17 February 2026 – 31 May 2027
Document Completion Date: | 02 July -2026
Implementing partner: | Design Thinking Sweden AB / Globalyx
Version Number: | Version 4.0
Activities |  | Deliverables |  | Timeline
# | Description | Description | Delivery date | Mar-26 | Apr-26 | May-26 | Jun-26 | Jul-26 | Aug-26 | Sep-26 | Oct-26 | Nov-26 | Dec-26 | Jan-27 | Feb-27 | Mar-27 | Apr-27 | May-27
1 | Mandatory output: Project management | Detailed work plan, M&E plan, GAAP, steering committee reports, closure package | 15/03/2026
1.1 | Draft work plan, M&E Plan and Impact Statement, GAAP, stakeholder mapping and implementation setup prepared and submitted for agreement with CTCN and national counterparts. | “Draft work plan, M&E Plan and Impact Statement, GAAP, stakeholder mapping and implementation setup prepared and submitted for agreement with CTCN and national counterparts.” | 15/04/2026
1.2 | Implementation: Project Steering Committee meeting reports | Minutes for Steering Committee meetings, decision matrix and agreed next steps documented for each meeting held, subject to governance schedule and member availability. | 15 /06/2026
1.3 | Post-implementation: closure and data collection report, press release, webinar and dialogue with financial institutions | Closure report package, outreach materials, webinar and financing dialogue record prepared at the end of the TA, subject to confirmation of activities by CTCN and partners. | 31/05/2027
2 | Output 1: Inception workshop and recommendations report on policy/act realignment | Inception workshop completed and a recommendations report including climate resilience prepared, outlining non‑binding policy options, subject to availability of policy documents and stakeholder inputs. | 08/08/2026
2.1 | Inception workshop | Technical agreement document, participating stakeholder list (gender-disaggregated), group photo, meeting notes | 20/08/2026
2.2 | Recommendations report on realignment of policy and act to include climate resilience | Recommendations report, interview notes and, as applicable, a recommendations matrix prepared and compiled, subject to availability of policy documents and stakeholder inputs | 31/08/2026
3 | Output 2: Improvement of data management systems | Pilot‑scale operational LULC database system configured and tested, MVP‑level server installed, one resource person trained and initial staff capacity strengthened, subject to data quality and institutional decisions. | 31/01/2027
3.1 | Digitalized and upgraded land-use and land-cover (LULC) capability database system | Validated scripts, data model and an integrated pilot database, with pilot‑scale LULC workflows tested and documented to the extent feasible within the TA scope | 23/02/2027
3.2 | Server installed with software and one resource person trained | MVP‑level pilot‑scale operational server with configured users/roles and basic backup procedures, and one resource person trained as system focal point, within the scope and duration of the TA. | 26/02/2027
3.3 | Training for staff on climate-resilient agriculture systems and emerging technologies | Training materials, attendance sheets, competency checklist and post-training feedback summary | 29/12/2026
4 | Output 3: Study visit and media coverage reports of climate-smart farming practices | Pilot‑scale study visit conducted, with a basic multimedia package and summary media documentation prepared, subject to logistics, weather conditions and stakeholder participation | 26/02/2027
4.1 | Organize study visits for farmers and officers to climate-resilient farming sites | Selected pilot site, agreed itinerary, participation records, technical notes, photos and optional testimonials documenting the pilot‑scale visit. | 26/02/2027
4.2 | Media coverage and study visit results report | Available media clippings and publication links, social/gender documentation where obtainable, and a concise consolidated study‑visit summary report, prepared based on information received from partners | 23/03/2027
5 | Output 4: Scale-up project concept note and capacity-building workshop | Available media clippings and publication links, social/gender documentation where obtainable, and a concise consolidated study‑visit summary report, prepared based on information received from partners. | 31/03/2027
5.1 | Scale-up project concept note | Technical concept note outlining pilot‑scale scale‑up options, indicative requirements, preliminary budget ranges, and governance/sustainability considerations (non‑binding), prepared to inform potential future funding discussions | 31/03/2027
5.2 | Capacity development and knowledge dissemination workshop | Final pilot‑scale multi‑stakeholder workshop, technical slides, participant lists (up to approximately 40 participants) and agreed dissemination outputs, subject to outreach, scheduling, stakeholder availability and agreement by CTCN and national counterparts. | 27/04/2027