[image: image1.jpg]Ci1CN

CLIMATE TECHNOLOGY CENTRE & NETWORK






Closure and Data Collection Report for CTCN Technical Assistance
1. Basic information 

	Title of response plan
	Green Cooling Africa Initiative (GCAI)

	Country / countries
	Namibia, Mauritius

	NDE focal point and organisation 
	Ms. Sin Lan Ng Yun Wing, NDE Mauritius, Environment and Sustainable Development Division 
Mr. Jonathan Kamwi, NDE Namibia, Ministry of Environment and Tourism

	Proponent focal point and organisation 
	Mr. Rajendra Foolmaun, NOU Mauritius, Environment and Sustainable Development Division
Mr. Oscar Festus, NOU Namibia, Ministry of Industrialization, Trade and SME Development

	Sector(s) addressed 
	Refrigeration and Air Conditioning 

	Technologies supported 
	Industry + Energy Efficiency (Mitigation)

	Implementation period and total duration 
	05/2016 – 06/2017 (duration: 13 months)

	Total budget for implementation 
	USD 597,000

	Designer of the response plan
	GIZ Proklima

	Implementer of response plan 
	GIZ Proklima 


2.  Summary of all activities, outputs and products that contribute to the expected impact of the technical assistance.  

	Description of delivered outputs and products as well as the activities undertaken to achieve them. In doing so, review the log frame of the original response plan and refer to it as appropriate
	The Green Cooling Africa Initiative (GCAI) was divided into four working outputs. Output I included the establishment of a robust Tier 2 inventory of the refrigeration and air conditioning (RAC) sector, according to IPCC methodology, including baseline and mitigation emissions scenarios. Output II covered a technology gap analysis with recommendations on low global warming potential (GWP) RAC technologies, covering the technology needs specific to the countries. The third output covered the review of the countries’ existing RAC-related policies and the formulation of policy recommendations supporting a low carbon pathway for the sector. Output IV resulted in the compilation of national as well as one regional technology roadmap with mitigation milestones for the RAC sector and its subsectors. 

The achievement will be described along the four working outputs and in reference to the activities as well as sub-activities mentioned in the log frame. 

1. Greenhouse Gas Inventory for the RAC Sector 
The first working package included the establishment of inventories according to the IPCC Tier 2 methodology for the countries’ RAC sectors, which served as a base for projections on the future RAC stock, energy use and GHG emissions. 
Sub-activities: 

1.1 Data Collection
1.1.1

Introduce the project to stakeholders

1.1.2

Identify of government focal point for data collection and coordination
1.1.3

Administer questionnaire for data collection through existing network of equipment owners, service providers, importers
1.1.4

Collate and analyse collected data
1.1.5

Collect and collate data available from secondary sources and other sources  (HPMP surveys, CACC surveys)
1.1.6

Quality checks and verification of data
1.2 Identification of priority sub-sectors
1.2.1
Organize workshop for stakeholders to present collected data
1.2.2
Establish criteria for identifying priority sub- sector i.e. strategic relevance, GHG emission reductions, economic and technical feasibility

In both countries, Mauritius and Namibia, stakeholders were introduced to the project and a basis for information exchange was established. Steering committees were set up and, as a result, regular exchange was taking place among the different stakeholders: National Ozone Officers (NOUs), National Designated Entities (NDEs), further ministry representatives, national and international consultants and GIZ. 

In Mauritius, the National Ozone Unit (NOU) is located within the Ministry of Social Security, National Solidarity, and Environment and Sustainable Development, Environment and Sustainable Development Division (former Ministry of Environment, Sustainable Development, and Disaster and Beach Management [MESDDBM]). In Namibia, two ministries were involved as local partners: The Ministry of Environment and Tourism (MET), as well as the Ministry of Industrialisation, Trade and SME Development (MITS-MED), where the NOU is located. On the grounds of these special circumstances in Namibia, the Permanent Secretary of MET, Dr. Malan Lindeque, requested MIT-SMED to support and carry out the Green Cooling Africa Initiative in a formal letter. In March 2017, the Permanent Secretary of MIT-SMED, Mr. Gabriel P. Sinimbo, replied and provided his assurance to MET of joint collaboration and full support to the Green Cooling Africa Initiative in Namibia through an official letter.
The Green Cooling Africa Initiative was introduced among the four participating countries, as well as to 9 other countries of the region, during the Green Cooling Africa Week (GCAW). The regional workshop was hosted by GIZ Proklima in cooperation with the Department of Environmental Affairs (DEA) of South Africa, the Department of Trade and Industry (DTI) of South Africa, the CTCN and the CTCN Consortium Member CSIR of South Africa. The GCAW took place from June 7th to 10th 2016, in Centurion, South Africa and included a two days RAC - Nationally Appropriate Mitigation Actions (NAMA) training. Seven delegates from the GCAI countries supported by CTCN (Mauritius, Namibia) as well as by the German Ministry of Environment, Nature Conservation, Building and Nuclear Safety (Ghana, Kenya), working in the ozone and climate departments of their home ministries were among the 50 participants of the GCAW, including NDEs. During the event, the GCAI and its activities were discussed, including the Green Cooling Africa Initiative. Presentations by representatives of the GCAI partner countries spurred great interest among the participants of the GCAW, which thereupon engaged in an exchange on how to further achieve a transformational change in the RAC sector and speed up technology transfer. 

Additionally, during a GIZ-organised side event at the 28th Meeting of the Parties (MOP) to the Montreal Protocol, where around 50 policy makers gathered to exchange about how to integrate a HFC phase down in ongoing national mitigation actions, the Green Cooling Africa Initiative and specifically the project activities in Namibia were presented as best practice example. 

In both countries, local consultants were contracted by GIZ in order to carry out the data collection. The consultants met with the NDEs, the different ministry departments, the NOU, Statistic Departments and other relevant stakeholders in order to identify priority subsectors. In this context, RAC industry stakeholder lists were established in both countries, serving as a base for the data collection. 

As a next step, tools for the data collection were provided by GIZ and the German consultancy HEAT to the local consultants in both countries. The consultants received questionnaires and corresponding master data sheets for the data entry for resellers/importers, end users and servicing companies. The questionnaires and master sheets were discussed with the consultants and their feedback was included in the process. 

In both countries, a national kick-off stakeholder workshop was held in order to introduce the initiative to different stakeholders such as industry and relevant ministries and to facilitate the data collection. 

The data collection in both countries covered both the current and future stock of cooling equipment and initially included all main subsectors: industrial, commercial, transport and domestic refrigeration, as well as domestic, commercial and mobile air conditioning. Due to challenges faced during the data collection process, some of the sectors could not be covered entirely by the primary data collection. 

The inventory is equipment-based and covers key parameters such as energy efficiency in terms of coefficient of performance (COP), energy consumption, as well as refrigerant type and consumption. The data collection was established according to Tier 2 standards, using primary and secondary sources. 

For the secondary data collection, the local consultants approached the National Customs Departments in order to receive country data on imports as well as exports of RAC equipment. Data was received on the relevant HS codes of RAC equipment imports. Additionally, relevant secondary data was collected in both countries. 

In Namibia, after a formal request, a letter from the Ministry of Finance addressed to the Ministry of Industrialisation, Trade and SME Development was provided to support the consultant in the secondary data collection. 
The primary data was collected through the questionnaires, which were sent out to the main RAC sector importers, servicing companies and end-users, based on the stakeholder lists established in joint collaboration of the local and German consultants and the NOUs. The RAC Excel questionnaires were submitted to all key stakeholders as soft copy and, upon request, as hard copy. The local consultants followed up on the request to the industry via phone calls and personal visits to the companies, assisting with the completion of the questionnaires. In both countries, the local consultants were assisted by a team that supported them to meet their objective. 

In a next step, the received and filled-out questionnaires were assessed, quality-checked and commented on by HEAT and, in case of low quality, sent back with the request for more detailed information. The data was put into the master sheets by the local consultants, which were afterwards checked by HEAT. In a last step, HEAT centralised, analysed and aggregated all information received from the questionnaires in one report for each country. 

In Mauritius, the primary and secondary data collection was completed in a timely manner, making it one of the best practice examples for RAC inventories - not only in the context of GCAI. By mid-November 2016, a large proportion of the questionnaires from various groups of stakeholders had been sent to HEAT and GIZ for commenting and quality reviews. Additionally, the master sheet with the compiled data had been set up. Primary data from over 150 questionnaires could be aggregated within an inventory report to provide a comprehensive picture of the country’s RAC sector and its greenhouse gas emissions. Secondary customs import data was available as well and has been used for comparison with the data derived from the questionnaires. 

In order to present, assess and verify the data collected for the inventory, a national stakeholder workshop was organised in Mauritius on the 28th of November, 2016. Over 50 representatives from the RAC industry, ministries and academic institutions came together to discuss the data collected and establish criteria for the identification of priority subsectors. The event was opened by the former Appointed Minister of Environment, Sustainable Development, and Disaster and Beach Management as well as Minister of Civil Service and Administrative Reforms, Honourable Mr. Alain Wong, and covered by the Mauritian Press. The workshop was characterised by a lively exchange of ideas as well as a critical discussion of the presented data on the RAC sector. Based on the feedback provided by participants, the data base was adjusted. 

In Namibia, due to various challenges especially regarding the consultant’s initial lack of success in getting any response from the companies, the process of data collection has been time-consuming and the inventory exercise delayed. 

In order to encourage participation and inform the relevant stakeholders of the Namibian RAC industry about the ongoing RAC inventory, a national stakeholder workshop was held on September 22nd, 2016. Additionally to the invitations sent out to important industry representatives, an advert was put in all major local newspapers in order to inform about the data collection and its purposes, as well as to invite the respective stakeholders to the workshop.
More than 20 companies, plus the government counterparts from the Ministry of Environment and Tourism and the Ministry of Industrialisation, Trade and SME Development, as well as representatives of the Customs Department attended the national workshop in Windhoek. The major air conditioning and commercial refrigeration importers that cover at least 80% of all RAC imports in the country participated as well. The event was well received by the participating stakeholders. It included discussions on pending changes and barriers in the RAC sector as well as their corresponding policies. The participants stated their understanding and support of the RAC inventory and the Green Cooling Africa Initiative. 

The cooperation with the consultant assigned for the primary data collection ended abruptly before the stakeholder workshop. Out of all questionnaires distributed by him, only one was received back by 20th of September, six weeks after the start of the assignment. During the workshop, the Namibian Institute of Refrigeration and Air Conditioning (NIRAC), a national association for the Namibian RAC industry, stood out as willing to assist with the process against compensation, urging their network, which includes the majority of RAC sector companies, to complete the data forms for the project. In order to maintain confidentiality, it was agreed that all data shall be send directly to GIZ and the consultancy HEAT by the companies. Additionally, NIRAC was supported by a letter from GIZ stating the confidentiality of the data to the RAC sector. 

Moreover, to cover the data collection in the Namibian fishing sector - which had not been included in the data collection, but makes up an important part of the RAC industry - another consultant, based in Walvis Bay, was contracted. However, due to the lacking response of the companies and their unwillingness to participate in the process, the consultant terminated her contract prematurely and primary data for the fishing sector could unfortunately not be collected. 

Another reason for the delay of the data collection in Namibia was the holiday season and the survey coinciding with the peak season for the RAC industry. However, in the first months of 2017, the data collection could be completed successfully with over 80% of the RAC equipment importers covered by the primary data collection process. In a next step, the data was compared to secondary data available from the customs import statistics as well as to the data from previous project submissions such as the HCFC Phase-out Management Plan (HPMP) for the RAC sector. 

On February 22, 2017, a stakeholder workshop was conducted in Windhoek to present and verify the inventory results and receive the feedback from the industry. The participants of the workshop included the big importers for air conditioning and commercial refrigeration, as well as representatives of other sectors and servicing companies. The participants engaged in a lively discussion during the presentation of the data. In general, the data was found to be accurate and approved by the industry members, in some cases the numbers were corrected due to very high or low numbers resulting from the questionnaires, especially in the subsector commercial refrigeration. The feedback from the workshop was used for reviewing the collected data and adaptions were made were necessary and included in the inventory report for Namibia. 
2. Technology Gap Analysis 
The second work package includes the comparison of existing technologies with internationally available green RAC technologies suitable for the respective countries to mitigate emissions. 

Sub-activities:

2.1 Analysis of cooling equipment in selected subsectors  
2.1.1

Undertake analysis that includes parameters of energy efficiency, COP, refrigerant use and refrigerant leakage rates
2.1.2

Foster regional collaboration
2.2 Comparative analysis 
2.2.1
Compare performance of local equipment against international equipment norms

For both countries, a database on local equipment and its associated performance based on available data has been established. Additionally, an analysis of the cooling equipment in selected subsectors for possible transition to low emission technologies and a comparative analysis of local equipment against internationally available best practice technologies was carried out. Based on the technology gap analyses, business as usual and mitigation potential scenarios were calculated.
3. Policy and Regulatory Framework Recommendations 
The third work package includes the assessment and revision of the countries’ existing policies for the RAC sector. Further it contains the comparison of these national policies, standards and regulations to respective international best practices and the provision of recommendations for best policy options in terms of RAC energy efficiency, refrigerant standards and labelling. The results of the analyses can be found in the respective country reports.
Sub-activities:

3.1 Support policy development that promotes adoption of low emission technologies in the cooling sector
3.1.1

Assess existing standards to amend or change as required
3.1.2

Provide support with technical expertise on state-of-the-art standards from other relevant countries
3.1.3
Assess existing standards to amend or change as required

3.1.4
Provide support with technical expertise on state-of-the-art standards from other relevant countries

3.1.5
Assess existing standards to amend or change as required

3.1.6
Provide support with technical expertise on state-of-the-art standards from other relevant countries
3.2 Recommend regulatory amendments, if required

3.3 Recommend fiscal measures and green financing support
For both countries, existing national policies, regulations and standards were revised and analysed. In a following step, country-specific barriers were identified for the key subsectors (chosen based on the results of the Tier 2 RAC inventory and the technology gap analysis) in joint collaboration with the partners from the National Ozone Units as well as the local consultants. 

For Mauritius, the results of the analysis can be found in the respective country report. The policy recommendations drawn from the analysis are country-specific and include the feedback from the national workshop on policy recommendations and actions in Mauritius on June 12, 2017. The workshop was attended by more than 30 participants, including policy-makers from Mauritius as well as representatives of the national RAC industry. The policy and technology recommendations for the sector were presented and discussed and the stakeholders jointly developed appropriate and feasible national policy strategies. In addition, funding opportunities were addressed, also with regards to the Nationally Determined Contributions (NDC) of Mauritius to the United Nations Framework Convention on Climate Change (UNFCCC). 

For Namibia, the results of the policy analysis and the recommended strategies regarding policies and technology options included in the technology roadmap were presented during a national workshop on May 23, 2017, in Windhoek. The event was attended by stakeholders from both partner Ministries (MET and MIT-SMED), as well as by representatives of other Ministries which are considered important for the inclusiveness of the project’s approach and the workshop’s objective to derive adequate policy action, such as Energy, Finance, the Climate Change Committee and a representative from the City of Windhoek. Furthermore, stakeholders from the RAC industry were present, as well as representatives of the National Training Authority. 

During the workshop, the participants actively discussed the presented policy recommendations and technology options. It became clear that for the Namibian RAC industry, training and certification is one of the most important areas for policy-makers to focus on. Furthermore, as was agreed upon by the participants, one of the foci in Namibia regarding policy action for the sector should be on labelling and energy efficiency. Both the industry as well as the policy makers thanked CTCN and GIZ for providing a platform to jointly discuss and derive national policy actions, considering the national circumstances and country-specific barriers. The results of the workshop are included in the final technology roadmap for Namibia as part of the final GCAI report. 

The national workshop was followed by a regional workshop in Windhoek on May 24, 2017, where the partners (NDEs, National Ozone Officers, UNFCCC focal points) of the four GCAI countries – Namibia, Mauritius, Kenya and Ghana – gathered to discuss the project as well as its outcomes and to compare national policy recommendations and recommend regional policy action. Due to unfortunate national circumstances, the participants from Mauritius had to cancel on short notice and were partly included in the workshop via Skype. 

The workshop served as a platform for the four countries to exchange experiences and discuss the regional cooperation under GCAI. Besides addressing and further developing the results that were achieved under GCAI until now, a space was opened to address national challenges regarding the inventory process and policy implementation that came up during the GCAI activities in the four partner countries. Topics for a regional roadmap were discussed and the focus of the next regional workshop in Mauritius, as well as its objectives, was addressed. It was concluded that the conversation on a regional level, brought up by GCAI needs to be continued, even beyond the scope of the current project. 

4. National and Regional Technology Roadmaps 

The fourth and final work package covers the elaboration of roadmap recommendations including milestones for the introduction of green cooling technologies both at the country and regional level, which serve as a basis for the development of future proposals for actions in the RAC sector. 
4.1  Develop milestone based action plan
4.1.1
Develop the action plan that includes: technological choices, time frame for adoption, existence or creation of conducive factors to facilitate change
4.2  Explore possible funding options
4.2.1

Asses funding opportunities of intentional organization/institutions
4.2.2


Explore funds available through local or regional initiatives including local banks
4.2.3
Explore public – private partnerships

4.3 Support replication and application of project deliverables at a regional scale
4.3.1

Create awareness on the Green Cooling Africa Initiative at relevant regional meetings
4.3.2


Create information and know-how exchange between NDEs of the region on the project, its methodologies and deliverables
4.3.3  
Target effort to inform and involve regional trading partners where possible and feasible in replicating the project efforts
4.3.4
Involve/ lobby with companies that have regional presence in promoting project objectives
4.3.4
Organize regional workshop
For both countries, national technology roadmaps have been developed, including country-specific milestone-based action plans to bring about a systematic change in technology and recommendations applied to the cooling sector. The roadmaps can be seen as planning instruments, translating the findings of inventory, technology gap analysis and policy analysis into strategies and milestones to increase the market share of green cooling technologies and mitigate GHG emissions in the RAC sector. They provide country-specific recommendations and suggest timelines for steps to take towards a green refrigeration and air conditioning sector. In this context, strategies for the reduction of direct and indirect emissions were outlined, regarding the following topics: energy efficiency, the transition to low GWP refrigerants, proper installation and servicing as well as the establishment of MRV systems. For each strategy, specific recommendations were formulated, tailored to the key subsectors or aimed at cross-cutting topics important to the whole RAC sector. The national technology roadmaps for the respective countries are part of the GCAI country reports.
With regards to the exploration of possible funding options in order for the countries to be able to develop further proposals, an additional international consultant was hired to support the governments of Namibia and Mauritius in the conceptualization of adequate financing mechanisms for envisioned GHG reduction in the country’s RAC sector. This activity supports the countries with the implementation of the technology roadmaps’ results. The assignment includes the exploration of funding opportunities through international funding institutions, local and regional initiatives, including local banks, as well as public private partnerships. 

To conclude the activities under the CTCN Response Plan and in order to present the national best-practice examples, transfer the project’s results from the national to the regional level and exchange views on chances and challenges for the region, GIZ, in collaboration with the Mauritian National Ozone Unit, organized a Green Cooling Africa Week in Mauritius, including a series of workshops and trainings from June 13 to June 16, 2017. The following events were part of the week: 

· On Tuesday, June 13, in a regional stakeholder workshop with over 40 participants from 17 countries of the region, the results of the GCAI as well as its methodology were presented. Participants included the countries’ National Ozone Officers and UNFCCC Focal Points, as well as selected NDEs. During the workshop, the activities that had been conducted in the GCAI partner countries were presented and its regional replication and/or upscaling as well as the regional roadmap were discussed. 

· On Wednesday, June 14, a training for the regional participants regarding the pathway from a tier 2 inventory to a project proposal was conducted. 
· On Thursday, June 15, the training continued with its focus on financial instruments and funding options, e.g. to support further policy action supporting a low mitigation pathway for the countries’ RAC sector. 
· For Friday, June 16, a fieldtrip was organized for the regional participants to see the CO2/Ammonia Cascade System at the Université de Mascareignes. 

During the week, the political decision-makers of the region engaged in a lively exchange of experiences about the project’s results, discussed the replication of the activities in their respective countries and participated actively in the trainings. For instance, one exercise consisted of including RAC sector mitigation actions in the countries’ NDCs. Participants acknowledged the high mitigation potential of the sector, according to Memory Kamoyo, Environmental Officer from Malawi, the results were quite “eye-opening”. 

Participants emphasized the need for green cooling and recognized the unique opportunity provided by GCAI for the potential replication and application of project deliverables in other countries of the region as well as at a regional scale. Further the event helped to create awareness of the project activities on a regional level and provided a space for information and know-how exchange between NOUs, NDEs, and UNFCCC Focal Points of the region. 

The technology roadmap strategies were provided to the relevant government bodies under whose jurisdiction the policy would need to be affected. Further, a guide to country-specific roadmaps for other countries of the region was established in form of a regional roadmap. The regional roadmap summarizes the experiences made in the four target countries and provides the reader with a template in order to implement the projects’ activities in the respective countries and to support them in their efforts to transform their RAC sector towards sustainable green cooling solutions. For this regional roadmap, fields of action were identified, where regional exchange of experiences, alignment of policies and other forms of cooperation could aid national efforts to increase the market share of low GWP and energy efficient RAC appliances. The regional approach brings additional value to the countries by means of synergetic use of information and resources. Ideally, elements of the roadmap will be taken over into the agendas and work streams of additional countries of the region. The data collection tools could also be applied to any other country interested in creating a detailed data basis on RAC equipment. 
The Green Cooling Africa Initiative has been implemented successfully, as was recognized by the partner countries, as well as other stakeholders of the project. The representatives of the partner countries Ghana, Kenya, Mauritius and Namibia expressed their gratitude towards CTCN and GIZ for the continuous support and guidance regarding the transformational change towards a low-emission and sustainable RAC sector. 
GCAI with its innovative nature provided an unique opportunity for the participating countries to prepare for an early transfer to climate and ozone layer friendly technology in the cooling sector. The partner countries are now considering or are already implementing an inclusion of the RAC sector’s mitigation potential in their Nationally Determined Contributions (NDCs). As a consequence, the countries would be able to mobilise further financial resources for the relevant follow up actions. The outputs of the GCAI provide the basis for financial proposals. 
Furthermore, the potential regional replication of GCAI’s activities and results in other countries of the region was discussed during the regional workshops and a regional network between NOUs, NDEs and UNFCCC Focal Points has been established. As a result, other countries of the region are considering project implementation on the grounds of GCAI in their respective countries.
Public-private partnerships were strengthened, especially through connecting the local RAC industries with their respective Ministries. Possible North-South partnerships were discussed, with technology suppliers in the global North being interested in supporting the industry in development countries. An exchange between national as well as international public and private stakeholders has been fostered in the national and regional workshops.
Through GCAI, awareness has been raised about the importance of the RAC sector for the fight against global warming and higher energy efficiency, due to the sector’s high mitigation potential at comparatively low costs. As Gaudensia Owino, part of Kenya’s NDE team, concluded, the conversation on a regional level, brought up by GCAI “needs to be kept going by all means”, even beyond the scope of project duration. The experience of the Green Cooling Africa Initiative will be presented during a CTCN Webinar, planned for October 18, 2017.


	Partners organisations
	In Germany:
· GIZ Proklima (Implementing Agency)
· As technical consultants to GIZ: HEAT GmbH
· As financial consultant: MACS GmbH

In Namibia:
· Ministry of Environment and Tourism, Department of Environmental Affairs (NDE)

· Ministry of Industrialization, Trade and SME Development (NOU)

In Mauritius:
· Ministry of Social Security, National Solidarity, and Environment and Sustainable Development, Environment and Sustainable Development Division (NDE and NOU)


	Beneficiaries
	Beneficiaries include the following:
· The partner ministries in the countries, as they were supported in the policy-making process and given a technology roadmap, containing adequate strategies and mitigation scenarios to include in further policies and their NDCs. Furthermore, they were accompanied in the process of getting further funding.
· The countries’ RAC industries, as they were included in the policy-making process, given a space to voice their concerns and were supported in an early transformation towards green cooling technologies, saving them money in the long run. Furthermore, the introduction of green cooling technologies requires capacity building and thus, triggers new employment within the sector.
· The countries as a whole as they benefit from energy savings, environmental protection, less health hazards caused by insufficient cool chains and employment generation.
· Since the TA supports the global fight against climate change through the mitigation of GHG emissions from the national RAC sectors, the environment as a whole can be named as beneficiary in a broader sense.


	Methodologies applied to produce outputs and products  
	The data collection for the RAC inventory covered both the current and future stock of cooling equipment and initially included all main subsectors, being industrial, commercial, transport and domestic refrigeration, as well as domestic, commercial and mobile air conditioning. The inventory is equipment-based and covers key parameters such as energy efficiency in terms of coefficient of performance (COP), energy consumption, as well as refrigerant type and consumption. The data collection was established according to Tier 2 standards, using primary and secondary sources. For the secondary data collection, the local consultants approached the National Customs Departments in order to receive country data on imports as well as exports of RAC equipment. Data was received on the relevant HS codes of RAC equipment imports. 

	Deviations
	Although the project was implemented successfully, some challenges and delays occurred during the project implementation. Due to the long contract negotiations between UNEP and GIZ, the start of the project has been significantly delayed. For this reason, when the technical proposal and time schedule were submitted to UNIDO, the project duration was reduced from 18 to 12 months. The project implementation period has further been reduced by another 2 months, due to a time lag between the submission of the technical proposal and the contract signing. Furthermore, the contracting of the international and national consultants took longer than expected and in both countries GIZ faced some challenges regarding the inventory, whereas the data collection in Namibia proved to be more difficult than in Mauritius. Both local consultants struggled with non-responsive industry members and some companies’ inability to provide historical data, due to non-existent or poorly managed databases. In Namibia, an additional fatigue could be noted in the industry, due to other surveys being carried out at the same time in regards to energy efficiency, which are also covering the RAC sector. Furthermore, companies of both countries were sometimes reluctant to give out information in fear of tax inspections. Due to the above-mentioned reasons and upon approval by CTCN/UNIDO, the project duration was extended until June 30, 2017.

	Achieved or anticipated gender benefits from the TA
	No gender benefits were mentioned in the response plan. 

	Achieved or anticipated co-benefits from the TA
	Environmental protection: This is and will be by far the biggest co-impact of the TA. The project initiated the transformation of the countries’ RAC sector towards green cooling technologies. Green cooling technologies protect natural resources and avoid the use of fluorinated and chemical substances which use limited resources and produce persistent wastes in the atmosphere. This is ultimately contributing to the fight against climate change and thus, to the protection of the environment.
Income and employment generation: With the introduction of green cooling technologies, new employments will be created for the installation, the planning, construction, maintenance and servicing of the technologies. The innovative technology requires skilled technicians with special know-how and thus, contributes to the economic development and the local economies of the countries.
Increased energy security: Improved energy efficiency of the equipment will effectively reduce the energy needs of the sector by a high percentage. That way, electricity consumption is saved and less fossil fuels have to be imported. For example, by introducing green cooling technologies in Mauritius, the country can reduce its energy consumption by approximately 25 %.
Foreign exchange savings: With the implementation of measures, fossil fuel based energy imports are reduced with consequential saving on imported energies.
Mobilisation of additional funds: The results of the TA have a high relevance for the compliance with international policies and regulations, such as the UNFCCC, Montreal Protocol and SDGs. As well as national climate and energy policies, e.g. the National Determined Contributions (NDCs). The TA provided the countries with concrete data and mitigation measures for the RAC sector, which can be included in their sector mitigation strategies within the NDCs. This presents a unique opportunity for the countries, as the data collection for the RAC sector via Tier 2 (IPCC) methodology is not yet included under the reporting requirements of UNFCCC. Thus, the inclusion of concrete mitigation scenarios and an implementation plan for the sector makes the countries frontrunners and therefore eligible for further funding. The TA enables the countries to apply for international funding, for example from the Green Climate Fund. All partner countries have expressed the interest to include the RAC sector in their NDCs and an assessment of adequate financing mechanisms for envisioned GHG reduction in the refrigeration and air conditioning (RAC) sector has been carried out for both Mauritius and Namibia.
Health: A reliable cooling chain, as promoted by the project, avoids foods waste and ensures both safe, healthy food and medical supplies in urban and rural areas of Africa, contributing to people’s healthy nutrition and food security.

	Anticipated follow up activities and next steps
	The Green Cooling Africa Initiative has been implemented successfully, as was recognized by the partner countries, as well as other stakeholders of the project. The representatives of the partner countries Mauritius and Namibia expressed their gratitude towards CTCN and GIZ for the continuous support and guidance regarding the transformational change towards a low-emission and sustainable RAC sector. GCAI with its innovative nature provided a unique opportunity for the participating countries to prepare for an early transfer to climate and ozone layer friendly technology in the cooling sector. All partner countries are now considering or are already implementing an inclusion of the RAC sector’s mitigation potential in their Nationally Determined Contributions (NDCs). As a consequence, the countries will be able to mobilise further financial resources for the relevant follow up actions. The outputs of the GCAI provide the basis for financial proposals to international funding institutions. Furthermore, the potential regional replication of GCAI’s activities and results in other countries of the region was discussed during the regional workshops and a regional network between NOUs, NDEs and UNFCCC Focal Points has been established. As a result, other countries of the region are considering project implementation on the grounds of GCAI in their respective countries. Through GCAI, awareness has been raised about the importance of the RAC sector for the fight against global warming and for higher energy efficiency, due to the sector’s high mitigation potential at comparatively low costs. As Gaudensia Owino, part of Kenya’s NDE team, concluded: The conversation on a regional level, brought up by GCAI, “needs to be kept going by all means”, even beyond the scope of project duration. The experience of the Green Cooling Africa Initiative will be presented during a CTCN Webinar, planned for September/October 2017. Further activities regarding the presentation of the GCAI and its results will be coordinated with CTCN.


1. Lessons learnt

	
	Lessons learnt
	Recommendations

	Lessons learnt for this TA. 
Describe essential factors contributing to successful implementation, as well as specific challenges. Recommendations include considerations on what would need to be in place for increasing success of similar efforts (i.e. regulatory, legal, stakeholders, communication, etc.)
	The Green Cooling Africa Initiative has been implemented successfully, as was recognized by the partner countries as well as other stakeholders of the project. GCAI with its innovative nature provided a unique opportunity for the participating countries to prepare for an early transfer to climate and ozone layer friendly technology in the cooling sector. The partner countries are now considering or are already implementing an inclusion of the RAC sector’s mitigation potential in their Nationally Determined Contributions (NDCs). As a consequence, the countries would be able to mobilise further financial resources for the relevant follow up actions. The outputs of the GCAI provide the basis for financial proposals. Furthermore, the potential regional replication of GCAI’s activities and results in other countries of the region was discussed during the regional workshops and a regional network between NOUs, NDEs and UNFCCC Focal Points has been established. As a result, other countries of the region are considering project implementation on the grounds of GCAI in their respective countries. Through GCAI, awareness has been raised about the importance of the RAC sector for the fight against global warming and higher energy efficiency, due to the sector’s high mitigation potential at comparatively low costs. Although the project was implemented successfully, some challenges and delays occurred during the project implementation. The contracting of the international and national consultants took longer than expected and in both countries GIZ faced some challenges regarding the inventory, whereas the data collection in Namibia proved to be more difficult than in Mauritius. In both countries, local consultants struggled with non-responsive industry members and some companies’ inability to provide historical data, due to non-existent or poorly managed databases. In Namibia, an additional fatigue could be noted in the industry, due to other surveys being carried out at the same time in regards to energy efficiency, which are also covering the RAC sector. Furthermore, companies of both countries were sometimes reluctant to give out information in fear of tax inspections. 
	The early inclusion of all relevant stakeholders, especially the industry members, has proven to be essential to the success of the project. Ideally, before the start of the data collection, a kick-off workshop is organised informing the industry, but also all important national ministries, such as Environment, Energy and Finance, about the inventory and objectives of the project. The early inclusion of the industry has the advantage that they prove to be more willing to support the project and its objectives. This is the case in particular, if they are given the space and time to voice their concerns and engage in a dialogue with their representatives in the Ministries. Additionally, the choice of consultant proved to be of high importance, as well as his/her connection to the industry. The local consultant needs to know the industry as well as national circumstances to a great extent and has to be capable to explain the inventory and questionnaires in detail to the stakeholders. Mistrust toward the purpose of the data collection can be partly avoided by the provision of a letter explaining the process of data analysis and emphasizing data confidentiality to the industry members. Experience shows further that custom data has to be treated with caution and should be verified via double-check with the primary data collected during the inventory and through consultation with stakeholders of the national RAC industries, due to potential double counting and different forms of measurement (e.g. units or kg). 

	Lessons learnt related to climate technology transfer

Describe opportunities, challenges and barriers for the use and deployment of the technology or technologies supported by the TA. The objective is to identify specific success factors for technology transfer 
	The successful implementation of technology transfer towards green cooling in the RAC sector with its specific needs depends to a great extent on market availability of “green” equipment, as well as on national policies and regulations favouring the introduction of green cooling technology. Even if the national RAC industry shows interest in transferring towards more climate-friendly and energy efficient technology, they often need additional incentives on a financial, as well as regulatory level. The opportunity that this moment in time bears for the technology transfer towards green cooling is based in the increase in regulatory requirements on an international level. The Kigali Amendment to the Montreal Protocol on Substances that Deplete the Ozone Layer has been or will be ratified by the majority of countries, pushing them to phase down climate damaging refrigerants (Hydrofluorocarbons). This will result in various changes within the cooling sector and can be used to push climate friendly and energy efficient cooling technology. 

	When trying to initiate a climate technology transfer, one has to consider national polices as well as the country’s specific market situation. Technology transfer can only be sustainable if conditions are created under which the transfer will stimulate the market regarding the supply with green technology and if national policies support the change and thus, the demand. Measures to support on an institutional level include amongst other tax reductions, subsidies or penalisation of obsolete technologies.

	Lessons learnt related the CTCN process for TA
	Lessons learnt regarding the CTCN process are related in particular to the adequate time planning for project preparation. Although the project was implemented successfully, some challenges and delays occurred before the actual start of project implementation. Due to the long contract negotiations between UNEP and GIZ, the start of the project has been significantly delayed. For this reason, when the technical proposal and time schedule were submitted to UNIDO, the project duration was reduced from 18 to 12 months. The project implementation period has further been reduced by another 2 months, due to a time lag between the submission of the technical proposal and the contract signing. 
	The consequential recommendation for potential further projects would be to start processes early and plan accordingly.


4. Illustration of the TA and photos 

For communication purposes, please provide 2-4 Power Point slides with illustrations or charts showing the TA process, applied methodology, activities, outputs and achieved results. The illustrations must be copied into the TA Closure report but must also be delivered as power point files. Also, please provide at least five high-resolution pictures in jpg format, capturing technical assistance. The pictures should illustrate how the TA has impacted the lives of the beneficiaries in particular and the communities in general.  
5. Information for TA impact description 

The information in the table below will be used to produce the CTCN TA Impact Description. The TA Impact description is a 2-page summary document for communication purposes. Please copy information from sections above and technical delivery reports as required.    
	Challenge: Approx. 500 characters with spaces
	RAC appliances are rapidly spreading across Africa, resulting in an increased energy demand along with increased emissions of greenhouse gases (GHG) and ozone depleting substances (ODS). Alternative technologies, which can retard or imped this development, are internationally available but not commonly used in Africa.                                                                                                                                                                                                                                           

	CTCN Assistance: 2 to 4 bullet points. Approximately 450 characters with spaces
	· GCAI is a regional initiative aimed to prepare for a transformational change towards sustainable cooling appliances. 
· The objective is to enable participating countries to have the necessary information (i.e. inventory) and tools (i.e. policy options) to create a shift in the cooling sector to more sustainable technology options. 

· This is to be achieved not only through country specific initiatives, but also through a constructive utilization of a regional approach. 

	Anticipated impact: 2 to 4 bullet points to summarise anticipated impact. Approximately 250 characters with spaces. As a minimum, please include one of the following: i) Quantity of greenhouse gas emissions reduced, avoided or sequestered; or ii) Number of people with increased capacity to adapt to the impacts of climate variability and change.  
	· Transition to a sustainable cooling equipment base in the respective countries
· Countries develop clear understanding on how the cooling sector contributes to their national energy consumption and GHG emissions + on appropriate policy measures  
· Appropriate actions on how to reduce the consumption of ODS, reduce energy demand and related GHG emissions are defined
· Anticipated quantity of GHG emissions reduced (cumulative until 2050):

Namibia: 24 Mt CO2eq

Mauritius: 46 Mt. CO2eq

	Linkages and contribution to NDC: 2 to 4 bullet points. Approximately 350 characters with spaces
	· High relevance for the compliance with the National Determined Contributions (NDCs) under UNFCCC. 

· Provision with concrete data and mitigation measures for the RAC sector, which can be included in sector mitigation strategies within the NDCs.

· Inclusion of concrete mitigation scenarios and an implementation plan for the sector makes the countries frontrunner and therefore eligible for further funding.

	The narrative story: Approximately 1200 characters with spaces
	RAC appliances are rapidly spreading across Africa, resulting in an increased energy demand along with increased emissions of greenhouse gases and ozone depleting substances. Alternative technologies are internationally available but not commonly used in Africa. GCAI introduces a shift towards a green cooling sector in Africa and goes beyond what has been addressed and practiced in many developing countries. It takes advantage of the economies of scale to facilitate sustainable industrial development. Activities from the TA include the provision of information (i.e. inventory) and tools (i.e. policy options) necessary to create a shift towards more sustainable technology options. This is supported by the exchange of know-how, expertise and experiences between the countries involved, thus facilitating scaling-up processes. 
The initiative`s main object is to support the development of inventories for the refrigeration and air conditioning (RAC) sector in Mauritius (SIDS) and Namibia. These inventories are based on Tier 2 methodology, determining business as usual (BAU) and mitigation emission paths and assessing technology needs through gap analysis. The RAC sector includes stationary and mobile air conditioning as well as domestic, commercial, industrial and transport refrigeration. Focus is placed on equipment with low GWP refrigerants, in particular natural refrigerants, as well as inverter technologies and further energy efficient design options. The local implementation is conducted by the National Designated Entities (NDEs) in cooperation with the National Ozone Units (NOUs). Government institutions are responsible for drafting national regulations and putting them in place. The private sector will have to implement desired technology changes. Civil society players can influence both public and private sectors and bring green cooling forward.
The phase-out of fluorinated-gases along with the increase in energy efficiency in the RAC sector facilitate the achievement of ambitious national determined contributions, which serve as the basis of global GHG savings . GCAI’s activities directly address multiple Sustainable Development Goals (SDGs). Advancement through this TA are especially expected in climate change mitigation, in productive and sustainable employment in the RAC sector, as well as in inclusive and sustainable industrialization through innovative and environmentally sound RAC technologies.


	Contribution to SDGs: Always include contribution to SDG 13, and to the extent possible, please include contribution to 2 other SDGs, describing the contribution with a few sentence for each SDGs concerned. A complete list of SDGs and their targets is available here: https://sustainabledevelopment.un.org/partnership/register/
	Goal 2. End hunger, achieve food security and improved nutrition and promote sustainable agriculture: 

· Around 40% of goods perish along (missing) cold chains, particularly in the Global South. Cold storage and cold supply, especially in rural, off grid areas is essential to protect the harvest and prevent food loss. The activities within GCAI support the technology transfer towards green cooling technologies in African countries and thus, contributes to the second SDG, bringing cooling technologies to rural areas. 
Goal 3. Ensure healthy lives and promote well-being for all at all ages
· Introducing cooling technologies in rural areas secures the cool storage of vaccines and further pharmaceuticals, which ensures the access to health systems for the population that has previously been excluded from proper healthcare provision.
Goal 4. Ensure inclusive and equitable quality education and promote life-long learning opportunities for all
· A strategy for affordable and quality technical, vocational education and training to ensure that local trainers and technicians are trained on the use of equipment running on low GWP refrigerants has been part of GCAI from the beginning. This results in the long run in better developed technical and vocational skills and the creation of new forms of employment. Furthermore, this ensures a fair access to RAC know-how on a country level. 
Goal 7. Ensure access to affordable, reliable, sustainable and modern energy for all
· Refrigerators and air-conditioners are amongst the top investments for poor families. Up to 80% of energy bills in poor households stem from refrigeration costs. Improved energy-efficiency and established minimum energy-efficiency standards for the cooling sector, as promoted by GCAI, supports affordable energy in partner countries.
Goal 8. Promote sustained, inclusive and sustainable economic growth, full and productive employment and decent work for all
· With the introduction of green cooling technologies, new employments will be created for the installation, the planning, construction, maintenance and servicing of the technologies. The innovative technology requires skilled technicians with special know-how and thus, contributes to the economic development and the local economies of the participating countries.
Goal 12. Ensure sustainable consumption and production patterns
· Consequences of the introduction of green cooling technologies include the reduction of food waste at the retail and consumer levels and the reduction of food losses along production/supply chains, including post-harvest losses, resulting in a more sustainable consumption of the cooled goods.
Goal 13. Take urgent action to combat climate change and its impacts
· HFC is the fastest-growing non-CO2 GHG (USEPA, 2014). Without an international control, continuing growth of HFCs will be responsible for 0.1°C temperature rise in 2050, with potential of increasing up to 0.5°C by 2100. Through the replacement of HFC refrigerants, up to 100 million tonnes of CO2eq can be saved by 2030. Additionally, the improved energy efficiency of RAC equipment can save up to 100 million tonnes CO2 eq by 2030. GCAI promotes the replacement of HCFCs and HFCs by natural refrigerants and the use of energy-efficient equipment.



Note: Please see example of a TA Impact Description at the following link: 
https://www.ctc-n.org/sites/www.ctc-n.org/files/benin_a_ag_forestry.final_.pdf

Annex 1 (for internal use in donor and UN reporting)
A.  Standardised CTCN performance indicators for donor and UN internal reporting
Please add quantitative values for indicators relevant to the particular TA in the list below.  Non-relevant indicators should be left blank. Please only fill in the table for activities and outputs conducted or produced directly by the CTCN assistance.
	CTCN standardised performance indicators 
	Quantitative value 
	Qualitative description
List the various elements corresponding to the quantitative value

	1. Overview

	Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by international experts and consultants
	300 days
140 days

  40 days
	GIZ Proklima
HEAT GmbH  
MACS GmbH

	Number of active person-days (not full duration) of technical assistance provided to counterparts or stakeholders by national experts and consultants
	100 days 
	Local consultants 

	Number of for external communication and outreach activities conducted to showcase the assistance (news release, newsletters, articles on website, etc.)
	20
	GIZ GCI Newsletters, CTCN newsletters, Tweets, newspaper articles in Mauritius and Namibia, 3 national TV in Mauritius, Kigali MOP  

	2. Events (other than trainings) held as part of the assistance

	Number of international and multi-country (at regional or sub-regional level) technology and knowledge sharing events
	4
	South Africa, Kigali, Namibia, Mauritius  

	Number of participants in the events above
	150
	

	Number of national technology and knowledge sharing events
	6
	Three national workshops per country 

	Number of participants in the events above
	140
	

	Number of public-private events related to technologies
	6
	Three national workshops including the RAC industry in Namibia, three national workshops including the industry in Mauritius

	Number of participants in the events above
	See above
	

	3. Training and capacity building activities conducted during the assistance

	Number of training sessions and capacity strengthening activities
	4
	Two full days of trainings were provided to the regional participants during the Green Cooling Week in South Africa in June 2016.

Two full days of trainings were provided to the regional participants during the Green Cooling Week in Mauritius in June 2017:

· June 14: Training regarding the pathway from a tier 2 inventory to a project proposal was conducted. 
· June 15: Training focusing on financial instruments and funding options, e.g. to support further policy action supporting a low mitigation pathway for the countries’ RAC sector. 

	Number of people who received the training
	79
	Regional participants in South Africa and Mauritius 

	Number of men 
	71%
	

	Number of women 
	29%
	

	Total number of organisations trained
	36
	

	Number of research organisations, laboratories and universities 
	
	

	Number of private companies 
	2
	

	Number of cities and local government 
	0
	

	Number of communities
	0
	

	Number of ministries 
	26
	

	Number of specialised governmental institutions
	5
	

	Number of non-profit organisations 
	0
	

	Level of satisfaction of participants after the training (from training feedback form). Categories include: From very satisfied, satisfied, partly not satisfied, not satisfied at all
	40%
60%
0%

0%
	Very satisfied 
Satisfied 

Partly not satisfied 

Not satisfied 

	Percentage of participants that increased their capacities thanks to the training (from training feedback form). Categories include: Significantly, very, moderately, to none.
	54%
43%

  3%
	Very much

Much 

Not much

	Percentage of men
	/
	Feedback forms were anonymous and did not separate gender. Sorry!

	Percentage of women
	/
	Feedback forms were anonymous and did not separate gender. Sorry!

	4. Tools, technical reports and information material supported by the assistance

	Total number of tools, technical reports and information material supported by the assistance (excluding mission, progress and internal reports)
	19
	

	Number of tools strengthened, revised or developed
	10
	RAC excel tools and questionnaires 

	Number of technical reports strengthened, revised or created
	8
	4 output reports for each country

	Number of other information materials strengthened, revised or created
	1 
	Regional roadmap

	5. Policies, laws and regulations supported by the assistance



	Number of policies, strategies, and plans drafted addressing climate change adaptation
	/
	TA with focus on climate change mitigation.

	Number of policies, strategies, and plans drafted addressing climate change mitigation
	2
	Policy Roadmaps

	Number of documents developed to inform other policies, strategies, and plans on climate change adaptation (sectoral strategies, national development plans, etc.)
	/
	TA with focus on climate change mitigation.

	Number of documents developed to inform other policies, strategies, and plans on climate change mitigation (sectoral strategies, national development plans, etc.)
	2
	One country report per partner country, including inventory report, technology gap analysis, policy assessment and recommendations, and technology roadmap with mitigation scenarios and a milestone-based strategy for the RAC sector.

	Number of laws, agreements, or regulations drafted addressing climate change adaptation
	/
	TA with focus on climate change mitigation.

	Number of laws, agreements, or regulations drafted addressing climate change mitigation
	/
	/

	Number of documents developed to inform laws, agreements, or regulations on climate change adaptation
	/
	TA with focus on climate change mitigation.

	Number of documents developed to inform laws, agreements, or regulations on climate change mitigation
	9
	All output reports

	6. Institutional strengthening supported by the assistance
	
	

	Number of institutional arrangements in place to coordinate near and long-term national adaptation plans (NAPs) 
	/
	TA with focus on climate change mitigation.

	Number of organisations with increased technical capacity to advance near and long term national adaptation plans (NAPs) which integrate EbA 
	/
	TA with focus on climate change mitigation.

	Number of organisations with increase awareness and knowledge among countries to better own and drive national adaptation planning processes
	/
	TA with focus on climate change mitigation.

	7. Partnerships and cooperation

	Number of private companies directly engaged in the assistance (that partnered with the proponent, the beneficiaries or the CTCN to implement the assistance)
	300
	Private sector (importers, retailers, end consumers, etc.) that participated at workshops or/and filled out  questionnaires, etc.

	Number of South-South collaboration enabled during or through the assistance, when stakeholders from other countries were involved in the assistance
	1
	A regional network was formed via the TA during regional meetings. Participants of the events emphasized the need for green cooling and recognized the unique opportunity provided by GCAI for the potential replication and application of project deliverables in other countries of the region as well as at a regional scale. The TA helped to create awareness of the project activities on a regional level and provided a space for information and know-how exchange between NOUs, NDEs, and UNFCCC Focal Points of the region. 

	Number of North-South collaboration enabled during or through the assistance, when stakeholders from other countries were involved in the assistance
	/
	/

	Number of Triangular collaboration enabled during or through the assistance, when stakeholders from other countries were involved in the assistance
	/
	/ 


B. Indicators of anticipated impacts that may occur after the TA is completed 
	CTCN standardised performance indicators 
	Quantitative value 

Insert the request value and unit
	Content

List the elements included in the number provided
	Expected timeline

Indicate when the indicator and value are expected to be achieved
	Responsible institution

Indicate the institution(s) that will play leading role in enabling the indicators and anticipated values to be achieved

	16. Anticipated finance mobilised

	a) Anticipated amount of public/donor investment mobilised (in USD) from the beneficiary country for climate change activities as a result of the TA 
	5,000,000 USD
	Public (including reduced import tariffs, VAT, trainings, etc.) 
	 2020-2030
	National ministries of environment or trade and industry

	b) Anticipated amount of public/donor investment mobilized (in USD) from international and regional sources for climate change activities as a result of the TA
	10,000,000 USD
	National/regional RAC mitigation projects (e.g. GCF)
	2020-2025
	National ministries of environment or trade and industry

	c) Anticipated amount of private investment mobilised (in USD) from the beneficiary country for climate change activities as a result of the TA 
	5,000,000 USD
	Private contributions
	2020-2030
	Various  companies 

	d) Anticipated amount of private investment mobilised (in USD) from international and regional sources for climate change activities as a result of the TA 
	1,000,000 USD
	Private contributions
	2020-2030
	Various companies

	17. Policies

	a) Anticipated number of policies, strategies, plans, addressing climate change mitigation officially proposed, adopted, or implemented as a result of the TA
	40
	10 x RAC policies 

10 x NDCs

10 x NDC imple-mentation plans/strategies

10 x MEPS for RAC 
	By 2020
	National ministries of environment 

	Anticipated number of policies, strategies, plans, addressing climate change adaptation officially proposed, adopted, or implemented as a result of the TA.
	/
	/
	/
	/

	b) Anticipated number of laws, agreements, or regulations addressing climate change mitigation officially proposed, adopted, or implemented as a result of the TA.
	10
	NDCs
MEPS

Technical standards

Tax/duties


	2025
	Relevant ministries (environment, finance, technology, education)

	Anticipated number of laws, agreements, or regulations addressing climate change adaptation officially proposed, adopted, or implemented as a result of the TA.
	/
	/
	/
	/

	c) Anticipated laws, policies, regulations, strategies and plans where climate change mitigation will be mainstreamed as a result of the TA
	/
	/
	/
	/

	Anticipated laws, policies, regulations, strategies and plans where climate change adaptation will be mainstreamed as a result of the TA
	/
	/
	/
	/

	18. Anticipated number of public-private partnerships created
	10
	
	By 2025
	

	19. Anticipated twinning arrangements created as a result of the TA
	/
	/
	/
	/

	20. Anticipated number of technology projects prepared and implemented to support action on low emission and climate-resilient development 
	20
	RAC technology projects in various sub sectors  
	By 2030
	Ministries of environment and industry

	21. Anticipated number of strengthened National Systems of Innovation and technology innovation centres in recipient country
	/
	/
	/
	/

	22. Anticipated Clean Energy Generation Capacity

Clean supported by the TA that has achieved financial closure 
	/
	/
	/
	/

	23. Anticipated and projected GHG reductions. Quantity of greenhouse gas (GHG) emissions, measured in metric tons of CO2-e, anticipated to be reduced or sequestered as a result of projects supported by the TA
	Namibia: 

24 Mt CO2eq
Mauritius

46 Mt. CO2eq
Other countries (Kenya, Ghana, etc.): 

200 
	Cumulative mitigation potential of RAC sector
	Up to 2050
	Ministries of environment and industry

	24. Anticipated clean energy generation capacity supported by the TA that has achieved financial closure

	/
	/
	/
	/

	25. Anticipated and projected greenhouse gas emissions reduced or avoided through 2030, in metric tons of CO2-e, from adopted laws, policies, regulations, or technologies related to clean energy/sustainable landscapes as a result of the TA 
	80 Mt. CO2eq
	Cumulative mitigation potential of RAC sector
	2030
	Ministries of environment and industry

	26. Anticipated number of people improving their livelihood as co-benefits as a result of the TA 
	100
	Technicians benefit from trainings and therefore have increased employment and income opportunities 
	2025
	Training institutes

	27. Anticipated  technology types effectively deployed in the country
	50
	Different RAC technologies
	2025
	Private sector (importers and consumers)

	28. Anticipated UNFCCC processes implemented as a result of the TA (NAMA, NAPA, NDC, etc.)
	14
	10 x NDCs

4 x NAMAs
	2025
	Ministries of environment

	29. Anticipated Technology Needs Assessments (TNA) and technology Action Plans (TAP) as a result of the TA
	/
	/
	/
	/

	30. Anticipated cooperative research, development and demonstration programmes within and between developed and developing country Parties facilitated as a result of the TA
	8
	Demonstration projects
	2025
	Technology supplier from developed countries and relevant ministries in developing countries

	31. Anticipated improved climate change observation systems and related information management in developing country Parties. 
	4
	MRV systems
	2020
	Ministries of environment


Annex 2 (for internal use – to be filled in by the CTCN)
CTCN evaluation

This section will be completed by the relevant CTCN Technology Manager. 

· Evaluation of the timeliness of the TA implementation as measured against the timeline included in the response plan; 

· Evaluation of TA quality as defined in the response plan;
· Overall performance of the Implementers;
· Overall engagement of the NDE and Proponent;
· Lessons learned on the CTCN process and steps taken by the CTCN to improve. 

