# Instructions to lead Implementers for drafting the

# Technical Assistance Closure and Data Collection Report

Objective of the technical assistance (TA) Closure Report and Data Collection Report:

- To communicate publicly in one synthesis document a summary of progress made and lessons learned under the technical assistance (TA) towards the anticipated impact (main template).

- Compile TA-specific information required for internal use in donor and UN reporting (annex 1).

Steps for completing the TA Closure report:

- The lead TA implementer drafts the report at the end of the assignment as a final deliverable /product.  The TA Closure report will capture all activities conducted under the TA hence it is expected that duplication of information will occur from earlier documents. Please copy and summarise relevant material from previous TA outputs/deliverables and the Response Plan, as relevant.

- A CTCN Manager will review and revise the report before final approval by the CTCN Director.

Important note on public and internal use of the closure report:

Once approved by the CTCN Director, the TA Closure and Data Collection Report will be a public document available on the CTCN website.  Annex 1 is for internal use only and will not be publicly available.

Closure and Data Collection Report for CTCN Technical Assistance

- Basic information

| Title of response plan | Bangladesh Energy Efficiency & Conservation Master Plan (EECMP) elements for energy auditor training and certification |
| --- | --- |
| Technical assistance reference number | DTIE18-EN55/SSFA/P1-33EUL-000120/WBSE-SB-0009000.01.39 |
| Country / countries | Bangladesh |
| NDE focal point and organisation | SREDA-Bangladesh |
| Proponent focal point and organisation | SREDA-Bangladesh |
| Sector(s) addressed |  |
| Technologies supported | Energy & Climate |
| Implementation period and total duration | 31st August 2018 to 14th March 2019 |
| Total budget for implementation | US$80600 |
| Designer of the response plan | National Productivity Council - India |
| Implementer of response plan | National Productivity Council - India |

2.  Summary of all activities, outputs and products that contribute to the expected impact of the technical assistance.

| Description of delivered outputs and products as well as the activities undertaken to achieve them. In doing so, review the log frame of the original response plan and refer to it as appropriate | Activity 1: Preparation of Syllabus and finalization of curriculum Activity 2: Design of course material and model question banks Activity 3: Preparation of Training module and Training of Trainers As per the scope of work, all the above three activities were completed successfully within the time frame |
| --- | --- |
| Partners organisations | National Productivity Council - India |
| Beneficiaries | SREDA-Bangladesh |
| Methodologies applied to produce outputs and products | The syllabus under each module was developed in consultation with senior consultants from NPC and subject matter experts drawn from consultancy organization in field of energy management & audit and proposed to SREDA. The curriculum was finalised incorporating inputs provided by Industry Associations, Designated Consumers and SREDA, Bangladesh. Subsequently course material and model question bank as per the contents under each module were developed and were circulated to SREDA for review and comments. Finally, training of trainer modules were prepared and a team of officials from Bangladesh was hosted and provided training at CETEE, AIP-NPC, Chennai. Experienced faculty drawn from various parts of country provided inputs which included lectures, case studies, and interactive discussions. The training was supplemented by field visits. |
| Deviations | No deviations from the response plan. |
| Achieved or anticipated gender benefits from the TA | Under National Certification Programme, energy managers and auditors in Bangladesh will be certified and a pool of independent energy managers and auditors will be created. The program is expected to be gender neutral providing opportunity to all interested candidates. |
| Achieved or anticipated co-benefits from the TA | The certified energy managers and auditors will support in implementation of Energy Efficiency (EE) and Conservation (C) Master Plan of Bangladesh |
| Anticipated follow up activities and next steps | SREDA will conduct national certification Exam for Energy managers and Energy Auditors in Bangladesh to start developing human resources for supporting implementation of the EE & C master plan Activities. |

- Lessons learnt

|  | Lessons learnt | Recommendations |
| --- | --- | --- |
| Lessons learnt for this TA. Describe essential factors contributing to successful implementation, as well as specific challenges. Recommendations include considerations on what would need to be in place for increasing success of similar efforts (i.e. regulatory, legal, stakeholders, communication, etc.) | - Early stage agreement on syllabus and parallel review of training modules by SREDA of the module by comparing with their other country experiences and sharing their views with NPC helped customize the modules to Bangladesh’s needs and requirements. - Comparing the proposed modules with other country experiences like South Korea took more time than anticipated and posed a challenge for timely completion. - Participation by all stakeholders, viz, Government agencies (SREDA, MOEF), Academia ( University professors), Consultants and NGOs ensured healthy discussion about ways and means to disseminate not only the knowledge gained but also how to apply. | - For trained trainers to use their learning beyond informal platforms a regulatory mechanism is required to certify the trained persons as Energy Auditors and Managers. India’s experience of certifying through its Bureau of Energy Efficiency can be considered as SREDA is already familiar with the BEE structure. - Energy Efficiency targets for different industrial sectors need to be prescribed to create demand for these auditors and to meet its NDC targets. (Eg; India’s PAT Scheme). - Using the knowledge gained through this program financial incentives need to be designed to ensure effective implementation of the recommendations made by these energy auditors especially by SMEs. |
| Lessons learnt related to climate technology transfer Describe opportunities, challenges and barriers for the use and deployment of the technology or technologies supported by the TA. The objective is to identify specific success factors for technology transfer | - Materials and technologies related to energy efficiency improvement and conservation like heat exchangers (waste heat recovery) insulation materials, energy efficiency motors ( IE2, 3,4), VFDs, energy efficient transformers etc. were discussed. All these provide the opportunities. - Some of these technologies need to be sourced from outside which may require payments in dollar/Euro/Yen and other currency terms creating pressure on foreign exchange reserves. - Indigenous manufacturers may not like allowing import of these technologies despite not having the ability to meet the demand. | - The experience of allowing import of LED bulbs and the net benefits accrued can be used as case study to allow parity with local manufacturers so that the benefits are realized early and thus gain more than what is spent. |
| Lessons learnt related to the CTCN process for TA | - The training of trainer is a first step and to realize the fruits of the training follow on regulatory mechanisms and structures are to be evolved. | - Each trained trainer is expected to create a multiplier effect by training 10-20 members in their respective organizations /institutions so that the learning gets institutionalized to effectively enable evolving legal and regulatory measures. |

4. Illustration of the TA and photos

For communication purposes, please provide 2-4 Power Point slides with illustrations or charts showing the TA process, applied methodology, activities, outputs and achieved results. The illustrations must be copied into the TA Closure report but must also be delivered as power point files. Also, please provide at least five high-resolution pictures in jpg format, capturing technical assistance. The pictures should illustrate how the TA has impacted the lives of the beneficiaries in particular and the communities in general.

5. Information for TA Impact Description

The information in the table below will be used to produce the CTCN TA Impact Description. The TA Impact description is a 2-page summary document for communication purposes.

| Challenge: Approx. 500 characters with spaces | During the last decade, primary energy consumption of Bangladesh increased by over 100% due to rapid industrialization and the gap between national energy production and the amount of primary energy use is becoming wider. The Government has initiated Energy Efficiency & Conservation Master Plan (EECMP) to guide the efforts on energy efficiency and conservation. As per the master plan, large energy consumers in industrial sector (factories) and commercial sector (buildings), as per pre-defined energy consumption level, will be designated as “large energy consumers” (DCs) by the regulation. The DC’s will be obligated to implement an Energy Management System (EMS). Although the proposed policy intervention is being welcomed because of its impact on production cost and environmental sustainability, there is no professional certification scheme that exists for energy auditors and managers |
| --- | --- |
| CTCN Assistance: 2 to 4 bullet points. Approximately 450 characters with spaces | - Technical assistance to SREDA to develop National Certification Programme for energy managers certified energy auditors and accredited/Designated energy auditors in Bangladesh. - Under this scheme, the selected energy auditor and managers will be certified and designated by SREDA. - Subsequently, these auditors and mangers will conduct stipulated activities for the purpose of ensuring the compliances as per the master plan. |
| Anticipated impact: 2 to 4 bullet points to summarise anticipated impact. Approximately 250 characters with spaces. As a minimum, please include the impacts described in annex 1B as well as other relevant qualitative and quantitative impacts anticipated after completion of CTCN technical assistance. | The main activities pertaining to technical assistance in development of National Certification Programme are - Preparation of Syllabus and finalization of curriculum - Design of course material and question banks - Training of Professionals - Trained Energy Managers/ Auditors will contribute to CO2 reduction by conducting Energy Audits |
| Linkages and contribution to NDC: 2 to 4 bullet points. Approximately 350 characters with spaces | The Assistance Supports Bangladesh’s Nationally Determined Contribution to - Implement the national certification programme and - Conduct the certification examination to start developing human resources for supporting implementation of the EE & C plan Activities. |
| The narrative story: Approximately 1200 characters with spaces | Although the per capita energy consumption of Bangladesh is one of the lowest in the world, the primary energy consumption is increasing steadily. During the last decade, primary energy consumption increased by over 100% due to rapid industrialization and the gap between national energy production and the amount of primary energy use is becoming wider. The Government has initiated several energy efficiency and energy conservation measures to reduce the energy intensity and the gap between energy supply and energy use. As a result, The Energy Efficiency & Conservation Master Plan (EECMP) was established, to guide the efforts on energy efficiency and conservation. Under the EECMP, three EE&C programs are to be promoted, namely, Energy Management Program, Energy Efficiency (EE) Labelling Program and Energy Efficiency (EE) Buildings Program. Sustainable and Renewable Energy Development Authority (SREDA) was established in 2012 as the nodal organization to promote, develop, co-ordinate and implement the renewable energy and Energy Efficiency activities in the country. As per the master plan, large energy consumers in industrial sector (factories) and commercial sector (buildings), as per pre-defined energy consumption level, will be designated as “large energy consumers” (DCs) by the regulation. The DC’s will be obligated to implement an Energy Management System (EMS). Although the proposed policy intervention is being welcomed because of its impact on production cost and environmental sustainability, there is no professional certification scheme that exists for energy auditors and managers. In this context, SREDA has sought assistance of CTCN in developing a national certification scheme of energy managers, certified energy auditors and accredited/Designated energy auditors. |
| Contribution to SDGs: Always include contribution to SDG 13, and to the extent possible, please include contribution to 2 other SDGs, describing the contribution with a few sentences for each SDG concerned. A complete list of SDGs and their targets is available here: https://sustainabledevelopment.un.org/partnership/register/ | SDG13- Technical Assistance will enable SREDA to - Promote mechanisms for raising capacity for effective climate change related planning and management - Integrate climate change measures into national policies, strategies and planning |

Note: Please see examples of TA Impact Description in adaptation and mitigation at the following link:

https://www.ctc-n.org/sites/www.ctc-n.org/files/learning-reports/18106-ctcnimpactdescriptionv02.pdf

https://www.ctc-n.org/sites/www.ctc-n.org/files/learning-reports/ta_impact_description_2014000002_gcai.doc

Annex 1 - Standardised CTCN performance indicators for donor and UN reporting

Please add quantitative values and qualitative descriptions for indicators relevant to the particular TA in the tables below.  Non-relevant indicators should be left blank.

- Activities and outputs supported by CTCN technical assistance

Please only fill in the table for activities and outputs conducted or produced directly by the CTCN assistance.

| CTCN standardised performance indicators | Quantitative value | Qualitative description List the various elements corresponding to the quantitative value |
| --- | --- | --- |
| Overview |  |  |
| - Number of work days of the international expert team spent on the implementation of the technical assistance | 10 days | Review meeting and consultation with subject experts Meeting with Industry Associations and Designated Consumer Units |
| - Number of work days of the locally-contracted expert team spent on the implementation of the technical assistance | 90 days | Preparation of Syllabus Finalisation of curriculum Design & development of Course material Preparation of model question banks Preparation of Training modules Conduct of Training of trainers programme |
| - Number of external communication and outreach activities conducted to showcase the assistance (news release, newsletters, articles on website, events presenting the results of the technical assistance, social media postings, and presentations at events outside the technical assistance etc.) | Not Applicable | Please list the type of external communications here |
| Events (other than trainings) held as part of the assistance |  |  |
| - Total number of events other than trainings (Aggregation of numbers in categories below) | Aggregation of numbers in categories below | Not Applicable |
| - Number of international and multi-country (at regional or sub-regional level) technology and knowledge sharing events |  |  |
| - Number of participants in the events above |  |  |
| - Number of national technology and knowledge sharing events (national events held including national consultations) |  |  |
| - Number of participants in the events above |  |  |
| - Number of public-private events related to technologies |  |  |
| - Number of participants in the events above |  |  |
| Training and capacity building activities conducted during the assistance |  |  |
| - Number of training sessions and capacity strengthening activities | 14 days | The following modules were covered Module I: ENERGY MANAGEMENT AND AUDIT Module II: ENERGY EFFICIENCY IN THERMAL TECHNICAL EQUIPMENT Module III: ENERGY EFFICIENCY IN ELECTRICAL TECHNICAL EQUIPMENT Module IV: FINANCIAL ANALYSIS BASICS Module V: ENERGY MONITORING,TARGETING AND REPORTING Module VI: ENERGY PERFORMANCE ASSESSMENT Practical lab sessions Visit to Industries |
| - Number of people who received the training | 13 |  |
| - Number of men | 13 |  |
| - Number of women | - |  |
| - Total number of organisations trained | 5 |  |
| - Number of research organisations, laboratories and universities | 2 | - Bangladesh University of Engineering and Technology - Dhaka University of Engineering and technology |
| - Number of private companies | - |  |
| - Number of cities and local government | 3 | - Sustainable and Renewable energy Development Authority (SREDA) - Ministry of Forestry and Environment - Power Cell |
| - Number of communities |  | Not Applicable |
| - Number of ministries | 2 | - Ministry of Power, Energy and Mineral Resources - Ministry of Forestry and Environment |
| - Number of specialised governmental institutions |  |  |
| - Number of non-profit organisations |  |  |
| - Number of participants that were significantly or moderately satisfied after the training (from CTCN training feedback form). | 13 |  |
| - Number of participants that significantly or moderately increased their capacities thanks to the training (from CTCN training feedback form). | 13 |  |
| - Number of men | 13 |  |
| - Number of women | - |  |
| Tools, technical documents and information material supported by the assistance |  |  |
| - Total number of tools, technical documents and information material supported by the assistance (excluding mission, progress and internal reports) |  |  |
| - Number of tools strengthened, revised or developed (including tools, methodology, software, calculation systems, etc.) |  |  |
| - Number of technical documents strengthened, revised or created | 6 | Module I: ENERGY MANAGEMENT AND AUDIT Module II: ENERGY EFFICIENCY IN THERMAL TECHNICAL EQUIPMENT Module III: ENERGY EFFICIENCY IN ELECTRICAL TECHNICAL EQUIPMENT Module IV: FINANCIAL ANALYSIS BASICS Module V: ENERGY MONITORING,TARGETING AND REPORTING Module VI: ENERGY PERFORMANCE ASSESSMENT |
| - Number of other information materials strengthened, revised or created (For example training and workshop reports, Power Points, exercise docs etc.) | 6 | Question Banks and power point slides for Training |
| Policies, laws and regulations supported by the assistance |  |  |
| - Total number of policies, strategies, plans, laws, agreements or regulations supported by the assistance |  | Not Applicable |
| - Number of policies, strategies, and plans drafted addressing climate change adaptation |  | Not Applicable |
| - Number of policies, strategies, and plans drafted addressing climate change mitigation |  | Not Applicable |
| - Number of documents developed to inform other policies, strategies, and plans on climate change adaptation (sectoral strategies, national development plans, etc.) |  | Not Applicable |
| - Number of documents developed to inform other policies, strategies, and plans on climate change mitigation (sectoral strategies, national development plans, etc.) |  | Not Applicable |
| - Number of laws, agreements, or regulations drafted addressing climate change adaptation |  | Not Applicable |
| - Number of laws, agreements, or regulations drafted addressing climate change mitigation |  | Not Applicable |
| - Number of documents developed to inform laws, agreements, or regulations on climate change adaptation |  | Not Applicable |
| - Number of documents developed to inform laws, agreements, or regulations on climate change mitigation |  | Not Applicable |
| Institutional strengthening supported by the assistance |  |  |
| - Total number of institutional arrangements supported to support climate change planning |  | Not Applicable |
| - Number of organisations with increased awareness and knowledge among countries to better own and drive national adaptation planning processes |  | Not Applicable |
| - Number of organisations with increased awareness and knowledge among countries to better own and drive national mitigation planning processes |  | Not Applicable |
| Partnerships and cooperation |  |  |
| Number of private companies directly engaged in the assistance (that partnered with the proponent, the beneficiaries or the CTCN to implement the assistance) (Excluding the role of the CTCN and TA implementers) |  | Not Applicable |
| - Number of South-South collaborations enabled during or through the assistance, when stakeholders from other countries were involved in the assistance (Excluding the role of the CTCN and TA implementers) |  | Not Applicable |
| - Number of North-South collaborations enabled during or through the assistance, when stakeholders from other countries were involved in the assistance (Excluding the role of the CTCN and TA implementers) |  | Not Applicable |
| - Number of Triangular collaborations enabled during or through the assistance, when stakeholders from other countries were involved in the assistance (Excluding the role of the CTCN and TA implementers) |  | Not Applicable |
| UNFCCC planning/support processes |  |  |
| - Number of National Adaptation Plans (NAPs) developed as part of the technical assistance |  | Not Applicable |
| - Number of Nationally Appropriate Mitigation Actions (NAMA) developed as part of the technical assistance |  | Not Applicable |
| - Number of Technology Needs Assessment s(TNAs) developed as part of the technical assistance |  | Not Applicable |

B. Impacts anticipated after completion of CTCN technical assistance: core indicators

Every technical assistance should contribute to at least one indicator below.

| CTCN core indicators | Quantitative value | Unit | Methodology Explain the method or process of verifying the indicator and how data was gathered | Assumptions Indicate assumptions made during quantification | Expected timeline Indicate when the indicator and value are expected to be achieved |
| --- | --- | --- | --- | --- | --- |
| - Total anticipated amount of funding/investment mobilised (in USD) as a result of the TA | - | - | - | - | - |
| - Anticipated amount of public funding mobilised (in USD) from national sources as a result of the TA | - | - | - | - | - |
| - Anticipated amount of public funding mobilized (in USD) from international and regional sources as a result of the TA | - | - | - | - | - |
| - Anticipated amount of private investment mobilised (in USD) from national sources as a result of the TA | - | - | - | - | - |
| - Anticipated amount of private investment mobilised (in USD) from international and regional sources as a result of the TA | - | - | - | - | - |
| - Anticipated number of beneficiaries as a result of a mitigation TA | - Number | -30 | -Confirmation from the industrial unit undergone energy audit | -At least Ten Energy auditors would complete 3 energy audits in the first year of implementation of certification scheme | - |
| - Anticipated number of people with increased resilience as co-benefits as a result of the TA | - | - |  | - | - |
| - Anticipated average the total GHG reductions in metric tons of CO2-e, as a result of the TA | - | - | - | - | - |
| - Anticipated average annual GHG reductions in metric tons of CO2-e, as a result of the TA | - | - | - | - | - |
| - Anticipated and projected greenhouse gas emissions reduced or avoided through 2030, in metric tons of CO2-e, from adopted laws, policies, regulations, or technologies related to clean energy/sustainable landscapes as a result of the TA | - | - | - | - | - |

C. Outputs and impacts anticipated after completion of CTCN technical assistance: standardised performance indicators

| CTCN standardised performance indicators | Quantitative value Insert the request value and unit | Content List the elements included in the number provided | Expected timeline Indicate when the indicator and value are expected to be achieved | Responsible institution Indicate the institution(s) that will play leading role(s) in enabling the indicators and anticipated values to be achieved |
| --- | --- | --- | --- | --- |
| - Anticipated number of policies, strategies, plans, addressing climate change mitigation officially proposed, adopted, or implemented as a result of the TA | -Number 1 | Development of a cadre of Energy Auditors/Energy Managers w- | -one year | -SREDA |
| - Anticipated number of policies, strategies, plans, addressing climate change adaptation officially proposed, adopted, or implemented as a result of the TA. | - | - | - | - |
| - Anticipated number of policies, strategies, plans, addressing climate change on both adaptation and mitigation officially proposed, adopted, or implemented as a result of the TA | - | - | - | - |
| - Anticipated number of laws or regulations addressing climate change mitigation officially proposed, adopted, or implemented as a result of the TA. | - | - | - | - |
| - Anticipated number of laws or regulations addressing climate change adaptation officially proposed, adopted, or implemented as a result of the TA. | - | - | - | - |
| - Anticipated number of laws or regulations addressing climate change both adaptation and mitigation officially proposed, adopted, or implemented as a result of the TA | - | - | - | - |
| - Anticipated number of public-private partnerships and collaboration created (Excluding the role of the CTCN and TA implementers) | - | - | - | - |
| - Anticipated twinning arrangements created as a result of the TA | - | - | - | - |
| - Anticipated number of technology projects to support action on low emission and climate-resilient development | - | - | - | - |
| - Anticipated number of strengthened National Systems of Innovation and technology innovation centres in recipient country | - | - | - | - |
| - Anticipated Clean Energy Generation Capacity in kWh supported by the TA | - | - | - | - |
| - Anticipated technology types effectively deployed in the country | - | - | - | - |
| - Anticipated UNFCCC processes implemented as a result of the TA (NAMA, NAPA, NDC, etc.) | - | - | - | - |
| - Anticipated Technology Needs Assessments (TNA) and technology Action Plans (TAP) as a result of the TA | - | - | - | - |
| - Anticipated cooperative research, development and demonstration programmes within and between developed and developing country Parties facilitated as a result of the TA | -Number 1 | -Development of a cadre of Environmental Auditors/Managers | -October 2019 – July 2020 | -Department of Environment Govt.of Bangladesh |
| - Anticipated improved climate change observation systems and related information management in developing country Parties. | - | - | - | - |