NDC Partnership Climate Action Enhancement Package (CAEP)

Terms of Reference for Guatemala

Supported by

- United Nations Development Programme (UNDP)

- United Nations Environment Programme (UNEP)

- Red Cross Climate Centre

# Objective of the technical assistance

# The Climate Action Enhancement Package (CAEP) assists developing countries, member of the NDC Partnership, in achieving two overarching objectives:

- Objective 1: Enhance NDCs, including by raising ambition, as part of the Paris Agreement’s NDC update process;

- Objective 2: Fast-track implementation of NDCs, including by providing in-country technical expertise and capacity building.

The present terms of reference are intended to guide institutional and associate members, as well as developed country members (through their national development agencies) of the NDC Partnership, hereby referred to as the ‘implementing partners’, in the delivery of support to the recipient country. The terms of reference are developed by the NDC Partnership Support Unit, in coordination and consultation with implementing partners and relevant authorities of the recipient country. The terms and delivery of support by implementing partners are contigent on the approval from the recipient country.

# Key principles

All implementing partners need to ensure that while implementing the technical assistance (TA), the following principles are adhered to:

- Work under the leadership and guidance the governments;

- Ensure a partnership-based approach, whereby the implementing partner is expected to coordinate with other partners supporting CAEP activities in country and draw expertise from the vast network of the NDC Partnership institutional and associate members;

- Promote participation of the key government ministries (including Ministry of Finance or Planning and sectoral ministries) and other relevant stakehodlers throughout the process of updating the NDCs;

- Ensure country presence throughout the assignment, relying on local expertise to the extent possible. The delivery team must support strengthened capacity at the national level;

- Apply gender principles to approach the assignment and wherever possible produce gender-disaggregated data and gender-specific actions;

- Develop the capacity of the Government for updating NDCs, throughout the entire duration of the TA; and

- Share information on progress on a periodic basis.

The recipient country commits to:

- Ensure government ownership over the process, providing decisions and approvals throughout the CAEP process;

- Apply a whole of society consultation approach ensuring multiple opportunities for stakeholders to provide inputs;

- Promote participation and ownership of the Ministry of Finance or Planning and other key spending ministries as well as key sectoral ministries throughout the process of updating the NDCs;

- Ensure CAEP support is coordinated with national development plans and policies and, domestic budgeting processes.

# Reporting

# Implementing partners are responsible for reporting to authorities of the recipient country on the progress of the support being provided in response to the country CAEP requests.  The implementing partners will ensure that the CAEP team  within the NDC Partnership Support Unit is kept informed of progress. The partners will send progress reports to CAEP (caep@ndcpartnership.org) on a quarterly basis that reports on:

- Progress against work plans and deliverables

- Any technical issues, including any potential deviation from the work plan or updated risk matrix, for consideration;

- Feedback on implementation issues requiring attention from other partners.

# Activity matrix

Instructions: Please complete the table below, providing a detailed description of the work activities that address the country’s CAEP request. Provide the total cost of the work to be performed and the expected timeline. All support provided under Objective 1 must be completed by the end of Q4 2020. Support under Objective 2 must be completed by the end of Q1 2021.

- Annex 3 to this TOR includes an example of a completed activity matrix, please consult the example as a reference.

- The “Objective”, “Country request” and “Activity code” columns will reflect original information provided in the full list of CAEP country requests.

- In the “Description of activity” column, please explain in no more than 100 words, the actions and type of support that will be provided to fulfil the country’s request. Country requests that will be responded to through one overall activity can be bundled into one response (see example for A0YY and A0ZZ). In the “Implementing partner(s)” column, please insert the name of the organization(s) who will respond to the country’s request(s), through the described activities.

- In the “Existing partner support” column, please include any existing support, that you are aware of, for this activity. Please include support you are already providing, as well as known support that other implementing partners are providing.

- In the “Total cost” column, please insert the overall cost of implementing the described activities in US dollars. In the “Timeline” columns, please indicate each quarter when work activities will take place and finish.

| a | b | c | d | e | f | g | h |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CAEP Objective | Country request | Activity code | Description of activity responding to country request (100 words) | Implementing partner(s) | Existing partner support | Total cost (in US$) | Timeline |  |  |  |  |  |
|  |  |  |  |  |  |  | 19 | 20 |  |  |  | 21 |
|  |  |  |  |  |  |  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 |
| Objective 1. NDC Revision and Raising Ambition | Developing a systemic vulnerability assessment of the Guatemalan extended Dry Corridor. The identified areas will be used to determine percentage of populations and areas of high climate change impact risk. Data will contribute to defining local adaptation goals in the agriculture, livestock and food security sectors. | A357 | - Analysis of complementarities with the CTCN TA previously implemented in the country - Vulnerability analysis with creation of indicators from the dry corridor area - Analysis for the prioritization of project areas - Inception workshop with relevant national stakeholders to present the methodology to be used - Local data analysis and matching with national climate processes and commitments (NDC, NAP, TNA, etc), in collaboration with local stakeholders; - Vulnerability assessment of the Guatemalan extended Dry Corridor to determine percentage of populations and areas of high climate change impact risk. - Fine-tuning of country adaptation goals in the agriculture, livestock and food security sectors and selection of a pilot project per sector. National plans and climate regulation to take into account the results of this work in light of raising ambition; - Concept note preparation for a funding mechanism (i.e. GCF) on one prioritised project - 02 national workshops to present the results to relevant ministries and stakeholders | UNEP | CTCN National Designated Entity (NDE): Mr. Carlos Walberto Ramos Salguero Position: Vice Minister of Natural Resources and Climate Change Ministerio de Ambiente y Recursos Naturales | 166,000 |  | X | X | X | X |  |
| Objective 1. NDC Revision and Raising Ambition | Generating the 2018 GHG inventory and projections for the Industrial Processes Sector, including a description of the methodology and comparison with the baseline (1990-2015). It includes a training for MARN officials and the corresponding sectoral task forces to support transparency and the definition of the enhanced NDC goals. | A358 |  | UNDP |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Generating the 2018 GHG inventory and projections for the Waste Sector, including a description of the methodology and comparison with the baseline (year 2010). It includes a training phase with MARN officials and the corresponding sectoral task forces in order to support transparency and the definition of the enhanced NDC goals. | A359 |  | UNDP |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Developing workshops for high-level authorities of the new government to strengthen governance mechanisms (Sectoral Task Forces) for updating/implementing the NDC. This will confirm roles and responsibilities for reporting and exchanging information among government entities in the NDC update process. Financial resources and technical assistance to develop workshops are required. | A360 |  | UNDP |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Updating the original NDC multi-sector roadmap prepared by the NDC Partnership in order to guide the implementation and evaluation process for the updated NDC. This roadmap will outline strategies, indicators and goals for strengthening governance, access to financial resources, and monitoring and evaluation of the roadmap. | A361 |  | UNDP |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Designing implementation strategies related to the updated NDC for sectoral adaptation actions in the Human Health and Water Resources Management sectors under the leadership of the Ministry of Health (MSPAS) and MARN, respectively. The strategies will define priority guidelines, indicators, and goals to meet the updated NDC of both sectors. | A362 |  | Unsupported* |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Developing six workshops under the leadership of MARN and SEGEPLAN to contribute to the NDC update process. Institutional roles and responsibilities will be reviewed for the implementation of the updated NDC. Parliaments related to climate change of the National Congress will be invited. | A363 |  | UNDP |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Developing two rounds of workshops with five mitigation sectors in order to update and validate mitigation targets. These workshops will be developed through the sectoral mitigation task forces. | A364 |  | UNDP |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Developing two rounds of workshops with four adaptation sectors (agriculture, livestock and food safety; coastal marine zones; human health; water resources management) in order to define and validate climate change adaptation goals. These workshops will be developed through the sectoral adaptation task forces. | A365 |  | Unsupported* |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Developing two final workshops led by MARN with representatives of all Sectoral Task Forces to validate and communicate the updated NDC | A366 |  | UNDP |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Developing a cost-benefit analysis of priority adaptation actions associated with the Agriculture, livestock and food security sector and the Marine Coastal Zones sector to prioritize indicators, metrics and activities that will be included in the updated NDC. | A367 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Developing a cost-benefit analysis of priority mitigation actions related to the Waste and Industrial Processes sectors. This will guide the prioritization and incorporation of activities within the updated NDC. | A368 |  | UNDP |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Developing training activities with MAGA and MARN related to the cost-benefit analysis of adaptation actions in the agriculture, livestock and food security and Marine Coastal Zones sectors, as well as MARN and other ministries relate to mitigation actions in the Waste and Industrial Processes sectors. | A369 | - Determine if the cost-benefit analysis of adaptation actions in agriculture, livestock and food security and Marine Coastal zone sectors was developed and obtain the information on the key experts that developed the analysis. - Coordinate with UNDP on the cost-benefit analysis of priority mitigation actions (Waste and Industrial Processes sectors) and obtain information on the key experts that developed the analysis. - Coordinate with experts the time needed to conduct training activities. - Coordinate with MAGA and MARN, as appropriate, the number of people that will receive training - Draft agenda for the trainings with experts and relevant stakeholders. - Coordination with all proposed participants: manage invitations and RSVPS, electronically distributing material related to training to participants before, during and after the trainings. - Conduct trainings: select, reserve, cover cost for, and coordinating logistics for the venue, signage and associated A/V, and provide on-the-ground support to training speakers and participants. | UNEP | While Guatemala is not a CCAC partner country, CCAC is working with SICA/CCAD on a roadmap for several countries in Central America, including Guatemala. | $129,250 | s |  |  | f |  |  |
| Objective 1. NDC Revision and Raising Ambition | Carrying out cost assessments for the implementation of updated NDC actions based on the alignment of the proposed National Low GHG Emissions Development Strategy with the Waste and Industrial Processes sectors´. | A370 | - Coordinate with UNDP on the updated NDC actions for the waste and industrial processes sectors. - Obtain the elements on waste and industrial processes sectors of the proposed National Low GHG Emissions - Assess the cost of implementing the updated NDC actions. The assessment will describe each action in detail, specifying the level of importance, expected time of implementation, resources needed, and responsibility for implementation. | UNEP | While Guatemala is not a CCAC partner country, CCAC is working with SICA/CCAD on a roadmap for several countries in Central America, including Guatemala. | $59,400 |  | s |  |  | f |  |
| Objective 1. NDC Revision and Raising Ambition | Generating a methodology for determining the activity data for the GHG inventory of the waste sector and identifying reliable sources of information. This will facilitate the collection of data and analysis of reliable projections. The quality of activity data will ensure a continuous improvement of the GHG projection information. | A371 |  | UNDP |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Coordinating and capacity with the National Statistics Institute (INE) to improve the processes of collecting, exchanging and recording information to support the five-year updates of the NDC. | A372 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Encouraging the participation and capacity-building of stakeholders of the Waste Sector Task Force to design inter-institutional arrangements for information exchange. The inclusion of information exchange agreements, quality control and quality assurance (QC and QA) will be defined to ensure the metric reliability of goals in the updated NDC. | A373 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Promoting south-south cooperation to exchange experiences and lessons learned with countries of the Region (e.g. Mexico, Chile) related to the process of updating NDCs. This will allow for an analysis of identified experiences, good practices and/or bottlenecks. | A374 |  | UNDP |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Aligning the mitigation and adaptation goals of the updated NDC with the PANCC. This will facilitate monitoring and evaluation of the PANCC, aiming for the continuous improvement of its implementation and will facilitate its operational planning of the institutional actions proposed in it. | A375 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Aligning the proposed National Low GHG Emissions Development Strategy (long-term strategy to 2050) and its mitigation options with the updated NDC in order to develop sectoral mitigation actions in the Waste and the Industrial processes sectors under the leadership of MARN. | A376 | The work proposed below refers to waste and industrial process sectors. The activities will be carried out in close collaboration with and under the guidance of MARN. - Review the proposed National Low GHG Emissions Development Strategy and its mitigation options - Review the updated NDC - Analysis of existing waste and industrial sector supply chain based on local data provided by MARN - Selection of appropriate climate technologies and provision of sectoral mitigation actions to Align the mitigation options proposed under the new Strategy with the updated NDC and to identify sectoral mitigation actions gaps for the sectors - Propose changes to mitigation options in the proposed Strategy to fulfil the updated NDC - Aligning the proposed National Low GHG Emissions Development Strategy (long-term strategy to 2050) and its mitigation options with the updated NDC in order to develop sectoral mitigation actions in the Waste and the Industrial processes sectors. - Final workshop to presents the results of the TA to relevant stakeholders | UNEP | While Guatemala is not a CCAC partner country, CCAC is working with SICA/CCAD on a roadmap for several countries in Central America, including Guatemala. CTCN has a focal point (National Designated Entity) in Guatemala CTCN National Designated Entity (NDE): Mr. Carlos Walberto Ramos Salguero Position: Vice Minister of Natural Resources and Climate Change Ministerio de Ambiente y Recursos Naturales | $84,700 (42,350 including CTCN budget, 42,350) |  | X | X | X |  |  |
| Objective 1. NDC Revision and Raising Ambition | Designing the updated NDC implementation strategies for sectoral adaptation actions in the Human Health and Water Resources Management sectors conducted by the MSPAS (Health Ministry) and MARN. These strategies will define priority guidelines, indicators, and goals to meet and mainstream the updated NDC in both sectors. | A377 |  | Red Cross Climate Centre |  |  |  |  |  |  |  |  |
| Objective 1. NDC Revision and Raising Ambition | Presenting the proposed National Low Emissions Development Strategy (long-term strategy 2050) to the new government authorities and the Mitigation Sectoral Task Force. This will facilitate institutional commitments for aligning the strategy with the updated NDC. | A378 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 2. Fast-tracking NDC Implementation | Defining a macroeconomic model for the Forestry and Other Land Use (FOLU) mitigation sector to assess the economic impact derived from emissions produced, and identifying high emissions activities that could be income sources and promote the reduction of GHG emissions. | A379 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 2. Fast-tracking NDC Implementation | Assessing the potential of options for encouraging investments in the FOLU sector. This could include instruments to encourage private sector investments and/or designing government incentives/subsidies to promote low emissions activities in the FOLU sector | A380 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 2. Fast-tracking NDC Implementation | Reviewing and updating the information generated by the Green Climate Fund Programme and UNDP Biodiversity Finance Initiative (BIOFIN) regarding the climate change finance status (financing opportunities, public expenditure, needs and financial gaps), which will allow financial sources to be linked to the updated NDC. | A381 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 2. Fast-tracking NDC Implementation | Developing a strategic investment programme for the implementation of the updated NDC. It will be aligned to the national planning scheme. Updating existing financial sources and identification the access routes will be developed. An official presentation will be given to the International Cooperation Agencies in Guatemala (G13). | A382 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 2. Fast-tracking NDC Implementation | Implementing the Climate Budget Tag (CBT) to monitor and track the public expenditure in mitigation and adaptation in the Ministry of Agriculture, Livestock and Food (MAGA). An identification of mitigation and adaptation actions in the institutional planning framework will be developed. | A383 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 2. Fast-tracking NDC Implementation | Designing a CBT monitoring matrix linking institutional policies and adaptation and mitigation budget to tag its climate expenditure and align to the updated NDC. This matrix will consider the UNFCCC finance guidelines. | A384 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 2. Fast-tracking NDC Implementation | Building institutional capacities in the MAGA to improve the understanding of the identification and tagging process of the adaptation and mitigation actions and the use of the CBT monitoring matrix. | A385 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 2. Fast-tracking NDC Implementation | Disseminating the Climate Budget Tag Implementation Guidelines throughout the climate change related government agencies. The process includes presenting the technical and administrative procedures to tag climate public expenditure for strengthening the national climate expenditure report and its relation in reducing financial gaps toward the accomplishment of the updated NDC. | A386 |  | Unsupported |  |  |  |  |  |  |  |  |
| Objective 2. Fast-tracking NDC Implementation | Identifying projects in the Waste and Industrial Processes mitigation sectors including finance sources (e.g. private, public and international). The project portfolio will be led by the MARN and will be oriented to the achievement of the updated NDC through the strategic investment programme for the updated NDC implementation. | A387 |  | Unsupported |  |  |  |  |  |  |  |  |

# Description of approach for building local capacity

Instructions: Describe what special measures or activities will be taken to ensure national capacity is strengthened through the CAEP support. Provide your answer in no more than 250 words.

[Implementing Partner Name]

Describe how your support under Objective 1 will build capacity in this country.

Describe how your support under Objective 2 will build capacity in this country.

Country capacity will be built thanks a close collaboration between MARN and other relevant local stakeholders with the selected implementing organization from the CTCN Network. Two main meetings are foreseen in this TA in order to engage with local counterparts: an inception meeting and a final workshop to present the results and share them with a wider audience in the country so to make sure that the NDC process has been updated and strengthened.

# Annex 1. Implementing Partner Risk Management Matrix

Instructions: This table is intended to identify and categorize the risks associated with the implementation of CAEP activities in the country. Risks should be focused at the aggregate country level (do not provide individual risks for each activity). Indicate the related impact with each risk and the risk probability (high, medium or low). For all risks, a mitigation measure must be provided.

| [Implementing Partner Name] |  |  |  |
| --- | --- | --- | --- |
| Risk | Impact (High, Medium, Low)The | Probaility (High, Medium, Low) | Mitigation Measures |
| EXAMPLE: Political election cycles slows down work activites. | M | M | CTCN has its focal point in the ministry of environment who will be able to continue work activities, despite election cycles or changes in political leadership. The organization will build relationships with non-appointed staff to be able to continue work during election cycles. CTCN has recently concluded an adaptation TA supporting the National Climate Change Information System in Guatemala and is following up with the country to make sure that the outcomes of that intervention are informing a national low endorsement. This will keep the collaboration with the focal point active and prevent the relationship with the country from slowing down. |
| Lack of data to quantify emissions from key source sectors | M | M | The MARN will be the key partner to obtain related data about the sectors under scrutiny (waste, industrial sector). In case of lack of data, the missing ones will be complemented with literature data and through assumptions based on on-site assessment of local industries |

# Annex 2. Detailed Budget for TAF

Instructions: Please provide a detailed budget for all activities to be carried out under CAEP for which you are requesting TAF resources. Reference the activity code at the top of each column. If activities are being bundled, please reflect the same bundling applied in the Activity Matrix (Section 5) and provide one combined budget. The budget file includes examples: Examples 1 and 2 show responses under Option 2, Example 3 shows a response under Option 3 and Example 4 shows an example of a bundled activity. The grand total (row 14) should reflect the total activity cost, including co-financing and TAF resources.

- Option 1: The implementing partner commits to using its own resources to address the country request and no TAF resources are requested.

- Option 2: The implementing partner requests co-financing from TAF to address the country request.

- Option 3: The implementing partner requests full financing from TAF to address the country request.

Budget Notes: Budget categories are representative and can be modified to algin with the organizations’s cost structure. Budget categories as generally described as:

- Personnel: Includes all costs for employees or persons working under a direct contract.

- Travel: Includes travel and associated subsistence costs related to the delivery of the activity. This includes travel to meetings, workshops, and other relevant events.

- Sub-granting: Includes any grants made by a partner to another organization

- Sub-contracting: Additional contracts issued to third-party persons or organizations to provide part or all of the activity under the original contract.

- Other Costs: Include other goods and services directly purchased (not subcontracted) to ensure the delivery of the activity. This could include consumables, room hire, catering, printing, etc.

- Administrative Overheads: Include indirect or fixed expenses costs not directly related to the delivery of the activity.

# Annex 3. Activity Matrix Examples

The table below provides an example of a completed activity matrix to be filled out by implementing partners and approved by the Government. It will show all partners providing support against country CAEP requests, and the details of that support.

| a | b | c | d | e | f | g | h |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| CAEP Objective | Country request | Activity code | Description of activity responding to country request (100 words) | Implementing partner(s) | Existing Partner support | Total cost (in US$) | Timeline |  |  |  |  |  |
|  |  |  |  |  |  |  | 19 | 20 |  |  |  | 21 |
|  |  |  |  |  |  |  | Q4 | Q1 | Q2 | Q3 | Q4 | Q1 |
| 1 | EXAMPLE: Convening an inter-ministerial NDC planning workshop to adopt new NDC targets, with clearly defined roles and responsibilities for line ministries. Organize and host three inter-ministerial steering committees with key decision makers in line ministries and high-level offices, including cabinet, parliament or office of the president. | A0VV | EXAMPLE: Organize and convene an inter-ministerial NDC planning workshop, including venue booking, catering, and support for attendees with travel/logistical support. Record workshop minutes, decisions or other outputs and disseminate information to workshop attendees. | Organization X | Organization X has been supporting this activity as part of its ongoing NDC support project | $85,375 | X | X | X |  |  |  |
| 2 | EXAMPLE: A blended finance strategy for investment projects with NDC implementation gains. Design of options for combining multiple sources of funding, including, but not limited to: domestic resources, concessional loans, commercial loans, user fees, private investment or other, to finance new projects or joint ventures for public use/good. | A0WW | EXAMPLE: Develop a blended finance strategy for NDC implementation, including multiple options for NDC finance instruments, arrangements, partnerships or other options. Convene stakeholder consultation workshops to engage whole of society and government in NDC implementation strategies. Convene a validation workshop to present final strategy to high-level government officials and other stakeholders. | Organization X | Organization Y is carrying out analysis on financial mechanisms which will feed into this work | $38,000 |  |  | X | X | X | X |
| 1 | EXAMPLE: Developing a 10-year plan for NDC implementation. Prioritization of specific actions to be undertaken in the near and long term. Determine options for achievable but ambitious targets to be adopted, with legislation necessary to achieve longer term, more ambitious goals, which may include a zero-carbon economy by XX date. | A0XX | EXAMPLE: Develop a 10-year plan for NDC implementation, including work activity phasing, and multiple options for achieving NDC targets. Provide analysis of legislation for long-term, low-carbon options, including analysis for a zero-carbon target. | [NAME] |  | $45,000 |  |  | X | X |  |  |
| 2 | EXAMPLE: An NDC investment plan that includes a pipeline of investment ready projects that contribute to NDC targets. Project identification, prioritization and assessment for investment readiness and emission abatement potential compiled within a centralized plan that can be ‘marketed’ to external sources of finance. Preparing projects for investment from international climate finance sources or private investment. Support to Ministry of Finance for taking investment projects from pre-development through feasibility to bankability, with corresponding capacity building to external resource mobilization units on project preparation and finance strategizing. | A0YY, A0ZZ | EXAMPLE: Develop an NDC investment plan, that includes a pipeline of projects to be readied for financing and structuring, with project sequencing, potential funding sources and finance strategy. As part of investment plan development, develop two projects for full bankability, bringing through to feasibility stages and risk analysis. | [NAME] |  | $437,500 |  | X | X | X | X | X |