## Implementation Plan
Implementation Plan Date: 13/05/2026
N° | Activity | 2026 | [48 empty] | 2027
| Months | Jan |  |  |  | Feb |  |  |  | March (1) |  |  |  | April (2) |  |  |  | May (3) |  |  |  |  | June (4) |  |  |  | July (5) |  |  |  | Aug (6) |  |  |  | Sept (7) |  |  |  | Oct (8) |  |  |  | Nov (9) |  |  |  | Dec (10) |  |  |  | Jan (11) |  |  |  | Feb (12) |  |  |  | March (13) |  |  |  | April (14) |  |  |  | May (15) |  |  |  |  | June (16) |  |  |  | July (17) |  |  |  | August (18)
| Weeks | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 5 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 5 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
A: Pre-implementation
A.1 | Detailed work plan of all activities
A.2 | Gender evaluation and gender action plan
D.A. | Detailed work plan; M&E plan; gender assessment and gender action plan
Output 1: Inception workshop and technology options
1.1 | Multi-stakeholder inception workshop to validate objectives, methodology, and roles
1.2 | Feasibility studies on solar-powered irrigation, greenhouses, and agroforestry (field assessments, best-practice review, and farmer consultations).
1.2.1. Site Assessments
1.2.2. Technology Review
1.2.3. Stakeholder Engagement
1.2.4. Preliminary Technical Recommendations
1.3 | Cost-benefit analysis of technology options, including water resource sustainability and maladaptation risks.
1.3.1. Cost-Benefit Data Collection
1.3.2. Water Resource Appraisal
1.3.3. Socio-Economic Analysis
1.3.4. Risk of Maladaptation
1.3.5. Consolidated CBA Report
1.4 | Development of a practical “technology menu” with farmer-oriented guidelines.
1.4.1. Synthesis of Findings
1.4.2. Technical Specifications
1.4.3. Dissemination
1.4.4. Stakeholder Validation
B1: | PSC biannual meeting
D1.1 | Inception workshop report including the list of stakeholders, meeting minutes with the list of participants, disaggregated by gender, materials used for the workshops and photos of the event.
D1.2 | Feasibility study report (solar irrigation, greenhouses, agroforestry).
D1.3 | Cost-benefit analysis report (including water resource assessment and maladaptation risk management).
D1.4 | Technology menu (catalogue/fact sheets) with practical guidelines for farmers.
D.B1. | Project Steering Committee meeting report
Output 2: Policy and Legislative Framework for Standards
2.1 | Review existing policies and standards for irrigation, agroforestry, and greenhouse infrastructure.
2.2 | Develop a national guideline and certification standards for solar-powered irrigation, including thresholds for sustainable water usage.
2.3 | Propose updates to incorporate agroforestry guidelines into relevant policies or standards.
B2: | PSC biannual meeting
D2.1 | Policy review report detailing gaps in current frameworks.
D2.2 | National guidelines and certification standards for solar-powered irrigation, incorporating water usage thresholds.
D2.3 | Recommendations for integrating agroforestry standards into policy frameworks.
D.B2. | Project Steering Committee meeting report
Output 3: Financing Structure and Digitalized Insurance Scheme
3.1 | Engage financial institutions to design a blended finance facility for smallholders, leveraging public and private funding
3.2 | Assess and design a digitalized insurance product tailored for smallholder vegetable farmers, exploring AI, remote sensing, or picture-based approaches.
3.3 | Identify partnership and risk-sharing structures (e.g. guarantee funds, reinsurance) to lower premiums and expand coverage.
D3.1 | Blended finance facility proposal (structure, term sheets, risk-sharing mechanisms).
D3.2 | Digital crop insurance product concept note with an operational roadmap (coverage, premium ranges, distribution).
D3.3 | Partnership & risk-mitigation framework (agreements, MOUs, or draft legal documents).
Output 4: Capacity Building and Training
4.1 | Develop bilingual training materials and curricula on irrigation, greenhouse management, agroforestry, and insurance literacy.
4.2 | Deliver provincial training workshops, train-the-trainers modules, and gender-focused sessions.
4.3 | Establish or upgrade provincial centers of excellence (with demonstration sites for solar irrigation and agroforestry).
B3: | PSC biannual meeting
D4.1 | Training materials and curricula (in local language and English), including user manuals and guidelines
D4.2 | Training workshops completed in each target province, with participant lists disaggregated by gender.
D4.3 | Train-the-Trainers Program documented with follow-up plans.
D4.4 | Centers of excellence established or upgraded in Dundgobi and Uvurkhangai provinces.
D4.5 | Final workshop report and in-person presentations.
D.B3. | Project Steering Committee meeting report
Output 5: Implementation Roadmap and Sustainability Financing Strategy, including two Scale-up Project Concept Notes
5.1 | Consolidate findings into a phased roadmap (short-, medium-, long-term) for scaling nationally.
5.2 | Develop a sustainable financing strategy, including two bankable scale-up project concept notes for submission to donors (e.g., GCF, IFAD, ADB).
5.3 | Present results in a final in-person workshop.
D5.1 | Implementation roadmap document with short-, medium-, and long-term actions.
D5.2 | Sustainable financing strategy, including two scale-up project concept notes with the package of supporting documents.
D5.3 | Final report and in-person presentations. Final compiled deliverable, combining deliverables 1, 2, 3, 4 and 5 into a final report
C: Post-implementation
C1 | Post-implementation: Closure and Data Collection report
C2 | Project-end communication and dissemination activities
B3: | PSC biannual meeting
D.C1. | Closure and Data Collection report
D.C2. | Press release, webinar, dialogue with financial institutions
D.B3. | Project Steering Committee meeting report